## SGE LFV
▶ MY18_E2UL_CSS 50T Gamma_DYNO Subsystem Test Daily Report
SN | ENG NO. | Engine Status | Test Item | Cell | 2017 |  |  |  |  | 2018 |  |  | Target | Current | Remark | Test Status | SOT Status | Engineer | Test Fuel
[5 empty] | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3
1 | LYX*153233005* | Gamma | Ventilation System Test | PATAC 5E01 | [8 empty] | 100% | 100% |  | Ongoing | NA | Wang libin | 95RON Marketing
2 |  | Gamma | Thermal Survey (Contain TC shutdown) | AVL ETC10 | [11 empty] | Not start | NA | Wang libin | 95RON Marketing
3 | C9SYG094AD | Gamma | Exhaust valve thermal survey(Special Valves) | PATAC 5E01 | [11 empty] | Not start | NA | Wang libin | 95RON Marketing
4 | C9SYG094AD | Gamma | spark plug thermal tests(heat range) | PATAC 5E01 | [8 empty] | 100% | 100% |  | Finished | NA | Wang libin | 92RON marketing
5 | C9SYG094AD | Gamma | Damper pulley Tuning | PATAC 5E01,EP4 | c | [7 empty] | 100% | 100% |  | Finished | NA | Wang libin | 92RON marketing
NA
Original Plan
Actual plan
Forecasting finish plan
Gamma DC

## Sheet1
Test List | Test Site | Test Engineer
Component friction | Rig-Friction | Wang libin
Port Flow test | Rig-Flow | Cheng Yi
Templug | Rig-3155
Thermal Survey (Contain TC shutdown) | Rig-Valvetrain
Valvetrain Dynamic Rig test | Rig-Cooling
Timing Chain Perfomance | PATAC EP1
Exhaust valve thermal survey(Special Valves) | PATAC EP2
Exhaust valve thermal survey(Real time)
Damper pulley Tuning | PATAC EP4
Piston peak temperature(Templug) | AVL ETC3
TC Oil Sealing Test | AVL ETC10
TC Shutdown | AVL PTC1
Intake system flow test | AVL ETC6
Exhaust system flow test | PATAC 5E01
spark plug thermal tests(heat range) | PATAC 5E01,EP4
EGR Cooler fouling
Injector Coking
Injector temperature survey test
Cooling Rig
Warm up
Oil dipstick calibration
Lubrication Test
Lube System Cold evaluation ( really cold -30C， warmup included)
Tilting Test
Ventilation System Test
Cooling 3155
High oil pressure 3155
oil spray 3155
Air Leak