## Sheet1 (2) (hidden)
pickup | RPO | Test | Plant | dyno | Purpose | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug |  | Sep | Oct |  | Nov |  | Dec
| L3A |  |  |  | OTS车，25台
| L3A |  |  |  | PPV车，22台
| L3A |  |  |  | PPAP,300台 | [8 empty] | 1 |  |  | 2
| LYX |  |  |  | PPV车，20台.8月22日
| LYX |  |  |  | PPAP,300台 | [13 empty] | 1 |  | 2
5月30日，共6台（2备+1 cordwood) | LFV | GED | WH | Yantai | 陆磊——住友曲轴（4月15日毛坯到PATAC)，活塞销（已有）验证 朱敏婧-进气凸轮轴、排气凸轮轴、国产化弹簧座
| LFV | GED | WH | Yantai | 陆磊——住友曲轴（4月15日毛坯到PATAC)，活塞销（已有）验证 朱敏婧-进气凸轮轴、排气凸轮轴、国产化弹簧座
| LFV | GETC | WH | FM | 张灏俊——增压器隔热罩，4个月——TBD 钱顾军——油底壳(5月零件可ok） 胡斌-EK气缸垫？
8月15日，共9台 | LFV | GED | WH | MAHLE | 陆磊——活塞加强验证，住友曲轴（4月15日毛坯到PATAC)，活塞销（已有）验证
| LFV | GED | WH | MAHLE | 陆磊——活塞加强验证，住友曲轴（4月15日毛坯到PATAC)，活塞销（已有）验证
| LFV | GEHS | WH | Yantai | 陆磊——活塞加强验证，住友曲轴（4月15日毛坯到PATAC)，活塞销（已有）验证
| LFV | GCSD | WH | Yantai | 陆磊——活塞加强验证，住友曲轴（4月15日毛坯到PATAC)，活塞销（已有）验证
5月4日，共17台 | LYX | GED | WH | PATAC | 朱敏婧——VVT（4月1日到）、凸轮轴（4月1日到）OTS验证 钱鹏——加长螺栓（4月1日到） 唐宁-水泵 D2UC NCT 13台
| LYX | GED | WH | PATAC | 朱敏婧——VVT、凸轮轴OTS验证 钱鹏——加长螺栓 唐宁-水泵
7月20，共4台 | L3A | GED | WH | PATAC | 徐超——油轨，油泵壳体国产化（6月1日到），EGE cooler？
| L3A | GED | WH | Yantai | 徐超——油轨，油泵壳体国产化（6月1日到）
6月30日，共4台 | LFV | GED | Nor | Yantai | 陆磊——CIE南京2线（4月30日毛坯到） 国产化连杆
| LE2 | GED | Nor | Yantai | 陆磊——CIE南京2线（4月30日毛坯到） 国产化连杆 （胡斌——EK气缸垫）
| LE2 | GED | Nor | Yantai | M2验证
| L3G | GED | Nor | Yantai | 陆磊-国产化连杆
造机大致时间
造机时间
特殊零件MRD至泛亚
试验时间
*特殊零件清单必须在MRD前两周锁定
Note on AJ4: MVBP2.0: 8月8日

## CSS 45T E2SC GAMMA2
▶CSS 45T3 L3Z E2SC GAMMA2 DYNO Validation Plan&Status
SN | ENG NO. | Engine Status | Test Item | Cell | 2017 |  |  |  |  | 2018 |  |  | Target | Current | Remark | Test Status | SOT Status | Test Fuel
[5 empty] | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 6
1 | C93ZG102AA | Gamma2 | GED | PATAC 5W05 | [8 empty] | 407 cycles | 0 cycle | Engine failure, desired and measured intake cam position didn't match, and we will setup new engine, wait for new engine. Responsibility: Huang Qian Due date: 2017.9.30 | Terminate | Green | 98RON Special
1-1 | C93ZG119AA | Gamma2 | GED | PATAC 5W04 | [8 empty] | 407 cycles | 79 cycle | Engine oil_t over 125degC, and oil analyse result is abnormity, remove the engine. Responsibility: Yang Jing Due date: 2017.10.12 We will setup new engine, wait for engine. Responsibility: Huang Qian Due date: 2017.10.15 | Terminate | Green | 98RON Special
2 | C93ZG119AA | Gamma2 | GED | PATAC 5W04 | [8 empty] | 407 cycles | 71 cycles | Engine oil leak from LCE, PPO will relace it. Responsibility: Huang Qian/Zhou Yinjun Due date: 2017.9.21 Engine oil leak from Cam Cover, PPO will replace it and then do hot-test by SJTU to confirm there won't be oil leak, and back to PATAC to set up. Responsibility: Huang Qian/Zhou Yinjun/Ma Yiming Due date: 2017.9.30 | Running Incident | Green | 95RON Low FD
1-2 | C93ZG115AA | Gamma2 | GED | PATAC 5W05 | [8 empty] | 407 cycles | 62 cycle | Engine can't start, the crankshaft can't rotate manually, wait for teardown result. Failure Date: 2017.11.07 | Terminate | Green | 98RON Special
2 | C93ZG103AA | Gamma2 | GED | PATAC 5W05 | [8 empty] | 407 cycles | 215 cycle | 2nd exhaust valve broken from cyl#1, which damaged the piston. Failure Date: 2017.11.01 | Terminate | Green | 98RON Special
2-1 | C93ZG116AA | Gamma2 | GED | MAHLE | [8 empty] | 407 cycles | 0 cycle | Dyno setup Responsibilty: Ma Yiming Due Date: 2017.11.13 | Work in progress | Green | 98RON Special
3 | C93ZG104AA | Gamma2 | GETC | PATAC 5E08 | [8 empty] | 8900 cycles | 500 cycle | Dyno equipment issue, test paused, AVL engineer is working on it. Responsibility: Yang Jing Due Date: 2017.11.12 | Work in progress | Green | 98RON Special
4 | C93ZG105AA | Gamma2 | GETC | PATAC 5W04 | [8 empty] | 8900 cycles |  |  | Not start | Green | 98RON Special
5 | C93ZG106AA | Gamma2 | GDTS | PATAC 5W02 | [8 empty] | 1000 cycles |  |  | Not start | Green | 98RON Special
6 | Engine06 | Gamma2 | GCSD | DIAS | [8 empty] | 90 cycles |  |  | Not start | Green | winter high&low RVP-GCSD
7 | C93ZG108AA | Gamma2 | GLSD | SJTU | [8 empty] | 1680 hours | 239 hours |  | Ongoing | Green | 95RON high gum-GLSD
8 | Engine08 | Gamma2 | LS-GED | PATAC 5W04 | [8 empty] | 727 cycles |  |  | Not start | Green | 98RON Special
9 | C93ZG110AA | Gamma2 | S&S | DYPT | [8 empty] | 278530 cycles | 0 cycle |  | Not start | Green | 95RON Marketing
Original Plan
Actual plan
Forecasting finish plan
VSO

## Sheet1 (hidden)
RPO | Test | Location | Purpose | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
L3A |  |  | OTS车，25台
L3A |  |  | PPV车，24台
L3A |  |  | PPAP,300台
LYX |  |  | PPV车，20台.暂定6月
LYX |  |  | PPAP,300台
LFV | GED | Yantai | 陆磊——住友曲轴（3月30日到PATAC)，活塞销验证，活塞加强验证
LFV | GED | Yantai | 陆磊——住友曲轴（3月30日到PATAC)，活塞销验证，活塞加强验证
LFV | GETC | MAHLE | 张灏俊——增压器隔热罩
LYX | GED | PATAC | 朱敏婧——VVT凸轮轴OTS验证 陆磊——活塞加强验证 D2UC NCT 估计6台
LYX | GED | PATAC | 朱敏婧——VVT凸轮轴OTS验证 陆磊——活塞加强验证
LFV | GED | Yantai | 陆磊——CIE南京2线
LE2 | GED | Yantai | 陆磊——CIE南京2线 胡斌——EK气缸垫
LE2 | GED | Yantai | M2验证
L3A | GED | PATAC | 徐超——油轨，油泵壳体国产化，EGE cooler？
L3A | GED | Yantai | 徐超——油轨，油泵壳体国产化
造机大致时间
造机时间
特殊零件MRD至泛亚
试验时间
*特殊零件清单必须在MRD前两周锁定