## Sheet1 (2) (hidden)
pickup | RPO | Test | Plant | dyno | Purpose | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug |  | Sep | Oct |  | Nov |  | Dec
| L3A |  |  |  | OTS车，25台
| L3A |  |  |  | PPV车，22台
| L3A |  |  |  | PPAP,300台 | [8 empty] | 1 |  |  | 2
| LYX |  |  |  | PPV车，20台.8月22日
| LYX |  |  |  | PPAP,300台 | [13 empty] | 1 |  | 2
5月30日，共6台（2备+1 cordwood) | LFV | GED | WH | Yantai | 陆磊——住友曲轴（4月15日毛坯到PATAC)，活塞销（已有）验证 朱敏婧-进气凸轮轴、排气凸轮轴、国产化弹簧座
| LFV | GED | WH | Yantai | 陆磊——住友曲轴（4月15日毛坯到PATAC)，活塞销（已有）验证 朱敏婧-进气凸轮轴、排气凸轮轴、国产化弹簧座
| LFV | GETC | WH | FM | 张灏俊——增压器隔热罩，4个月——TBD 钱顾军——油底壳(5月零件可ok） 胡斌-EK气缸垫？
8月15日，共9台 | LFV | GED | WH | MAHLE | 陆磊——活塞加强验证，住友曲轴（4月15日毛坯到PATAC)，活塞销（已有）验证
| LFV | GED | WH | MAHLE | 陆磊——活塞加强验证，住友曲轴（4月15日毛坯到PATAC)，活塞销（已有）验证
| LFV | GEHS | WH | Yantai | 陆磊——活塞加强验证，住友曲轴（4月15日毛坯到PATAC)，活塞销（已有）验证
| LFV | GCSD | WH | Yantai | 陆磊——活塞加强验证，住友曲轴（4月15日毛坯到PATAC)，活塞销（已有）验证
5月4日，共17台 | LYX | GED | WH | PATAC | 朱敏婧——VVT（4月1日到）、凸轮轴（4月1日到）OTS验证 钱鹏——加长螺栓（4月1日到） 唐宁-水泵 D2UC NCT 13台
| LYX | GED | WH | PATAC | 朱敏婧——VVT、凸轮轴OTS验证 钱鹏——加长螺栓 唐宁-水泵
7月20，共4台 | L3A | GED | WH | PATAC | 徐超——油轨，油泵壳体国产化（6月1日到），EGE cooler？
| L3A | GED | WH | Yantai | 徐超——油轨，油泵壳体国产化（6月1日到）
6月30日，共4台 | LFV | GED | Nor | Yantai | 陆磊——CIE南京2线（4月30日毛坯到） 国产化连杆
| LE2 | GED | Nor | Yantai | 陆磊——CIE南京2线（4月30日毛坯到） 国产化连杆 （胡斌——EK气缸垫）
| LE2 | GED | Nor | Yantai | M2验证
| L3G | GED | Nor | Yantai | 陆磊-国产化连杆
造机大致时间
造机时间
特殊零件MRD至泛亚
试验时间
*特殊零件清单必须在MRD前两周锁定
Note on AJ4: MVBP2.0: 8月8日

## 48V (hidden)
▶48V DYNO Validation Plan&Status
SN | Trans NO. | Trans Status | Test Item | Cell | 2017 | [7 empty] | 2018 |  |  |  | Target | Current % | Test Status | Remark | PRTS | SOT Status | Remark
[5 empty] | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4
1 | NA | DCT BETA | Start Stop | DYPT | [11 empty] | (5/1-10/30) | 500000 cycles | 58.84% | Ongoing |  |  | Already done
2 | LS163577M2WX0002 | DCT BETA | Start Cart | GRC | [11 empty] | (5/11-12/31) | 500000 cycles | 16.2% | Ongoing | Replaced DCT trans @ 77755 Cycle (LS163577M2WX0003→LS163577M2WX0002) |  | Already done
2 | CONUB004AS | 6T35 BETA | Start Cart | GRC | [11 empty] | (8/1-3/20) | 500000 cycles | 0% | Running Incident | Working on MGU software. |  | Already done
▶48V DYNO Validation Plan&Status
SN | Trans NO. | Trans Status | Test Item | Cell | 2017 |  |  |  | 2018 | [7 empty] | Target | Current % | Test Status | Remark | PRTS | SOT Status | Remark
[5 empty] | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
1 | NA | 6T30 BETA | Start Cart | GRC | [11 empty] | (11/1-5/15) | 500000 cycles | 0% |  |  |  | Not yet start
2 | NA | DCT GAMMA | Start Cart | GRC | [11 empty] | (11/1-5/15) | 500000 cycles | 0% |  |  |  | Not yet start
Original Plan
Actual plan
Forecasting finish plan
Original Plan
Actual plan
Forecasting finish plan

## GFE (hidden)
2017-11-07
▶GFE DYNO Validation Plan&Status
SN | Trans NO. | Trans Status | Eng NO. | Eng Status | Test Item | Cell | 2017 | [6 empty] | Target | Trans Cycles | Current % | Test Status | Remark | PCRS | SOT Status | Remark
[7 empty] | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | C9KFG164CQ | Gamma | L2B*170763134 | Gamma | TEDD | PTA | [7 empty] | 24000 | 0 | 0% | Running Incident | Measure cooling fluid volume till 8/24—Gao Peiyuan Long term solution:Xu Guoqiang/Gao Peiyuan |  | Already done
2 | C9KFG113CQ | Gamma | L2B*170763135 | Gamma | Start&Stop | PTB | [7 empty] | 43708 | 0 | 0% | Running Incident | Measure cooling fluid volume till 8/24—Gao Peiyuan Long term solution:Xu Guoqiang/Gao Peiyuan |  | Already done
3 | C9KFG169CQ | Gamma | L2B*170763133 | Gamma | TEDD | PTC | [7 empty] | 24000 | 0 | 0% | Running Incident | Measure cooling fluid volume till 8/24—Gao Peiyuan Long term solution:Xu Guoqiang/Gao Peiyuan |  | Already done
4 | B2B | Gamma | NA | Gamma | B2B | M 1 | [7 empty] | 185.4 | 0 | 100% | Finished | 0 |  | Already done
5 | C9KFG001CQ | Gamma | L2B*161333733* | Gamma | TEDD | GRC | [7 empty] | 24000 | 0 | 0% | Waiting | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep. |  | Already done
6 | C9KFG005CQ | Gamma | L2B*161333732* | Gamma | TEDD | Horiba | [7 empty] | 24000 | 0 | 0% | Waiting | Horiba facility issue,waiting for new parts,plan to debug at 8/21 |  | Already done
Original Plan
Actual plan
Forecasting finish plan

## GF6
▶6T35 K256 & K257 Gamma TEDD DYNO Validation Plan&Status
SN | Trans NO. | Trans Status | Test Item | Cell | 2017 | [13 empty] | Target | Current % | Test Status | Remark | PRTS | SOT Status | Remark
[5 empty] | 1 | 2 | 3 | 4 |  | 5 | 6 | 7 |  | 8 | 9 | 10 |  | 11
| C8NUG045CS | 6T35 GAMMA | TEDD | GRC 13# |  |  |  |  | VSO:14Apr | [9 empty] | 19300 cycles + 950 cycles | 100% | Finished |  | 1923931 | Already done
| C8NUG047CS | 6T35 GAMMA | TEDD | GRC 15# |  |  |  |  | VSO:14Apr | [9 empty] | 19300 cycles + 950 cycles | 100% + 950 cycles | Finished |  | 1923931 | Already done
1 | C8NUG048CS | 6T35 GAMMA | TEDD | GRC 12# |  |  |  |  | VSO:14Apr | [9 empty] | 19300 cycles + 950 cycles | 100% + 950 cycles | Finished |  | 1923914 | Already done
| C8NUG051CS | 6T35 GAMMA | TEDD | GRC 11# | [14 empty] | 8090 cycles + 950 cycles | 0% | Finished |  |  | Already done
2 | C8NUG054CS | 6T35 GAMMA | TEDD | GRC 13# | [14 empty] | 19300 cycles + 950 cycles | 100% + 950 cycles | Finished |  |  | Already done |  | 19300
3 | 618CFS97230A0561 | 6T35 Sal | Quick Dyno TEDD | GRC 11# | [8 empty] | Sal: 19Jul | [5 empty] | 1500 cycles | 100% | Finished |  |  | Already done |  | 1500
| 6T35 Final Drive | 6T35 GAMMA | B2B | PATAC B2B M2 | [14 empty] | 569 hours | 100% | Finished |  |  | Already done
| 618CFS97207A0702 | 6T35 NS3 | Quick Dyno TEDD | GRC 11# | [8 empty] | Sal: 19Jul | [5 empty] | 1500 cycles | 100% | Finished |  |  | Already done
▶6T30 JBUx Beta TEDD DYNO Validation Plan&Status
SN | Trans NO. | Trans Status | Test Item | Cell | 2017 | [9 empty] | 2018 |  |  |  | Target | Current % | Test Status | Remark | PRTS | SOT Status | Remark
[5 empty] | 5 | 6 | 7 | 8 |  | 9 | 10 | 11 |  | 12 | … | 7 |  | 8
1 | C02AB001CS | 6T30 BETA | TEDD | GRC 17# | [12 empty] | VSO:23Jul |  | 19300 cycles | 100% | Finished |  |  | Already done |  | 19300
Original Plan
Actual plan
Forecasting finish plan
Original Plan
Actual plan
Forecasting finish plan

## GF9
▶9T50 E2UL MY change DYNO Validation Plan&Status
SN | Trans NO. | Trans Status | Test Item | Cell | 2017 | [6 empty] | 2018 |  |  |  |  | Target | Current % | Test Status | Remark | SOT Status | Remark
[5 empty] | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 |  | 2 | 3 | 4
1 | C93HG012CB | GAMMA MY change | TEDD | GRC | [8 empty] | VSO: 15Jan |  |  |  | TBD | 15.51% | Ongoing |  | Red | Dyno setup:1st dyno build complete. 2nd dyno build from 23Oct Cal: GPS provide Dyno Cal on 9/15. GPS Dyno Cal develop in progress. Target date: 27Oct17 Owner: Liu Yang/Asha | 3024
2 | C93HG013CB | GAMMA MY change | TEDD | GRC | [12 empty] | TBD | 0% | Work in progress | Debugging Owner: Liu Yang Target date: 10Nov17 | Red
3 | C93HG014CB | GAMMA MY change | TEDD | GRC | [12 empty] | TBD | 0% | Work in progress | Waiting for dyno resource Owner: Liu Yang Target date: 4Dec17 | Red
4 | 9T50 FWD Final Drive | GAMMA | B2B | PATAC B2B M2 | [12 empty] | 228 hours *3 sets | 100% 100% 100% | Finished |  | Green
0
Original Plan
Actual plan
Forecasting finish plan

## CVT
▶CVT250 E2SC Gamma DYNO Validation Plan&Status
SN | Trans NO. | Trans Status | Test Item | Cell | 2017 |  |  |  | 2018 | [7 empty] | Target | Current % | Test Status | Remark | PRTS | SOT Status | Remark
[5 empty] | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 |  | 6 | 7
1 | TBD | GAMMA | TEDD | GRC | [9 empty] | VSO:29Jun |  |  | TBD | 0% | Work in progress | Debugging Owner: Luo Hehua Target date: 10Nov17 |  | Yellow | Hardware setup complete, engine started successfully, TCM ECM INCA communication OK, debugging in progress. Taget date: 27Oct17 Owner: Luo hehua
2 | TBD | GAMMA | TEDD | GRC | [12 empty] | TBD | 0% | Work in progress | Waiting for dyno resource Owner: Luo Hehua Target date: 20Nov17 |  | Yellow
3 | TBD | GAMMA | TEDD | GRC | [12 empty] | TBD | 0% | Work in progress | Waiting for dyno resource Owner: Luo Hehua Target date: 18Dec17 |  | Yellow
Original Plan
Actual plan
Forecasting finish plan

## EPXX (hidden)
▶EPXX DYNO Validation Plan&Status
SN | Trans NO. | Trans Status | Test Item | Cell | 2017 |  |  |  | 2018 | [6 empty] | Target | Current % | Test Status | Remark | PRTS | SOT Status | Remark
[5 empty] | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
1 | TBD | Early Beta | TEDD | Huayi | [10 empty] | (10/1-10/30) | TBD | 0% | Waiting |  |  | Yellow | Dyno resource not confirmed, may need single source for Huayi.
2 | TBD | BETA | TEDD | GRC | [10 empty] | (11/30-3/20) | TBD | 0% | Waiting |  |  | Not yet start
3 | TBD | BETA | TEDD | GRC | [10 empty] | (1/1-4/20) | TBD | 0% | Waiting |  |  | Not yet start
4 | TBD | BETA | TEDD | GRC | [10 empty] | (2/1-5/20) | TBD | 0% | Waiting |  |  | Not yet start
5 | TBD | BETA | Start Cart | GRC | [10 empty] | (11/30-7/30) | TBD | 0% | Waiting |  |  | Not yet start
Original Plan
Actual plan
Forecasting finish plan

## NMT (hidden)
▶JBUB 6P17 DYNO Validation Plan&Status
SN | Trans NO. | Trans Status | Test Item | Cell | 2017 | [5 empty] | Target | Current % | Test Status | Remark | EIR | SOT Status | Remark
[5 empty] | 7 | 8 | 9 | 10 | 11 | 12
1 | 11170727M3CX0046 | Beta | Diff Case | SAGW | [6 empty] | 14.5 | 52% | Ongoing | 计划8/18翻新完成 |  | Green | 采用K216 6P17变速箱壳体和输入轴、从动一档齿，使用JBUB差速器 按照3.5-3.5-3.5-4进行试验 试验循环数更改为每进行2小时更换一次输出轴 7/10开始试验；7/11第一轮试验，CP报警停机，试验暂停；7/13解体发现输出轴/主减齿轮断齿，并打碎前壳体，翻新后继续进行试验；7/17更换失效零件后继续试验，运行176min CP报警停机，试验暂停；7/18解体发现输出轴断齿。前轴承板内圈有刮痕，计划翻新后重新进行试验；7/26完成翻新后第一个循环，等待翻新更换输出轴；
2 | C0JPB065CM | Beta | Gear&Bearing Fatigue Test | CAERI | [6 empty] | 297.5 | 61.98% | Ongoing | 8/17第六循环三档 |  | Green | 输入轴：JBUX新制造批次，400%气喷 从一：JBUX磨齿改制 放大侧隙 输出轴： 200%强喷 主减速：200%强喷 输出轴前轴承：人本的75外径+大凸度滚子+外圈短期措施（加凹槽） 先做1档和2档，之后打开变速箱检查输出轴前轴承状态，再做剩下档位 8/2发运；8/3开始试验；8/4运行1&2档第五循环；8/7完成1&2档循环后，拆箱检查轴承状态无异常，进行第一循环6档；8/8第二循环三档；8/9第二循环六档；8/10第三循环五档；8/11第四循环三档，三档运行70min出现异响，delta振动值最高上升到1400，但未达报警值3000，待运回拆解；8/11开箱检查无异常，合箱后准备继续试验；8/15第四循环五档；8/16第五循环四档；8/17第六循环三档
3 | C0JPB066CM | Beta | Gear&Bearing Fatigue Test | SAGW | [6 empty] | 297.5 | 10.76% | Ongoing | 计划8/18开箱检查 |  | Green | 输入轴：JBUX新制造批次，400%气喷 从一：JBUX磨齿改制 放大侧隙 输出轴： 200%强喷 主减速：200%强喷 输出轴前轴承：常州光洋的74外径+大凸度滚子+外圈短期措施（加凹槽） 先做1档和2档，之后打开变速箱检查输出轴前轴承状态，再做剩下档位 8/14台架保养；8/15进行试验；8/16第五循环二档；8/17完成1&2档十个循环，下台架进行开箱检查；计划8/18开箱检查
非ADV试验状态
1 | C0JPB001CM | Beta | Efficiency | PATAC HORIBA | [7 empty] | 83% | Waiting | 验证台架的可重复性 计划8/18完成一档剩余试验 |  | Green | 验证台架的可重复性 8/3开始试验；8/7台架电机冷却水管渗液，试验暂停，等待供应商检修；8/17冷冻水报警停机；计划8/18完成一档剩余试验
2 | C0JPB059CM | Beta | Mu-split | CAERI | [7 empty] | 100% | Waiting | 计划8/18开始试验 |  | Green | 最大扭矩为175Nm进行试验，完成后最大扭矩为145Nm进行试验，以对数据进行对比
▶GEM 5P13 AMT DYNO Validation Plan&Status
SN | Trans NO. | Trans Status | Test Item | Cell | 2017 | [5 empty] | Target | Current % | Test Status | Remark | EIR | SOT Status | Remark
[5 empty] | 7 | 8 | 9 | 10 | 11 | 12
1 | C0IWG004AM | Gamma | Synchronizering Fatigue Test | SAGW | [6 empty] | 475000 | 77% | Ongoing | 8/17停机，马瑞利重新将标定数据填写，重新开始试验 |  | Green | 6/20等待马瑞利调试；6/21开始1-2-1档位3500转同步时间0.25s；7/3完成3500RPM，开始5000RPM工况；7/6完成1-2-1工况，进行2-3-2第一种工况；7/19完成2-3-2第一种工况，开始第二种工况；7/24发现台架振动偏大，排查台架问题中；7/26台架轴承座有问题，紧急进行加工维修中；8/2继续进行；8/3开始3-4-3第一种工况试验；8/10完成3-4-3第一种工况，等待马瑞利调试第二种工况，下台架进行气密性测量；8/14完成3-4-3第二种工况，开始4-5-4第一种工况；8/17停机，马瑞利重新将标定数据填写，重新开始试验
2 | C0IWG005AM | Gamma | Synchronizering Fatigue Test | KYOWA | [6 empty] | 475000 | 0% | Waiting | 8/18等待马瑞利调试 |  | Green
▶GEM 5P13 DYNO Validation Plan&Status
SN | Trans NO. | Trans Status | Test Item | Cell | 2017 | [5 empty] | Target | Current % | Test Status | Remark | EIR | SOT Status | Remark
[5 empty] | 7 | 8 | 9 | 10 | 11 | 12
1 | C0YYG030CM_2 | Gamma | Diff Case | SAGW | [6 empty] | 14.5 | 32% | Waiting | 计划9/1开始试验 |  | Green | 4-4-4.5分三个阶段 7/26开始第一阶段试验；7/27完成第一阶段试验；8/4翻新完成，等待JBUB66#总成试验完成进行试验，
2 | C0YYG058CM | Gamma | Gear&Bearing Fatigue Test | CAERI | [6 empty] | 625000 | 16% | Waiting | 验证decouple 8/14完成4-5-4，待运回泛亚翻新一二档滑块弹簧 |  | Green | 验证decouple 8/8开始4-5-4试验；
3 | C0YYG003CM | Gamma | Efficiency | PATAC HORIBA | [7 empty] | 0% | Waiting | 等待台架 计划8/28开始试验 |  | Green
非ADV试验状态
1 | C0YYG007CM_2 | Gamma | Diff Gear | SAGW | [7 empty] | 0% | Waiting | 差速器行星轴镀Ni-P，新垫片 8/4翻新完成，计划9/1开始试验 |  | Green
Original Plan
Actual plan
Forecasting finish plan

## Sheet1 (hidden)
RPO | Test | Location | Purpose | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
L3A |  |  | OTS车，25台
L3A |  |  | PPV车，24台
L3A |  |  | PPAP,300台
LYX |  |  | PPV车，20台.暂定6月
LYX |  |  | PPAP,300台
LFV | GED | Yantai | 陆磊——住友曲轴（3月30日到PATAC)，活塞销验证，活塞加强验证
LFV | GED | Yantai | 陆磊——住友曲轴（3月30日到PATAC)，活塞销验证，活塞加强验证
LFV | GETC | MAHLE | 张灏俊——增压器隔热罩
LYX | GED | PATAC | 朱敏婧——VVT凸轮轴OTS验证 陆磊——活塞加强验证 D2UC NCT 估计6台
LYX | GED | PATAC | 朱敏婧——VVT凸轮轴OTS验证 陆磊——活塞加强验证
LFV | GED | Yantai | 陆磊——CIE南京2线
LE2 | GED | Yantai | 陆磊——CIE南京2线 胡斌——EK气缸垫
LE2 | GED | Yantai | M2验证
L3A | GED | PATAC | 徐超——油轨，油泵壳体国产化，EGE cooler？
L3A | GED | Yantai | 徐超——油轨，油泵壳体国产化
造机大致时间
造机时间
特殊零件MRD至泛亚
试验时间
*特殊零件清单必须在MRD前两周锁定