## Sheet1 (2) (hidden)
pickup | RPO | Test | Plant | dyno | Purpose | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug |  | Sep | Oct |  | Nov |  | Dec
| L3A |  |  |  | OTS车，25台
| L3A |  |  |  | PPV车，22台
| L3A |  |  |  | PPAP,300台 | [8 empty] | 1 |  |  | 2
| LYX |  |  |  | PPV车，20台.8月22日
| LYX |  |  |  | PPAP,300台 | [13 empty] | 1 |  | 2
5月30日，共6台（2备+1 cordwood) | LFV | GED | WH | Yantai | 陆磊——住友曲轴（4月15日毛坯到PATAC)，活塞销（已有）验证 朱敏婧-进气凸轮轴、排气凸轮轴、国产化弹簧座
| LFV | GED | WH | Yantai | 陆磊——住友曲轴（4月15日毛坯到PATAC)，活塞销（已有）验证 朱敏婧-进气凸轮轴、排气凸轮轴、国产化弹簧座
| LFV | GETC | WH | FM | 张灏俊——增压器隔热罩，4个月——TBD 钱顾军——油底壳(5月零件可ok） 胡斌-EK气缸垫？
8月15日，共9台 | LFV | GED | WH | MAHLE | 陆磊——活塞加强验证，住友曲轴（4月15日毛坯到PATAC)，活塞销（已有）验证
| LFV | GED | WH | MAHLE | 陆磊——活塞加强验证，住友曲轴（4月15日毛坯到PATAC)，活塞销（已有）验证
| LFV | GEHS | WH | Yantai | 陆磊——活塞加强验证，住友曲轴（4月15日毛坯到PATAC)，活塞销（已有）验证
| LFV | GCSD | WH | Yantai | 陆磊——活塞加强验证，住友曲轴（4月15日毛坯到PATAC)，活塞销（已有）验证
5月4日，共17台 | LYX | GED | WH | PATAC | 朱敏婧——VVT（4月1日到）、凸轮轴（4月1日到）OTS验证 钱鹏——加长螺栓（4月1日到） 唐宁-水泵 D2UC NCT 13台
| LYX | GED | WH | PATAC | 朱敏婧——VVT、凸轮轴OTS验证 钱鹏——加长螺栓 唐宁-水泵
7月20，共4台 | L3A | GED | WH | PATAC | 徐超——油轨，油泵壳体国产化（6月1日到），EGE cooler？
| L3A | GED | WH | Yantai | 徐超——油轨，油泵壳体国产化（6月1日到）
6月30日，共4台 | LFV | GED | Nor | Yantai | 陆磊——CIE南京2线（4月30日毛坯到） 国产化连杆
| LE2 | GED | Nor | Yantai | 陆磊——CIE南京2线（4月30日毛坯到） 国产化连杆 （胡斌——EK气缸垫）
| LE2 | GED | Nor | Yantai | M2验证
| L3G | GED | Nor | Yantai | 陆磊-国产化连杆
造机大致时间
造机时间
特殊零件MRD至泛亚
试验时间
*特殊零件清单必须在MRD前两周锁定
Note on AJ4: MVBP2.0: 8月8日

## 19MY E2UL LSY Gamma2
▶ 19MY E2UL LSY Dyno Validation Plan&Status
SN | ENG NO. | Engine Status | Test Item | Cell | 2017 | [5 empty] | 2018 | [7 empty] | Target | Current % | Test Status | Remark | SOT Status | Remark | Test Fuel
[5 empty] | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
1 | C9SYG083AD | Gamma2 | GED | PATAC 5E01 | [14 empty] | 347 cycles | 39.48% | Terminate | Issue: 9/15 137cyc found bubble in coolant. Nitrogen leakage test NOK for cylinder #1,#2,#3. 9/19 Tore down the engine and found combustion gas leak trace from cylinder #1,#2,#3 to coolant jacket in deck face. Root cause: still in research | Already done |  | 95RON Low FD
1-1 | C9SYG100AD | Gamma2 | GED | PATAC 5E01 | [14 empty] | 347 cycles | 0.5764% | Work in progress | Use Opel air bleed procedure ATM wide open Debugging | Already done |  | 95RON Low FD
2 | C9SYG087AD | Gamma2 | GED | Mahle TC6 | [14 empty] | 347 cycles | 82.13% | Ongoing | Use Opel air bleed procedure | Already done |  | 95RON Low FD
3 | C9SYG084AD | Gamma2 | GETC | PATAC 5E04 | [14 empty] | 8900 cycles | 14.27% | Terminate | Issue: 8/17 1270cyc found bubble in coolant. Root cause: cylinder head over heat Solution: 1. Heat up rate change to 1.0~1.1 deg C/s 2. Head and block CT scan before building new GETC engine. | Already done |  | 95RON Low FD
3-1 | C9SYG092AD | Gamma2 | GETC | PATAC 5E04 | [14 empty] | 8900 cycles | 51.97% | Terminate | Issue: 10/13 4630cyc found bubble in coolant. Nitrogen leakage test NOK for cylinder #2. Root cause: still in research | Already done |  | 95RON Low FD
4 | C9SYG354AA | Gamma2 | GETC | PATAC 5E05 | [14 empty] | 8900 cycles | 38.15% | Terminate | Use Opel air bleed procedure Issue: 11/2 3395cyc found coolant in IEM and cylinder #2&#3. Root cause: still in research | Already done |  | 95RON Low FD
5 | C9SYG093AD | Gamma2 | GDTS | PATAC 5W11 | [14 empty] | 1000 cycles | 0% | Work in progress | Debugging | Already done |  | 95RON Low FD
6 | C9SYG095AD | Gamma2 | GEHS | PATAC 5E05 | [14 empty] | 3 hours | 100% | Finished |  | Already done |  | 95RON Low FD
7 | C9SYG096AD | Gamma2 | GEHS | PATAC 5E05 | [14 empty] | 3 hours | 100% | Finished |  | Already done |  | 95RON Low FD
8 | C9SYG088AD | Gamma2 | GCSD | DIAS Cold Room | [14 empty] | 90 cycles | 1.111% | Running Incident | Issue: 11/4 1cyc engine hard to start Solution: need cal update, send data to Opel Responsibility: Opel Due date: 2017.11.14 | Already done |  | winter high&low RVP-GCSD
9 | C9SYG089AD | Gamma2 | GLSD | SJTU | [14 empty] | 2052 hours | 68.66% | Ongoing |  | Already done |  | 95RON high gum-GLSD
10 | C9SYG091AD | Gamma2 | LS-GED | Mahle TC3 | [14 empty] | 675 cycles | 50.96% | Terminate | Issue: 10/14 344cyc found bubble in coolant and heard noise. Leak down were 80% for all cylinders. Found one more valve stem key in cam carrier. Root cause: still in research | Already done |  | 95RON Low FD
11 | C9SYG085AD | Gamma2 | AFM | PATAC 5E11 | [14 empty] | 1800 hours | 21.33% | Terminate | Issue: 9/27 384hrs found bubble in coolant. Nitrogen leakage test NOK for cylinder #2,#3. 9/29 Tore down the engine and found combustion gas leak trace from cylinder #2,#3 to coolant jacket in deck face. Root cause: still in research Solution: retrofit cam carrier ASM to a new engine, continue to validate the SCS related parts. | Already done |  | 95RON Low FD
11-1 | C9SYG103AD | Gamma2 | AFM | PATAC 5E11 | [14 empty] | 1416 hours | 14.97% | Ongoing | Cam carrier from C9SYG085AD Use Opel air bleed procedure | Already done |  | 95RON Low FD
12 | C9SYG090AD | Gamma2 | S&S | DYPT EC1 | [14 empty] | 256000 cycles | 74.8% | Ongoing |  | Already done |  | 95RON Marketing
Original Plan
Actual plan
Forecasting finish plan
VSO
SORP

## Sheet1 (hidden)
RPO | Test | Location | Purpose | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
L3A |  |  | OTS车，25台
L3A |  |  | PPV车，24台
L3A |  |  | PPAP,300台
LYX |  |  | PPV车，20台.暂定6月
LYX |  |  | PPAP,300台
LFV | GED | Yantai | 陆磊——住友曲轴（3月30日到PATAC)，活塞销验证，活塞加强验证
LFV | GED | Yantai | 陆磊——住友曲轴（3月30日到PATAC)，活塞销验证，活塞加强验证
LFV | GETC | MAHLE | 张灏俊——增压器隔热罩
LYX | GED | PATAC | 朱敏婧——VVT凸轮轴OTS验证 陆磊——活塞加强验证 D2UC NCT 估计6台
LYX | GED | PATAC | 朱敏婧——VVT凸轮轴OTS验证 陆磊——活塞加强验证
LFV | GED | Yantai | 陆磊——CIE南京2线
LE2 | GED | Yantai | 陆磊——CIE南京2线 胡斌——EK气缸垫
LE2 | GED | Yantai | M2验证
L3A | GED | PATAC | 徐超——油轨，油泵壳体国产化，EGE cooler？
L3A | GED | Yantai | 徐超——油轨，油泵壳体国产化
造机大致时间
造机时间
特殊零件MRD至泛亚
试验时间
*特殊零件清单必须在MRD前两周锁定