## GEM C13NA Gamma
▶ NGC GEM 13NA Gamma Validation Plan
SN | ENG NO. | Engine Status | Test Item | Cell | 2017 | [7 empty] | 2018 | [9 empty] | Target | Current | Remark | Test Status | SOT Status | Test Fuel
[5 empty] | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | LI5*171712008* | GEM Gamma | GED | PATAC 5E06 | [18 empty] | 426 cycles | 426 cycles |  | Finished | Already done | 95RON Marketing
2 | LI5*171712009* | GEM Gamma | GED | PATAC 5E07 | [18 empty] | 426 cycles | 426 cycles | 搭载信息：点火线圈搭载验证（绕线机变更产品验证） 搭载信息：PCV新方案搭载验证（油气分离器按照截流孔进行设计冻结与开硬模，同时保护针阀设计） 故障发生时间：2017.9.4 发动机在交变工况连续出现扭矩下降，而导致触发报警停机，问题排查中 责任人：王俊 目标日期：2017.9.5 PUMA故障，导致发动机无法运行，试验暂停。 责任人：王国官 目标日期：2017.8.29 | Finished | Already done | 95RON Marketing
3 | LI5*171872016* | GEM Gamma | GEHS | PATAC 5E08 | [18 empty] | 3 cycles | 3 cycles |  | Finished | Already done | 95RON Marketing
4 | LI5*171872017* | GEM Gamma | GEHS | PATAC 5E08 | [18 empty] | 3 cycles | 3 cycles |  | Finished | Already done | 95RON Marketing
5 | LI5** | GEM Gamma | GCSD | DIAS 冷库 | [18 empty] | 60 cycles | 0 cycles |  | Not start | Already done | winter high&low RVP-GCSD
6 | LI5** | GEM Gamma | GCSD | DIAS 冷库 | [18 empty] | 60 cycles | 0 cycles |  | Not start | Already done | winter high&low RVP-GCSD
Original Plan
Actual plan
Forecasting finish plan
VSO