## Lists (hidden)
StatusList | YesNo | Weekends
| Yes | Ran Weekends
Running | No | DID NOT Run Weekends
Running Incident
Incident
Pre Test
Work In Progress
Investigating
Waiting
Waiting Parts
Waiting Manpower
Waiting Ready to Run
Down
Down (Weekend)
Test Terminated
Pending
Pending LATE
Complete

## Holidays (hidden)
Holiday Data
2008-11-14
2008-11-27
2008-11-28
2008-12-22
2008-12-23
2008-12-24
2008-12-25
2008-12-26
2008-12-29
2008-12-30
2008-12-31
2009-01-01
2009-01-02
2009-01-19
2009-04-10
2009-04-13
2009-05-22
2009-05-25
2009-06-29
2009-06-30
2009-07-01
2009-07-02
2009-07-03
2009-09-07
2009-11-16
2009-11-26
2009-11-27
2009-12-24
2009-12-25
2009-12-28
2009-12-29
2009-12-30
2009-12-31
2010-01-01
2010-04-02
2010-05-31
2010-07-05
2010-07-06
2010-07-07
2010-07-08
2010-07-09
2010-09-06
2010-11-02
2010-11-15
2010-11-25
2010-11-26
2010-12-24
2010-12-27
2010-12-28
2010-12-29
2010-12-30
2010-12-31
2011-01-17
2011-04-22
2011-05-30
2011-07-04
2011-07-05
2011-07-06
2011-07-07
2011-07-08
2011-09-05
2011-11-14
2011-11-24
2011-11-25
2011-12-26
2011-12-27
2011-12-28
2011-12-29
2011-12-30

## Drop Box (hidden)
Test Cell | LAF | LDK*111580392
Pallet Prep | GENII 6T40 | 611FCRM1228A1474
Drop Zone
Build Room
Cart Room
Dock 45
PAT Crib
NF wing
NF dyno
D111
D113
D115
D117
D119
D121
D123
D125
D126
D127
D128
D129
D131
D133
D135
D137
D139
D141
D143

## GFE Validation New Daily Log
2017-11-07
▶GFE DYNO Validation Plan&Status
SN | Trans NO. | Trans Status | Eng NO. | Eng Status | Test Item | Cell | 2017 | [7 empty] | 2018 | Target | Trans Cycles | Current % | Test Status | Remark | PCRS | SOT Status | Remark
[7 empty] | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | 1
1 | C9KFG168CQ | Gamma | L2B*170763134 | Gamma | TEDD | PTA | [7 empty] | VSO:22Jan |  | 24000 | 14664 | 61.1% | Ongoing | 0 |  | Yellow | Cooling flow rate not meet test request. Long term solution:Xu Guoqiang/Gao Peiyuan
2 | C9KFG113CQ | Gamma | L2B*170763135 | Gamma | Start&Stop | PTB | [9 empty] | 43708 | 3230 | 7.39% | Running Incident | Issue Date:10/30 Issue Describe:Facility fault Next Step:Fix facility Target Date:TBD Owner:Yao Yuxing |  | Yellow | Cooling flow rate not meet test request. Long term solution:Xu Guoqiang/Gao Peiyuan
3 | C9KFG182CQ | Gamma | L2B*170763133 | Gamma | TEDD | PTC | [9 empty] | 24000 | 5126 | 21.36% | Running Incident | Issue Date:11/6 Issue Describe:Facility Error Target Date:TBD Owner:Yao Yuxing |  | Yellow | Cooling flow rate not meet test request. Long term solution:Xu Guoqiang/Gao Peiyuan
4 | B2B | Gamma | NA | Gamma | B2B | M 1 | [9 empty] | 185.4 | 0 | 100% | Finished | 0 |  | Green
5 | T9EPG612CQ | Gamma | L2B*161333733* | Gamma | TEDD | GRC | [9 empty] | 24000 | 0 | 0% | Working in Progress | Debugging ,expect to run test on 11/15 |  | Green
6 | C9KFG005CQ | Gamma | L2B*161333732* | Gamma | TEDD | Horiba | [9 empty] | 24000 | 0 | 0% | Working in Progress | Debugging Target Date:11/10 Owner:Wu Chenwen |  | Green
Original Plan
Actual plan
Forecasting finish plan

## GFE Validation Daily Log (hidden)
> GFE TRANSMISSION DAILY REPORT <
Date: |  |  |  |  | 2017-11-07 | [6 empty] | Zheng Yixiu
Location | Pallet # | PON # |  | RPO | Property Number | Current Software | Test | PQMS # | Title | Back up Transmission | Cycle Goal | Trans Cycles | Percent Complete | Average Cycles/Day | Maximum Cycles/Day | Max Eff. Completion | Projected Completion | Status | Comments
Test Cell | PTA | 0 | Trans | MKF | C9KFG168CQ | AA0202B516_toPATAC_FlashedMuleCar_Dynoized_3_9_2019 | TEDD | #NAME? | GFE Gamma TEDD Validation (K226 Local Content) | None | 24000 | 14664 | 61.1% | 0 | 0 | #DIV/0! | Unable to Predict | Running | 0
|  |  | Engine | L2B | L2B*170763134 | S55TH_171712011_04Apr2017_TEDD_2 S55M1_171712011_04Apr2017_TEDD_2 S55M2_171712011_04Apr2017_TEDD_2
Test Cell | PTB | 0 | Trans | MKF | C9KFG113CQ | AA0202B516_toPATAC_FlashedMuleCar_Dynoized_3_9_2019 | Start&Stop | #NAME? | GFE GammaStart&Stop Validation (K226 Local Content) | None | 43708 | 3230 | 7.39% | 0 | 0 | #DIV/0! | Unable to Predict | Running Incident | Issue Date:10/30 Issue Describe:Facility fault Next Step:Fix facility Target Date:TBD Owner:Yao Yuxing
|  |  | Engine | L2B | L2B*170763135 | S55TH_171712011_04Apr2017_TEDD_2 S55M1_171712011_04Apr2017_TEDD_2 S55M2_171712011_04Apr2017_TEDD_2
Test Cell | PTC |  | Trans | MKF | C9KFG182CQ | AA0202B516_toPATAC_FlashedMuleCar_Dynoized_3_9_2019 | TEDD | #NAME? | GFE Gamma TEDD Validation (K226 Local Content) | None | 24000 | 5126 | 21.36% | Unable to Calculate | 11661 | #DIV/0! | Unable to Predict | Running Incident | Issue Date:11/6 Issue Describe:Facility Error Target Date:TBD Owner:Yao Yuxing
|  |  | Engine | L2B | L2B*170763133 | S55TH_171712011_04Apr2017_TEDD_2 S55M1_171712011_04Apr2017_TEDD_2 S55M2_171712011_04Apr2017_TEDD_2
Test Cell | M 1 | 0 | Trans | GFE 2nd Axis |  |  | B2B | #NAME? | 6th set | None | 185 | 0 | 0% | Unable to Calculate | 0 | Not Enough Data to Calculate | Not Enough Data to Calculate | 0 | 0
Hrs
Test Cell | GRC |  | Trans | MKF | T9EPG612CQ | AA0202B516_toPATAC_FlashedMuleCar_Dynoized_3_9_2019 | TEDD | #NAME? | GFE Gamma TEDD Validation (K226 Local Content) | None | 24000 | 0 | 0% | 0 | 0 | #DIV/0! | Unable to Predict | Work In Progress | Debugging ,expect to run test on 11/15
|  |  | Engine | L2B | L2B*161333733* | S55TH_171712011_04Apr2017_TEDD_2 S55M1_171712011_04Apr2017_TEDD_2 S55M2_171712011_04Apr2017_TEDD_2
Test Cell | Horiba | 0 | Trans | MKF | C9KFG005CQ | AA0202B516_toPATAC_FlashedMuleCar_Dynoized_3_9_2019 | TEDD | #NAME? | GFE Gamma TEDD Validation (K226 Local Content) | None | 24000 | 0 | 0% | 0 | 0 | #DIV/0! | Unable to Predict | 0 | Debugging Target Date:11/10 Owner:Wu Chenwen
|  |  | Engine | L2B | L2B*161333732* | S55TH_171712011_04Apr2017_TEDD_2 S55M1_171712011_04Apr2017_TEDD_2 S55M2_171712011_04Apr2017_TEDD_2
C83DG003CB
2015.10.10
2015.11.4
2015.12.27
2016.4.30
B
Formulas:
Max Eff. Completion = IF([Percent Complete]>10%,WORKDAY(G4,([Cycle Goal]-[Trans Cycles])/[Maximum Cycles/Day],Holidays!$A2:A36), "Not Enough Data to Calculate")
Projected Completion = IFERROR(IF([Percent Complete]>10%,'GFE Validation Daily Log'!#REF!:V10WORKDAY(G4,(G7[Cycle Goal]-[Trans Cycles])/[Average Cycles/Day],Holidays!$A2:A36), "Not Enough Data to Calculate"),"Unable to Predict")
Note on B2: Make sure you paste copied cells as a bitmap image in Lotus Notes to preserve formatting.
Note on R6: MAX Cycles/Day for the remainder of the test. FOR REFERENCE INFORMATION ONLY
Note on S6: Based on running the MAX Cycles/Day for the remainder of the test. FOR REFERENCE INFORMATION ONLY
Note on B7: Test cell rows correspond to the columns in "Validation Daily Log". Cycles, Percent complete, average cycles/ day, projected completion, status, and comments are all automatically populated from the Validation Log.
Note on B9: Test cell rows correspond to the columns in "Validation Daily Log". Cycles, Percent complete, average cycles/ day, projected completion, status, and comments are all automatically populated from the Validation Log.
Note on B11: Test cell rows correspond to the columns in "Validation Daily Log". Cycles, Percent complete, average cycles/ day, projected completion, status, and comments are all automatically populated from the Validation Log.
Note on B13: Test cell rows correspond to the columns in "Validation Daily Log". Cycles, Percent complete, average cycles/ day, projected completion, status, and comments are all automatically populated from the Validation Log.
Note on B15: Test cell rows correspond to the columns in "Validation Daily Log". Cycles, Percent complete, average cycles/ day, projected completion, status, and comments are all automatically populated from the Validation Log.
Note on B17: Test cell rows correspond to the columns in "Validation Daily Log". Cycles, Percent complete, average cycles/ day, projected completion, status, and comments are all automatically populated from the Validation Log.

## PTA (hidden)
3
| L2B |  | L2B*170763134
Columns Active (Click to activate) | MKF |  | C9KFG168CQ
| Test Cell |  | Test Schedule: | TEDD
| Cycle Goal: | 24000 | Pallet #: | PTA
| Trans Software: | S55TH_171712011_04Apr2017_TEDD_2 S55M1_171712011_04Apr2017_TEDD_2 S55M2_171712011_04Apr2017_TEDD_2 | Engine Software: | AA0202B516_toPATAC_FlashedMuleCar_Dynoized_3_9_2019
| PQMS# |  | PON#
|  | Title: | GFE Gamma TEDD Validation (K226 Local Content)
| Back up Trans: |  |  |  | Part installed |  |  |  | Part removed
| Cycles | Cycles/day | Status | Comments | PN | Name | Prior cycles | Origin | PN | Name | Cycles on part Check for history! | Reason for change
2017-07-18 | 0 | 0 | Pending | DCDC hardware issue
2017-07-19 | 0 | 0 | Pending | Expected to change new card on 7/21
2017-07-20 | 0 | 0 | Pending | Expected to change new card on 7/21
2017-07-21 | 0 | 0 | Pending | New card doesn't work,checking issues
2017-07-22 | 0 | 0 | Pending | New card doesn't work,checking issues
2017-07-23 | 0 | 0 | Pending | New card doesn't work,checking issues
2017-07-24 | 0 | 0 | Pending | Investigate and repair the issue of DCDC hardware
2017-07-25 | 0 | 0 | Pending | Contact GE China to repair the issue of DCDC hardware
2017-07-26 | 0 | 0 | Pending | Contact GE China to repair the issue of DCDC hardware
2017-07-27 | 0 | 0 | Waiting Ready to Run | The issue of DCDC hardware is figure out after importing the default parameter,expect to start test 7/28
2017-07-28 | 0 | 0 | Waiting Ready to Run | Install pressure sensor
2017-07-29 | 0 | 0 | Waiting Ready to Run | Install pressure sensor
2017-07-30 | 0 | 0 | Waiting Ready to Run | Install pressure sensor
2017-07-31 | 0 | 0 | Waiting Ready to Run | Ready to run TEDD
2017-08-01 | 0 | 0 | Waiting Ready to Run | 753 connector leakage
2017-08-02 | 0 | 0 | Work In Progress | Replace PTC shift control module to PTA
2017-08-03 | 0 | 0 | Work In Progress | Replace PTC shift control module to PTA
2017-08-04 | 0 | 0 | Work In Progress | Collect s/s test data to GPS,ready to break-in for TEDD
2017-08-05 | 0 | 0 | Work In Progress | Collect s/s test data to GPS,ready to break-in for TEDD
2017-08-06 | 0 | 0 | Work In Progress | Collect s/s test data to GPS,ready to break-in for TEDD
2017-08-07 | 0 | 0 | Work In Progress | Change dyno parameters for TEDD test,collect data to GPS
2017-08-08 | 0 | 0 | Waiting | Concerto issue,try to modify the script high voltage target
2017-08-09 | 0 | 0 | Waiting Ready to Run | Trans oil condition maintance,ready to run test with new vehicle parameters and share data with GPS
2017-08-10 | 0 | 0 | Waiting Ready to Run | Run test with new vehicle parameters,waiting data trace confirm by GPS,change transmission cooling water
2017-08-11 | 0 | 0 | Work In Progress | Waiting data trace confirm by GPS,modify vehicle speed to 170kph to start TPIM and ATF temperature exceed limit Freezing water cooling efficiency can not match test condition
2017-08-12
2017-08-13
2017-08-14 | 0 | 0 | Work In Progress | TPIM and ATF temperature exceed limit Freezing water cooling efficiency can not match test condition
2017-08-15 | 50 | 339 | Running | TPIM and ATF temperature exceed limit Freezing water cooling efficiency can not match test condition Short term solution:done Long term solution:Xu Guoqiang/Gao Peiyuan
2017-08-16 | 389 |  | Down | 554 broken,transmission oil and water mixed,ATF became milky Long term solution:Xu Guoqiang/Gao Peiyuan
2017-08-17
2017-08-18 | 0 |  | Incident
2017-08-19
2017-08-20
2017-08-21 |  |  | Incident | Retrofit backup Trans Completed, Ready to run SPIN FUNCTION Check. Cooling Flow Rate Measurement till 8/24—Gao Peiyuan Long term solution:Xu Guoqiang/Gao Peiyuan
2017-08-22 |  |  | Incident | Install transmission. Bridge crane issue ,waiting to maintain on 8/23 Cooling Flow Rate Measurement till 8/24—Gao Peiyuan Long term solution:Xu Guoqiang/Gao Peiyuan
2017-08-23 |  |  | Incident | Install transmission. Bridge crane issue ,waiting to maintain on 8/23 Cooling Flow Rate Measurement till 8/24—Gao Peiyuan Long term solution:Xu Guoqiang/Gao Peiyuan
2017-08-24 |  |  | Incident | Dyno setup,expect to run today Cooling Flow Rate Measurement till 8/24—Gao Peiyuan Long term solution:Xu Guoqiang/Gao Peiyuan
2017-08-25 |  |  | Running | Check cooling flow rate today
2017-08-26 |  |  | Running | Check cooling flow rate today
2017-08-27
2017-08-28 | 1476 | 1476 | Work In Progress | Trans needs to change parts,expect to run on 9/1 Cooling Flow Rate Measurement Long term solution:Xu Guoqiang/Gao Peiyuan
2017-08-29 | 1476 | 0 | Work In Progress | Swap OUTPUT CARRIRER assembled Dalian,expect to start on 9/2
2017-08-30 | 1476 | 0 | Work In Progress | Swap OUTPUT CARRIRER assembled Dalian SPIN function check failure and sent transmission to PPO check Expect to start on 9/2
2017-08-31 | 1476 | 0 | Work In Progress | Swap OUTPUT CARRIRER assembled Dalian SPIN function check failure and sent transmission to PPO check Expect to start on 9/2
2017-09-01 | 1476 | 0 | Work In Progress | Swap OUTPUT CARRIRER assembled Dalian SPIN function check Expect to start on 9/2
2017-09-02
2017-09-03
2017-09-04 | 1476 | 1476 | Work In Progress | Swap OUTPUT CARRIRER assembled Dalian Expect to start on 9/6
2017-09-05 | 1476 | 0 | Work In Progress | Swap OUTPUT CARRIRER assembled Dalian Expect to start on 9/6
2017-09-06 | 1476 | 0 | Work In Progress | Swap OUTPUT CARRIRER assembled Dalian Trans doing spin test,plan to deliver to dyno on 9/8
2017-09-07 | 1476 | 0 | Work In Progress | Swap OUTPUT CARRIRER assembled Dalian Trans doing spin test,plan to deliver to dyno on 9/8
2017-09-08 | 1476 | 0 | Work In Progress | Swap OUTPUT CARRIRER assembled Dalian Wating to do spin test,plan to deliver to dyno on 9/11
2017-09-09
2017-09-10
2017-09-11 | 1476 | 1476 | Work In Progress | Swap OUTPUT CARRIRER assembled Dalian Doing spin test,plan to deliver to dyno on 9/11
2017-09-12 | 1476 | 0 | Work In Progress | Swap OUTPUT CARRIRER assembled Dalian Install transmission,plan to run on 9/18.
2017-09-13 | 1476 | 0 | Work In Progress | Swap OUTPUT CARRIRER assembled Dalian Install transmission,plan to run on 9/18.
2017-09-14 | 1476 | 0 | Work In Progress | Swap OUTPUT CARRIRER assembled Dalian Install transmission,plan to run on 9/18.
2017-09-15 | 1476 | 0 | Work In Progress | Swap OUTPUT CARRIRER assembled Dalian Install transmission,try to run on 9/16.
2017-09-16 |  |  | Running
2017-09-17
2017-09-18 | 2383 | 2383 | Running
2017-09-19 | 2684 | 301 | Running
2017-09-20 | 3089 | 405 | Running
2017-09-21 | 3724 | 635 | Running Incident | Issue Describe:Cable connector burnt. Issue Date:2017.9.21. Resopnser:Yao Yuxing
2017-09-22 | 3724 | 0 | Running Incident | Issue Describe:Cable connector burnt. Issue Date:2017.9.21. Next Step:Check cable connector Resopnser:Zheng Litao/Hong Nianzhong
2017-09-23
2017-09-24
2017-09-25 | 3724 | 3724 | Running Incident | Issue Describe:High Voltage unstable Issue Date:2017.9.21. Next Step:Waiting GE response Resopnser:Yao Yuxing
2017-09-26 | 3724 | 0 | Running Incident | Issue Describe:High Voltage unstable Issue Date:2017.9.21. Next Step:Waiting GE response Resopnser:Yao Yuxing
2017-09-27 | 3724 | 0 | Running Incident | Issue Describe:High Voltage unstable Issue Date:2017.9.21. Next Step:Waiting GE response Resopnser:Yao Yuxing
2017-09-28 | 3724 | 0 | Running Incident | Issue Describe:High Voltage unstable Issue Date:2017.9.21. Next Step:Waiting GE response Resopnser:Yao Yuxing
2017-09-29 | 3724 | 0 | Running Incident | Issue Describe:High Voltage unstable Issue Date:2017.9.21. Next Step:Discuss action plan Resopnser:Yao Yuxing
2017-09-30 | 3724 | 0 | Running Incident | Issue Describe:High Voltage unstable Issue Date:2017.9.21. Next Step:Waiting GE response Resopnser:Yao Yuxing
2017-10-01 | 3724 | 0 | Running Incident | Issue Describe:High Voltage unstable Issue Date:2017.9.21. Next Step:Plan to debug on 10/9 Resopnser:Yao Yuxing
2017-10-02
2017-10-03
2017-10-04
2017-10-05
2017-10-06
2017-10-07
2017-10-08
2017-10-09 | 3724 | 3724 | Running Incident | Issue Describe:High Voltage unstable Target Date:2017.10.10. Next Step:Debugging Owner:Yao Yuxing
2017-10-10 | 3724 | 0 | Running Incident | Issue Describe:High Voltage unstable Target Date:2017.10.10. Next Step:Debugging Owner:Yao Yuxing
2017-10-11 | 3724 | 0 | Running Incident | Issue Describe:High Voltage unstable,suspect transmission damaged. Next Step:Check the transmission status Target date:2017.10.13 Owner:Li Xinlong
2017-10-12 | 11661 | 7937 | Running Incident | Issue Describe:High Voltage unstable,suspect transmission damaged. Next Step:Check the transmission status—2017.10.13Li Xinlong Next Step:Waiting to do function check,exchange PTC Trans(C9KFG168CQ) to PTA,plan to install Trans on 2017.10.14
2017-10-13 | 11661 | 0 | Running Incident | Issue Describe:High Voltage unstable Next Step:Do function check today(2017.10.13),exchange PTC Trans(C9KFG168CQ) to PTA,plan to install Trans on 2017.10.14
2017-10-14 | 11661 | 0
2017-10-15 | 11661 | 0
2017-10-16 | 11661 | 0 | Running Incident | Issue Date:9/21 Issue Describe:High Voltage unstable Next Step:Install transmission on 10.14 due to function check delay,plan to run test on 10/17 . Owner:Hong Nianzhong
2017-10-17 | 11661 | 0 | Running Incident | Issue Date:9/21 Issue Describe:High Voltage unstable Next Step:Transmission Torque shaking ,CAL team support on site 10/17. Owner:Hong Nianzhong
2017-10-18 | 11661 | 0 | Running | Issue Date:9/21 Issue Describe:High Voltage unstable Next Step:Discuss permanent solution tomorrow(2017.10.19) Start to run test after change CAL today (2017.10.18) Owner:Yao Yuxing
2017-10-19 | 11709 | 48 | Running | Issue Date:9/21 Issue Describe:High Voltage unstable Next Step:Waiting GE response Target Date:TBD Owner:Yao Yuxing
2017-10-20 | 12090 | 381 | Running | Issue Date:9/21 Issue Describe:High Voltage unstable Next Step:Try to find permanent solution Target Date:TBD Owner:Yao Yuxing
2017-10-21
2017-10-22
2017-10-23 | 12192 | 12192 | Running Incident | Issue Date:10/23 Issue Describe:Motor Torque abnormal Next Step:Collect data and send to GPS Target Date:TBD Owner:Hong Nianzhong
2017-10-24 | 12192 | 0 | Running Incident | Issue Date:10/23 Issue Describe:Motor Torque abnormal Next Step:Change high voltage device Target Date:10/24 Owner:Hong Yao Yuxing
2017-10-25 | 12192 | 0 | Running Incident | Issue Date:10/23 Issue Describe:Motor Torque abnormal Next Step:Change high voltage device Target Date:10/25 Owner:Hong Yao Yuxing
2017-10-26 | 12192 | 0 | Running Incident | Issue Date:10/26 Issue Describe:CAN Monitor Communication error Target Date:10/27 Owner:Lin Xiaoquan
2017-10-27 | 12237 | 45 | Running | Motor Torque normal due to change Trans CAL
2017-10-28
2017-10-29
2017-10-30 | 12237 | 12237 | Running Incident | Issue Date:10/29 Issue Describe:High voltage connector burning Next Step:Swap new high voltage cable,Horriba exchange PTC high voltage device to PTA. Target Date:10/31. Owner:Lin Xiaoquan/Yao Yuxing
2017-10-31 | 12237 | 0 | Running
2017-11-01 | 13677 | 1440 | Running
2017-11-02 | 13989 | 312 | Running
2017-11-03 | 14002 | 13 | Running
2017-11-04 | 14002 | 0
2017-11-05 | 14002 | 0
2017-11-06 | 14110 | 108 | Running
2017-11-07 | 14664 | 554 | Running
2017-11-08
2017-11-09
2017-11-10
2017-11-11
2017-11-12
2017-11-13
2017-11-14
2017-11-15
2017-11-16
2017-11-17
2017-11-18
2017-11-19
2017-11-20
2017-11-21
2017-11-22
2017-11-23
2017-11-24
2017-11-25
2017-11-26
2017-11-27
2017-11-28
2017-11-29
2017-11-30
2017-12-01
2017-12-02
2017-12-03
2017-12-04
2017-12-05
2017-12-06
2017-12-07
2017-12-08
2017-12-09
2017-12-10
2017-12-11
2017-12-12
2017-12-13
2017-12-14
2017-12-15
2017-12-16
2017-12-17
2017-12-18
2017-12-19
2017-12-20
2017-12-21
2017-12-22
2017-12-23
2017-12-24
2017-12-25
2017-12-26
2017-12-27
2017-12-28
2017-12-29
2017-12-30
2017-12-31
2018-01-01
2018-01-02
2018-01-03
2018-01-04
2018-01-05
2018-01-06
2018-01-07
2018-01-08
2018-01-09
2018-01-10
2018-01-11
2018-01-12
2018-01-13
2018-01-14
2018-01-15
2018-01-16
2018-01-17
2018-01-18
2018-01-19
2018-01-20
2018-01-21
2018-01-22
2018-01-23
2018-01-24
2018-01-25
2018-01-26
2018-01-27
Maximum Cycles/Day |  | 12237
1
Average Daily Cycles Calculations
Weekends? | Ran Weekends
Working Days for Average Calculation | #N/A
Total Days Since SOT | 55
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
Formulas:
Columns Active (Click to activate) = NETWORKDAYS(A1579,[Columns Active (Click to activate), row above],Holidays!$A2:A36)
Note on A2: This document supports up to 15 transmissions at any given time. To hide extra columns, select the column of the given color that you would like to hide, right click, and select "Hide". Similarly, to bring back hidden columns, select the column immediately before and after the hidden column, right click, and select "unhide".
Note on B2: Type Engine RPO here.
Note on D2: Type Engine Number here.
Note on B3: Type Trans RPO here.
Note on D3: Type Transmission Number here.
Note on B4: Select a test cell.
Note on E4: Insert test schedule here.
Note on C5: Insert cycle goal here.
Note on E5: Insert pallet # here.
Note on C6: Type trans software here.
Note on E6: Type engine software here.
Note on C7: Enter PQMS # here.
Note on E7: Insert PON # here.
Note on D9: Type back up transmission number here.
Note on A10: Insert date here. Clicking on the cell and dragging it down to the cell below will automatically fill out the date for the next day. This does not skip weekends, however. Only add the latest date (Do not drag the date past your latest entry) or else the tracking sheet will not see your data. The tracking sheet looks at the latest date, regardless of whether or not there is information in it.
Help
Search
Help
Search
x
^
Jump to Latest Entry Date
Fill in Today's Date

## PTB (hidden)
2
| L2B |  | L2B*170763135
Columns Active (Click to activate) | MKF |  | C9KFG113CQ
| Test Cell |  | Test Schedule: | Start&Stop
| Cycle Goal: | 43708 | Pallet #: | PTB
| Trans Software: | S55TH_171712011_04Apr2017_TEDD_2 S55M1_171712011_04Apr2017_TEDD_2 S55M2_171712011_04Apr2017_TEDD_2 | Engine Software: | AA0202B516_toPATAC_FlashedMuleCar_Dynoized_3_9_2019
| PQMS# |  | PON#
|  | Title | GFE GammaStart&Stop Validation (K226 Local Content)
| Back up Trans: |  |  |  | Part installed |  |  |  | Part removed
| Cycles | Cycles/day | Status | Comments | PN | Name | Prior cycles | Origin | PN | Name | Cycles on part Check for history! | Reason for change
2017-07-18 | 0 | 0 | Pending | DCDC hardware issue
2017-07-19 | 0 | 0 | Pending | Expected to change new card on 7/21
2017-07-20 | 0 | 0 | Pending | Expected to change new card on 7/21
2017-07-21 | 0 | 0 | Pending | New card doesn't work,checking issues
2017-07-22 | 0 | 0 | Pending | New card doesn't work,checking issues
2017-07-23 | 0 | 0 | Pending | New card doesn't work,checking issues
2017-07-24 | 0 | 0 | Pending | The issue of DCDC hardware is figure out after replacing new card and importing the default parameter ,waiting investigate the shift robot issue
2017-07-25 | 0 | 0 | Pending | Change new shift robot ,start commissioning
2017-07-26 | 0 | 0 | Pending | AVL commissioning
2017-07-27 | 0 | 0 | Pending | AVL commissioning
2017-07-28 | 0 | 0 | Pending | AVL commissioning
2017-07-29 | 0 | 0 | Pending
2017-07-30 | 0 | 0 | Pending
2017-07-31 | 0 | 0 | Pending | Waiting data trace confirm by GPS
2017-08-01 | 0 | 0 | Pending | Install pressure sensor
2017-08-02 | 0 | 0 | Pending | Setup emengency stop ,waiting for PTA S/S data conformed by GPS
2017-08-03 | 0 | 0 | Pending | Setup emengency stop ,waiting for PTA S/S data conformed by GPS
2017-08-04 | 0 | 0 | Pending | Ready to annual maintance
2017-08-05 | 0 | 0 | Pending | Ready to annual maintance
2017-08-06 | 0 | 0 | Pending | Ready to annual maintance
2017-08-07 | 0 | 0 | Work In Progress | Oil condition debugging
2017-08-08 | 0 | 0 | Work In Progress | Oil condition debugging
2017-08-09 | 0 | 0 | Work In Progress | Oil condition debugging
2017-08-10 | 0 | 0 | Work In Progress | Oil condition debugging
2017-08-11 | 0 | 0 | Work In Progress | Oil condition debugging
2017-08-12
2017-08-13
2017-08-14 | 0 | 0 | Work In Progress | Oil condition debugging
2017-08-15 | 0 | 0 | Incident | Oil condition debugging Short term solution:Solve issue till 8/21—Xu Guoqiang/Gao Peiyuan Long term solution:Xu Guoqiang/Gao Peiyuan
2017-08-16 | 0 | 0 | Incident | Oil condition debugging Short term solution:Solve issue till 8/21—Xu Guoqiang/Gao Peiyuan Long term solution:Xu Guoqiang/Gao Peiyuan
2017-08-17
2017-08-18 | 0 | 0 | Incident | Oil condition debugging Cooling Flow Rate Measurement till 8/24—Gao Peiyuan Long term solution:Xu Guoqiang/Gao Peiyuan
2017-08-19
2017-08-20
2017-08-21 | 0 | 0 | Incident | Oil condition debugging Cooling Flow Rate Measurement till 8/24—Gao Peiyuan Long term solution:Xu Guoqiang/Gao Peiyuan
2017-08-22 |  |  | Incident | Fix Shift Robot ,ready to run Cooling Flow Rate Measurement till 8/24—Gao Peiyuan Long term solution:Xu Guoqiang/Gao Peiyuan
2017-08-23 |  |  | Incident | Change cables due to start abnormally. Cooling Flow Rate Measurement till 8/24—Gao Peiyuan Long term solution:Xu Guoqiang/Gao Peiyuan
2017-08-24 |  |  | Incident | Engine wire found no issue,reinstall today. Cooling Flow Rate Measurement till 8/24—Gao Peiyuan Long term solution:Xu Guoqiang/Gao Peiyuan
2017-08-25 |  |  | Incident | Change DCDC filter,expect to run on 8/26
2017-08-26
2017-08-27
2017-08-28 |  |  | Incident | Cable issue,expect to run on 8/29 Cooling Flow Rate Measurement Long term solution:Xu Guoqiang/Gao Peiyuan
2017-08-29 |  |  | Incident | Replacing TPIM
2017-08-30 |  |  | Incident | Transmission voltage abnormal due to dyno supply power Debugging now
2017-08-31 |  |  | Running | Start to run today
2017-09-01 |  |  | Work In Progress | Debugging,expect to run 9/2
2017-09-02 |  |  | Running
2017-09-03
2017-09-04 | 56 |  | Running
2017-09-05
2017-09-06 | 208
2017-09-07 | 331 |  | Running
2017-09-08 | 407 |  | Running
2017-09-09
2017-09-10
2017-09-11 | 786 |  | Running
2017-09-12 | 1011 | 225 | Running
2017-09-13 | 1245 | 234 | Running
2017-09-14 | 1416 | 171 | Running
2017-09-15 | 1600 | 184 | Running
2017-09-16
2017-09-17
2017-09-18 | 1923 | 1923
2017-09-19 | 2025 | 102 | Running
2017-09-20 | 2481 | 456 | Running
2017-09-21 | 2481 | 0 | Running Incident | Dyno maintance. Responser:Lin Xiaoquan
2017-09-22 | 2481 | 0 | Running Incident | Dyno maintance. Plan to run:9/23. Responser:Lin Xiaoquan
2017-09-23
2017-09-24
2017-09-25 | 2481 | 2481 | Running Incident | Issue Describe:High Voltage unstable Issue Date:2017.9.21. Next Step:Waiting GE response Resopnser:Yao Yuxing
2017-09-26 | 2481 | 0 | Running Incident | Issue Describe:High Voltage unstable Issue Date:2017.9.21. Next Step:Waiting GE response Resopnser:Yao Yuxing
2017-09-27 | 2481 | 0 | Running Incident | Issue Describe:High Voltage unstable Issue Date:2017.9.21. Next Step:Waiting GE response Resopnser:Yao Yuxing
2017-09-28 | 2481 | 0 | Running Incident | Issue Describe:High Voltage unstable Issue Date:2017.9.21. Next Step:Waiting GE response Resopnser:Yao Yuxing
2017-09-29 | 2481 | 0 | Running Incident | Issue Describe:High Voltage unstable Issue Date:2017.9.21. Next Step:Discuss action plan Resopnser:Yao Yuxing
2017-09-30 | 2481 | 0 | Running Incident | Issue Describe:High Voltage unstable Issue Date:2017.9.21. Next Step:Plan to debug on 10/9 Resopnser:Yao Yuxing
2017-10-01
2017-10-02
2017-10-03
2017-10-04
2017-10-05
2017-10-06
2017-10-07
2017-10-08
2017-10-09
2017-10-10 | 2481 | 2481 | Running Incident | Issue Describe:High Voltage unstable Next Step:Debugging Owner:Yao Yuxing
2017-10-11 | 2481 | 0 | Running Incident | Issue Describe:High Voltage unstable Next Step:Debugging Owner:Yao Yuxing
2017-10-12 | 2481 | 0 | Running Incident | Issue Describe:High Voltage unstable Next Step:Waiting PTA result Owner:Yao Yuxing
2017-10-13 | 2481 | 0 | Running Incident | Issue Date:9/21 Issue Describe:High Voltage unstable Next Step:Waiting PTA result,plan to run on 10/18. Owner:Yao Yuxing
2017-10-14
2017-10-15
2017-10-16 | 2481 | 2481 | Running Incident | Issue Date:9/21 Issue Describe:High Voltage unstable Next Step:Waiting PTA result,plan to run on 10/18. Owner:Yao Yuxing
2017-10-17 | 2481 | 0 | Running Incident | Issue Date:9/21 Issue Describe:High Voltage unstable Next Step:Annual maintance 10/16—10/17(Lin Xiaoquan)，waiting PTA result,plan to run on 10/18. Owner:Yao Yuxing
2017-10-18 | 2481 | 0 | Running Incident | Issue Date:9/21 Issue Describe:High Voltage unstable Next Step:Change CAL,plan to run on 10/19—Hong Nianzhong Discuss permanent solution tomorrow(2017.10.19)—Yao Yuxing
2017-10-19 | 2481 | 0 | Running | Issue Date:9/21 Issue Describe:High Voltage unstable Next Step:Waiting GE response Target Date:TBD Owner:Yao Yuxing
2017-10-20 | 2428 | -53 | Running | Issue Date:9/21 Issue Describe:High Voltage unstable Next Step:Try to find permanent solution Target Date:TBD Owner:Yao Yuxing
2017-10-21
2017-10-22
2017-10-23 | 2835 | 2835 | Running
2017-10-24 | 3051 | 216 | Running
2017-10-25 | 3178 | 127 | Running
2017-10-26 | 3230 | 52 | Running Incident | Issue Date:10/26 Issue Describe:Device error Target Date:10/27 Owner:Yao Yuxing
2017-10-27 | 3230 | 0 | Running Incident | Issue Date:10/26 Issue Describe:Device error,waiting Horiba to fix device Next Step:Expected to run 10/30. Owner:Yao Yuxing
2017-10-28
2017-10-29
2017-10-30 | 3230 | 3230 | Running Incident | Issue Date:10/30 Issue Describe:Axle shaft broken. Next Step:Swap new axle shaft 10/30,waiting PTA results Owner:Lin Xiaoquan
2017-10-31 | 3230 | 0 | Running Incident | Issue Date:10/30 Issue Describe:Facility fault Next Step:Fix facility Target Date:TBD Owner:Yao Yuxing
2017-11-01 | 3230 | 0 | Running Incident | Issue Date:10/30 Issue Describe:Facility fault Next Step:Fix facility Target Date:11/2 Owner:Yao Yuxing
2017-11-02 | 3230 | 0 | Running Incident | Issue Date:10/30 Issue Describe:Facility fault Next Step:Fix facility Target Date:11/2 Owner:Yao Yuxing
2017-11-03 | 3230 | 0 | Running Incident | Issue Date:10/30 Issue Describe:Facility fault Next Step:Fix facility Target Date:11/6 Owner:Yao Yuxing
2017-11-04
2017-11-05
2017-11-06 | 3230 | 3230 | Running Incident | Issue Date:10/30 Issue Describe:Facility fault Next Step:Fix facility Target Date:TBD Owner:Yao Yuxing
2017-11-07 | 3230 | 0 | Running Incident | Issue Date:10/30 Issue Describe:Facility fault Next Step:Fix facility Target Date:TBD Owner:Yao Yuxing
2017-11-08
2017-11-09
2017-11-10
2017-11-11
2017-11-12
2017-11-13
2017-11-14
2017-11-15
2017-11-16
2017-11-17
2017-11-18
2017-11-19
2017-11-20
2017-11-21
2017-11-22
2017-11-23
2017-11-24
2017-11-25
2017-11-26
2017-11-27
2017-11-28
2017-11-29
2017-11-30
2017-12-01
2017-12-02
2017-12-03
2017-12-04
2017-12-05
2017-12-06
2017-12-07
2017-12-08 | [8 empty] | -52.5
2017-12-09
2017-12-10
2017-12-11
2017-12-12
2017-12-13
2017-12-14
2017-12-15
2017-12-16
2017-12-17
2017-12-18
2017-12-19
2017-12-20
2017-12-21
2017-12-22
2017-12-23
2017-12-24
2017-12-25
2017-12-26
2017-12-27
2017-12-28
2017-12-29
2017-12-30
2017-12-31
2018-01-01
2018-01-02
2018-01-03
2018-01-04
2018-01-05
2018-01-06
2018-01-07
2018-01-08
2018-01-09
2018-01-10
2018-01-11
2018-01-12
3230
1
Average Daily Cycles Calculations
Weekends? | DID NOT Run Weekends
Working Days for Average Calculation | #N/A
Total Days Since SOT | 41
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
Formulas:
Columns Active (Click to activate) = NETWORKDAYS(A1600,[Columns Active (Click to activate), row above],Holidays!$A2:A36)
Note on A2: This document supports up to 15 transmissions at any given time. To hide extra columns, select the column of the given color that you would like to hide, right click, and select "Hide". Similarly, to bring back hidden columns, select the column immediately before and after the hidden column, right click, and select "unhide".
Note on B2: Type Engine RPO here.
Note on D2: Type Engine Number here.
Note on B3: Type Trans RPO here.
Note on D3: Type Transmission Number here.
Note on B4: Select a test cell.
Note on E4: Insert test schedule here.
Note on C5: Insert cycle goal here.
Note on E5: Insert pallet # here.
Note on C6: Type trans software here.
Note on E6: Type engine software here.
Note on C7: Enter PQMS # here.
Note on E7: Insert PON # here.
Note on D9: Type back up transmission number here.
Note on A10: Insert date here. Clicking on the cell and dragging it down to the cell below will automatically fill out the date for the next day. This does not skip weekends, however. Only add the latest date (Do not drag the date past your latest entry) or else the tracking sheet will not see your data. The tracking sheet looks at the latest date, regardless of whether or not there is information in it.
Help
Search
Help
Search
x
^
Jump to Latest Entry Date
Fill in Today's Date

## Settings (hidden)
Pontiac Dyno Tracking Sheet
Columns Active (Click to activate)
Engine |  | Cell Contents
RPO |  |  | Trans RPO | Engine RPO | Pallet | Title
| 1 | C9KFG182CQ | MKF | L2B | PTC | GFE Gamma TEDD Validation (K226 Local Content)
| 2 | C9KFG113CQ | MKF | L2B | PTB | GFE GammaStart&Stop Validation (K226 Local Content)
| 3 | C9KFG168CQ | MKF | L2B | PTA | GFE Gamma TEDD Validation (K226 Local Content)
| 4 | #REF! | #REF! | #REF! | #REF! | #REF!
| 5 | 0 | GENII 6T40 | LAF | 0 | 0
| 6 | #REF! | #REF! | #REF! | #REF! | #REF!
| 7 | #REF! | #REF! | #REF! | #REF! | #REF!
| 8 | #REF! | #REF! | #REF! | #REF! | #REF!
| 9 | 0 | GENII 6T40 | LAF | 0 | 0
| 10 | 0 | GENII 6T40 | LAF | 0 | 0
| 11 | 0 | GENII 6T40 | LAF | 0 | 0
| 12 | 0 | GENII 6T40 | LAF | 0 | 0
| 13 | 0 | GENII 6T40 | LAF | 0 | 0
| 14 | 0 | GENII 6T40 | LAF | 0 | 0
| 15 | 0 | GENII 6T40 | LAF | 0 | 0
| 16 | 0 | GENII 6T40 | LAF | 0 | 0
| 17 | 0 | GENII 6T40 | LAF | 0 | 0
| 18 | 0 | GENII 6T40 | LAF | 0 | 0
| 19 | 0 | GENII 6T40 | LAF | 0 | 0
| 20 | 0 | GENII 6T40 | LAF | 0 | 0
| 21 | 0 | GENII 6T40 | LAF | 0 | 0
| 22 | 0 | GENII 6T40 | LAF | 0 | 0
| 23 | 0 | GENII 6T40 | LAF | 0 | 0
| 24 | 0 | GENII 6T40 | LAF | 0 | 0
| 25 | 0 | GENII 6T40 | LAF | 0 | 0
Version
Version
Note on G6: This document supports up to 15 transmissions at any given time. To hide extra columns, select the column of the given color that you would like to hide, right click, and select "Hide". Similarly, to bring back hidden columns, select the column immediately before and after the hidden column, right click, and select "unhide".

## 5 (hidden)
5
| LAF |  | LDK*111580392
Columns Active (Click to activate) | GENII 6T40 |  | 611FCRM1228A1474
| Test Cell |  | Test Schedule:
| Cycle Goal: |  | Pallet #:
| Trans Software: |  | Engine Software:
| PQMS# |  | PON#
Title:
| Back up Trans: |  |  |  | Part installed |  |  |  | Part removed
| Cycles | Cycles/day | Status | Comments | PN | Name | Prior cycles | Origin | PN | Name | Cycles on part Check for history! | Reason for change
0 | 0 | 0
Maximum Cycles/Day |  | 0
1
Average Daily Cycles Calculations
Weekends? | DID NOT Run Weekends
Working Days for Average Calculation | #N/A
Total Days Since SOT | 0
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
Help
Search
Help
Search
x
^
Jump to Latest Entry Date
Fill in Today's Date
Note on A2: This document supports up to 15 transmissions at any given time. To hide extra columns, select the column of the given color that you would like to hide, right click, and select "Hide". Similarly, to bring back hidden columns, select the column immediately before and after the hidden column, right click, and select "unhide".
Note on B2: Type Engine RPO here.
Note on D2: Type Engine Number here.
Note on B3: Type Trans RPO here.
Note on D3: Type Engine Number here.
Note on B4: Select a test cell.
Note on E4: Insert test schedule here.
Note on C5: Insert cycle goal here.
Note on E5: Insert pallet # here.
Note on C6: Type trans software here.
Note on E6: Type engine software here.
Note on D9: Type back up transmission number here.
Note on A10: Insert date here. Clicking on the cell and dragging it down to the cell below will automatically fill out the date for the next day. This does not skip weekends, however. Only add the latest date (Do not drag the date past your latest entry) or else the tracking sheet will not see your data. The tracking sheet looks at the latest date, regardless of whether or not there is information in it.

## 9 (hidden)
9
| LAF |  | LDK*111580392
Columns Active (Click to activate) | GENII 6T40 |  | 611FCRM1228A1474
| Test Cell |  | Test Schedule:
| Cycle Goal: |  | Pallet #:
| Trans Software: |  | Engine Software:
| PQMS# |  | PON#
Title:
| Back up Trans: |  |  |  | Part installed |  |  |  | Part removed
| Cycles | Cycles/day | Status | Comments | PN | Name | Prior cycles | Origin | PN | Name | Cycles on part Check for history! | Reason for change
0 | #REF! | 0
Maximum Cycles/Day |  | 0
1
Average Daily Cycles Calculations
Weekends? | DID NOT Run Weekends
Working Days for Average Calculation | #N/A
Total Days Since SOT | 0
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
Help
Search
x
^
Jump to Latest Entry Date
Fill in Today's Date
Note on A2: This document supports up to 15 transmissions at any given time. To hide extra columns, select the column of the given color that you would like to hide, right click, and select "Hide". Similarly, to bring back hidden columns, select the column immediately before and after the hidden column, right click, and select "unhide".
Note on B2: Type Engine RPO here.
Note on D2: Type Engine Number here.
Note on B3: Type Trans RPO here.
Note on D3: Type Transmission Number here.
Note on B4: Select a test cell.
Note on E4: Insert test schedule here.
Note on C5: Insert cycle goal here.
Note on E5: Insert pallet # here.
Note on C6: Type trans software here.
Note on E6: Type engine software here.
Note on C7: Enter PQMS # here.
Note on E7: Insert PON # here.
Note on D9: Type back up transmission number here.
Note on A10: Insert date here. Clicking on the cell and dragging it down to the cell below will automatically fill out the date for the next day. This does not skip weekends, however. Only add the latest date (Do not drag the date past your latest entry) or else the tracking sheet will not see your data. The tracking sheet looks at the latest date, regardless of whether or not there is information in it.

## 10 (hidden)
10
| LAF |  | LDK*111580392
Columns Active (Click to activate) | GENII 6T40 |  | 611FCRM1228A1474
| Test Cell |  | Test Schedule:
| Cycle Goal: |  | Pallet #:
| Trans Software: |  | Engine Software:
| PQMS# |  | PON#
Title
| Back up Trans: |  |  |  | Part installed |  |  |  | Part removed
| Cycles | Cycles/day | Status | Comments | PN | Name | Prior cycles | Origin | PN | Name | Cycles on part Check for history! | Reason for change
0 | 0 | 0
Maximum Cycles/Day |  | 0
1
Average Daily Cycles Calculations
Weekends? | DID NOT Run Weekends
Working Days for Average Calculation | #N/A
Total Days Since SOT | 0
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
Help
Search
x
^
Jump to Latest Entry Date
Fill in Today's Date
Note on A2: This document supports up to 15 transmissions at any given time. To hide extra columns, select the column of the given color that you would like to hide, right click, and select "Hide". Similarly, to bring back hidden columns, select the column immediately before and after the hidden column, right click, and select "unhide".
Note on B2: Type Engine RPO here.
Note on D2: Type Engine Number here.
Note on B3: Type Trans RPO here.
Note on D3: Type Transmission Number here.
Note on B4: Select a test cell.
Note on E4: Insert test schedule here.
Note on C5: Insert cycle goal here.
Note on E5: Insert pallet # here.
Note on C6: Type trans software here.
Note on E6: Type engine software here.
Note on D9: Type back up transmission number here.
Note on A10: Insert date here. Clicking on the cell and dragging it down to the cell below will automatically fill out the date for the next day. This does not skip weekends, however. Only add the latest date (Do not drag the date past your latest entry) or else the tracking sheet will not see your data. The tracking sheet looks at the latest date, regardless of whether or not there is information in it.

## 11 (hidden)
11
| LAF |  | LDK*111580392
Columns Active (Click to activate) | GENII 6T40 |  | 611FCRM1228A1474
| Test Cell |  | Test Schedule:
| Cycle Goal: |  | Pallet #:
| Trans Software: |  | Engine Software:
| PQMS# |  | PON#
Title:
| Back up Trans: |  |  |  | Part installed |  |  |  | Part removed
| Cycles | Cycles/day | Status | Comments | PN | Name | Prior cycles | Origin | PN | Name | Cycles on part Check for history! | Reason for change
0 | 0 | 0
Maximum Cycles/Day |  | 0
1
Average Daily Cycles Calculations
Weekends? | DID NOT Run Weekends
Working Days for Average Calculation | #N/A
Total Days Since SOT | 0
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
Help
Search
x
^
Jump to Latest Entry Date
Fill in Today's Date
Note on A2: This document supports up to 15 transmissions at any given time. To hide extra columns, select the column of the given color that you would like to hide, right click, and select "Hide". Similarly, to bring back hidden columns, select the column immediately before and after the hidden column, right click, and select "unhide".
Note on B2: Type Engine RPO here.
Note on D2: Type Engine Number here.
Note on B3: Type Trans RPO here.
Note on D3: Type Transmission Number here.
Note on B4: Select a test cell.
Note on E4: Insert test schedule here.
Note on C5: Insert cycle goal here.
Note on E5: Insert pallet # here.
Note on C6: Type trans software here.
Note on E6: Type engine software here.
Note on D9: Type back up transmission number here.
Note on A10: Insert date here. Clicking on the cell and dragging it down to the cell below will automatically fill out the date for the next day. This does not skip weekends, however. Only add the latest date (Do not drag the date past your latest entry) or else the tracking sheet will not see your data. The tracking sheet looks at the latest date, regardless of whether or not there is information in it.

## 12 (hidden)
12
| LAF |  | LDK*111580392
Columns Active (Click to activate) | GENII 6T40 |  | 611FCRM1228A1474
| Test Cell |  | Test Schedule:
| Cycle Goal: |  | Pallet #:
| Trans Software: |  | Engine Software:
| PQMS# |  | PON#
Title:
| Back up Trans: |  |  |  | Part installed |  |  |  | Part removed
| Cycles | Cycles/day | Status | Comments | PN | Name | Prior cycles | Origin | PN | Name | Cycles on part Check for history! | Reason for change
0 | 0 | 0
Maximum Cycles/Day |  | 0
1
Average Daily Cycles Calculations
Weekends? | Ran Weekends
Working Days for Average Calculation | #N/A
Total Days Since SOT | 0
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
Help
Search
x
^
Jump to Latest Entry Date
Fill in Today's Date
Note on A2: This document supports up to 15 transmissions at any given time. To hide extra columns, select the column of the given color that you would like to hide, right click, and select "Hide". Similarly, to bring back hidden columns, select the column immediately before and after the hidden column, right click, and select "unhide".
Note on B2: Type Engine RPO here.
Note on D2: Type Engine Number here.
Note on B3: Type Trans RPO here.
Note on D3: Type Transmission Number here.
Note on B4: Select a test cell.
Note on E4: Insert test schedule here.
Note on C5: Insert cycle goal here.
Note on E5: Insert pallet # here.
Note on C6: Type trans software here.
Note on E6: Type engine software here.
Note on D9: Type back up transmission number here.
Note on A10: Insert date here. Clicking on the cell and dragging it down to the cell below will automatically fill out the date for the next day. This does not skip weekends, however. Only add the latest date (Do not drag the date past your latest entry) or else the tracking sheet will not see your data. The tracking sheet looks at the latest date, regardless of whether or not there is information in it.

## 13 (hidden)
13
| LAF |  | LDK*111580392
Columns Active (Click to activate) | GENII 6T40 |  | 611FCRM1228A1474
| Test Cell |  | Test Schedule:
| Cycle Goal: |  | Pallet #:
| Trans Software: |  | Engine Software:
| PQMS# |  | PON#
Title
| Back up Trans: |  |  |  | Part installed |  |  |  | Part removed
| Cycles | Cycles/day | Status | Comments | PN | Name | Prior cycles | Origin | PN | Name | Cycles on part Check for history! | Reason for change
0 | 0 | 0
Maximum Cycles/Day |  | 0
1
Average Daily Cycles Calculations
Weekends? | DID NOT Run Weekends
Working Days for Average Calculation | #N/A
Total Days Since SOT | 0
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
Help
Search
x
^
Jump to Latest Entry Date
Fill in Today's Date
Note on A2: This document supports up to 15 transmissions at any given time. To hide extra columns, select the column of the given color that you would like to hide, right click, and select "Hide". Similarly, to bring back hidden columns, select the column immediately before and after the hidden column, right click, and select "unhide".
Note on B2: Type Engine RPO here.
Note on D2: Type Engine Number here.
Note on B3: Type Trans RPO here.
Note on D3: Type Transmission Number here.
Note on B4: Select a test cell.
Note on E4: Insert test schedule here.
Note on C5: Insert cycle goal here.
Note on E5: Insert pallet # here.
Note on C6: Type trans software here.
Note on E6: Type engine software here.
Note on D9: Type back up transmission number here.
Note on A10: Insert date here. Clicking on the cell and dragging it down to the cell below will automatically fill out the date for the next day. This does not skip weekends, however. Only add the latest date (Do not drag the date past your latest entry) or else the tracking sheet will not see your data. The tracking sheet looks at the latest date, regardless of whether or not there is information in it.

## 14 (hidden)
14
| LAF |  | LDK*111580392
Columns Active (Click to activate) | GENII 6T40 |  | 611FCRM1228A1474
| Test Cell |  | Test Schedule:
| Cycle Goal: |  | Pallet #:
| Trans Software: |  | Engine Software:
| PQMS# |  | PON#
Title:
| Back up Trans: |  |  |  | Part installed |  |  |  | Part removed
| Cycles | Cycles/day | Status | Comments | PN | Name | Prior cycles | Origin | PN | Name | Cycles on part Check for history! | Reason for change
0 | 0 | 0
Maximum Cycles/Day |  | 0
1
Average Daily Cycles Calculations
Weekends? | DID NOT Run Weekends
Working Days for Average Calculation | #N/A
Total Days Since SOT | 0
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
Help
Search
x
^
Jump to Latest Entry Date
Fill in Today's Date
Note on A2: This document supports up to 15 transmissions at any given time. To hide extra columns, select the column of the given color that you would like to hide, right click, and select "Hide". Similarly, to bring back hidden columns, select the column immediately before and after the hidden column, right click, and select "unhide".
Note on B2: Type Engine RPO here.
Note on D2: Type Engine Number here.
Note on B3: Type Trans RPO here.
Note on D3: Type Transmission Number here.
Note on B4: Select a test cell.
Note on E4: Insert test schedule here.
Note on C5: Insert cycle goal here.
Note on E5: Insert pallet # here.
Note on C6: Type trans software here.
Note on E6: Type engine software here.
Note on D9: Type back up transmission number here.
Note on A10: Insert date here. Clicking on the cell and dragging it down to the cell below will automatically fill out the date for the next day. This does not skip weekends, however. Only add the latest date (Do not drag the date past your latest entry) or else the tracking sheet will not see your data. The tracking sheet looks at the latest date, regardless of whether or not there is information in it.

## 15 (hidden)
15
| LAF |  | LDK*111580392
Columns Active (Click to activate) | GENII 6T40 |  | 611FCRM1228A1474
| Test Cell |  | Test Schedule:
| Cycle Goal: |  | Pallet #:
| Trans Software: |  | Engine Software:
| PQMS# |  | PON#
Title:
| Back up Trans: |  |  |  | Part installed |  |  |  | Part removed
| Cycles | Cycles/day | Status | Comments | PN | Name | Prior cycles | Origin | PN | Name | Cycles on part Check for history! | Reason for change
0 | 0 | 0
Maximum Cycles/Day |  | 0
1
Average Daily Cycles Calculations
Weekends? | DID NOT Run Weekends
Working Days for Average Calculation | #N/A
Total Days Since SOT | 0
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
Help
Search
x
^
Jump to Latest Entry Date
Fill in Today's Date
Note on A2: This document supports up to 15 transmissions at any given time. To hide extra columns, select the column of the given color that you would like to hide, right click, and select "Hide". Similarly, to bring back hidden columns, select the column immediately before and after the hidden column, right click, and select "unhide".
Note on B2: Type Engine RPO here.
Note on D2: Type Engine Number here.
Note on B3: Type Trans RPO here.
Note on D3: Type Transmission Number here.
Note on B4: Select a test cell.
Note on E4: Insert test schedule here.
Note on C5: Insert cycle goal here.
Note on E5: Insert pallet # here.
Note on C6: Type trans software here.
Note on E6: Type engine software here.
Note on D9: Type back up transmission number here.
Note on A10: Insert date here. Clicking on the cell and dragging it down to the cell below will automatically fill out the date for the next day. This does not skip weekends, however. Only add the latest date (Do not drag the date past your latest entry) or else the tracking sheet will not see your data. The tracking sheet looks at the latest date, regardless of whether or not there is information in it.

## 16 (hidden)
16
| LAF |  | LDK*111580392
Columns Active (Click to activate) | GENII 6T40 |  | 611FCRM1228A1474
| Test Cell |  | Test Schedule:
| Cycle Goal: |  | Pallet #:
| Trans Software: |  | Engine Software:
| PQMS# |  | PON#
Title:
| Back up Trans: |  |  |  | Part installed |  |  |  | Part removed
| Cycles | Cycles/day | Status | Comments | PN | Name | Prior cycles | Origin | PN | Name | Cycles on part Check for history! | Reason for change
0 | 0 | 0
Maximum Cycles/Day |  | 0
1
Average Daily Cycles Calculations
Weekends? | DID NOT Run Weekends
Working Days for Average Calculation | #N/A
Total Days Since SOT | 0
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
Help
Search
x
^
Jump to Latest Entry Date
Fill in Today's Date
Note on A2: This document supports up to 15 transmissions at any given time. To hide extra columns, select the column of the given color that you would like to hide, right click, and select "Hide". Similarly, to bring back hidden columns, select the column immediately before and after the hidden column, right click, and select "unhide".
Note on B2: Type Engine RPO here.
Note on D2: Type Engine Number here.
Note on B3: Type Trans RPO here.
Note on D3: Type Transmission Number here.
Note on B4: Select a test cell.
Note on E4: Insert test schedule here.
Note on C5: Insert cycle goal here.
Note on E5: Insert pallet # here.
Note on C6: Type trans software here.
Note on E6: Type engine software here.
Note on D9: Type back up transmission number here.
Note on A10: Insert date here. Clicking on the cell and dragging it down to the cell below will automatically fill out the date for the next day. This does not skip weekends, however. Only add the latest date (Do not drag the date past your latest entry) or else the tracking sheet will not see your data. The tracking sheet looks at the latest date, regardless of whether or not there is information in it.

## 17 (hidden)
17
| LAF |  | LDK*111580392
Columns Active (Click to activate) | GENII 6T40 |  | 611FCRM1228A1474
| Test Cell |  | Test Schedule:
| Cycle Goal: |  | Pallet #:
| Trans Software: |  | Engine Software:
| PQMS# |  | PON#
Title:
| Back up Trans: |  |  |  | Part installed |  |  |  | Part removed
| Cycles | Cycles/day | Status | Comments | PN | Name | Prior cycles | Origin | PN | Name | Cycles on part Check for history! | Reason for change
0 | 0 | 0
Maximum Cycles/Day |  | 0
1
Average Daily Cycles Calculations
Weekends? | DID NOT Run Weekends
Working Days for Average Calculation | #N/A
Total Days Since SOT | 0
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
Help
Search
x
^
Jump to Latest Entry Date
Fill in Today's Date
Note on A2: This document supports up to 15 transmissions at any given time. To hide extra columns, select the column of the given color that you would like to hide, right click, and select "Hide". Similarly, to bring back hidden columns, select the column immediately before and after the hidden column, right click, and select "unhide".
Note on B2: Type Engine RPO here.
Note on D2: Type Engine Number here.
Note on B3: Type Trans RPO here.
Note on D3: Type Transmission Number here.
Note on B4: Select a test cell.
Note on E4: Insert test schedule here.
Note on C5: Insert cycle goal here.
Note on E5: Insert pallet # here.
Note on C6: Type trans software here.
Note on E6: Type engine software here.
Note on D9: Type back up transmission number here.
Note on A10: Insert date here. Clicking on the cell and dragging it down to the cell below will automatically fill out the date for the next day. This does not skip weekends, however. Only add the latest date (Do not drag the date past your latest entry) or else the tracking sheet will not see your data. The tracking sheet looks at the latest date, regardless of whether or not there is information in it.

## 18 (hidden)
18
| LAF |  | LDK*111580392
Columns Active (Click to activate) | GENII 6T40 |  | 611FCRM1228A1474
| Test Cell |  | Test Schedule:
| Cycle Goal: |  | Pallet #:
| Trans Software: |  | Engine Software:
| PQMS# |  | PON#
Title:
| Back up Trans: |  |  |  | Part installed |  |  |  | Part removed
| Cycles | Cycles/day | Status | Comments | PN | Name | Prior cycles | Origin | PN | Name | Cycles on part Check for history! | Reason for change
0 | 0 | 0
Maximum Cycles/Day |  | 0
1
Average Daily Cycles Calculations
Weekends? | DID NOT Run Weekends
Working Days for Average Calculation | #N/A
Total Days Since SOT | 0
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
Help
Search
x
^
Jump to Latest Entry Date
Fill in Today's Date
Note on A2: This document supports up to 15 transmissions at any given time. To hide extra columns, select the column of the given color that you would like to hide, right click, and select "Hide". Similarly, to bring back hidden columns, select the column immediately before and after the hidden column, right click, and select "unhide".
Note on B2: Type Engine RPO here.
Note on D2: Type Engine Number here.
Note on B3: Type Trans RPO here.
Note on D3: Type Engine Number here.
Note on B4: Select a test cell.
Note on E4: Insert test schedule here.
Note on C5: Insert cycle goal here.
Note on E5: Insert pallet # here.
Note on C6: Type trans software here.
Note on E6: Type engine software here.
Note on D9: Type back up transmission number here.
Note on A10: Insert date here. Clicking on the cell and dragging it down to the cell below will automatically fill out the date for the next day. This does not skip weekends, however. Only add the latest date (Do not drag the date past your latest entry) or else the tracking sheet will not see your data. The tracking sheet looks at the latest date, regardless of whether or not there is information in it.

## 19 (hidden)
19
| LAF |  | LDK*111580392
Columns Active (Click to activate) | GENII 6T40 |  | 611FCRM1228A1474
| Test Cell |  | Test Schedule:
| Cycle Goal: |  | Pallet #:
| Trans Software: |  | Engine Software:
| PQMS# |  | PON#
Title:
| Back up Trans: |  |  |  | Part installed |  |  |  | Part removed
| Cycles | Cycles/day | Status | Comments | PN | Name | Prior cycles | Origin | PN | Name | Cycles on part Check for history! | Reason for change
0 | 0 | 0
Maximum Cycles/Day |  | 0
1
Average Daily Cycles Calculations
Weekends? | DID NOT Run Weekends
Working Days for Average Calculation | #N/A
Total Days Since SOT | 0
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
Help
Search
x
^
Jump to Latest Entry Date
Fill in Today's Date
Note on A2: This document supports up to 15 transmissions at any given time. To hide extra columns, select the column of the given color that you would like to hide, right click, and select "Hide". Similarly, to bring back hidden columns, select the column immediately before and after the hidden column, right click, and select "unhide".
Note on B2: Type Engine RPO here.
Note on D2: Type Engine Number here.
Note on B3: Type Trans RPO here.
Note on D3: Type Transmission Number here.
Note on B4: Select a test cell.
Note on E4: Insert test schedule here.
Note on C5: Insert cycle goal here.
Note on E5: Insert pallet # here.
Note on C6: Type trans software here.
Note on E6: Type engine software here.
Note on D9: Type back up transmission number here.
Note on A10: Insert date here. Clicking on the cell and dragging it down to the cell below will automatically fill out the date for the next day. This does not skip weekends, however. Only add the latest date (Do not drag the date past your latest entry) or else the tracking sheet will not see your data. The tracking sheet looks at the latest date, regardless of whether or not there is information in it.

## 20 (hidden)
20
| LAF |  | LDK*111580392
Columns Active (Click to activate) | GENII 6T40 |  | 611FCRM1228A1474
| Test Cell |  | Test Schedule:
| Cycle Goal: |  | Pallet #:
| Trans Software: |  | Engine Software:
| PQMS# |  | PON#
Title:
| Back up Trans: |  |  |  | Part installed |  |  |  | Part removed
| Cycles | Cycles/day | Status | Comments | PN | Name | Prior cycles | Origin | PN | Name | Cycles on part Check for history! | Reason for change
0 | 0 | 0
Maximum Cycles/Day |  | 0
1
Average Daily Cycles Calculations
Weekends? | DID NOT Run Weekends
Working Days for Average Calculation | #N/A
Total Days Since SOT | 0
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
Help
Search
x
^
Jump to Latest Entry Date
Fill in Today's Date
Note on A2: This document supports up to 15 transmissions at any given time. To hide extra columns, select the column of the given color that you would like to hide, right click, and select "Hide". Similarly, to bring back hidden columns, select the column immediately before and after the hidden column, right click, and select "unhide".
Note on B2: Type Engine RPO here.
Note on D2: Type Engine Number here.
Note on B3: Type Trans RPO here.
Note on D3: Type Transmission Number here.
Note on B4: Select a test cell.
Note on E4: Insert test schedule here.
Note on C5: Insert cycle goal here.
Note on E5: Insert pallet # here.
Note on C6: Type trans software here.
Note on E6: Type engine software here.
Note on D9: Type back up transmission number here.
Note on A10: Insert date here. Clicking on the cell and dragging it down to the cell below will automatically fill out the date for the next day. This does not skip weekends, however. Only add the latest date (Do not drag the date past your latest entry) or else the tracking sheet will not see your data. The tracking sheet looks at the latest date, regardless of whether or not there is information in it.

## 21 (hidden)
21
| LAF |  | LDK*111580392
Columns Active (Click to activate) | GENII 6T40 |  | 611FCRM1228A1474
| Test Cell |  | Test Schedule:
| Cycle Goal: |  | Pallet #:
| Trans Software: |  | Engine Software:
| PQMS# |  | PON#
Title:
| Back up Trans: |  |  |  | Part installed |  |  |  | Part removed
| Cycles | Cycles/day | Status | Comments | PN | Name | Prior cycles | Origin | PN | Name | Cycles on part Check for history! | Reason for change
0 | 0 | 0
Maximum Cycles/Day |  | 0
1
Average Daily Cycles Calculations
Weekends? | DID NOT Run Weekends
Working Days for Average Calculation | #N/A
Total Days Since SOT | 0
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
Help
Search
x
^
Jump to Latest Entry Date
Fill in Today's Date
Note on A2: This document supports up to 15 transmissions at any given time. To hide extra columns, select the column of the given color that you would like to hide, right click, and select "Hide". Similarly, to bring back hidden columns, select the column immediately before and after the hidden column, right click, and select "unhide".
Note on B2: Type Engine RPO here.
Note on D2: Type Engine Number here.
Note on B3: Type Trans RPO here.
Note on D3: Type Transmission Number here.
Note on B4: Select a test cell.
Note on E4: Insert test schedule here.
Note on C5: Insert cycle goal here.
Note on E5: Insert pallet # here.
Note on C6: Type trans software here.
Note on E6: Type engine software here.
Note on D9: Type back up transmission number here.
Note on A10: Insert date here. Clicking on the cell and dragging it down to the cell below will automatically fill out the date for the next day. This does not skip weekends, however. Only add the latest date (Do not drag the date past your latest entry) or else the tracking sheet will not see your data. The tracking sheet looks at the latest date, regardless of whether or not there is information in it.

## 22 (hidden)
22
| LAF |  | LDK*111580392
Columns Active (Click to activate) | GENII 6T40 |  | 611FCRM1228A1474
| Test Cell |  | Test Schedule:
| Cycle Goal: |  | Pallet #:
| Trans Software: |  | Engine Software:
| PQMS# |  | PON#
Title:
| Back up Trans: |  |  |  | Part installed |  |  |  | Part removed
| Cycles | Cycles/day | Status | Comments | PN | Name | Prior cycles | Origin | PN | Name | Cycles on part Check for history! | Reason for change
2014-06-03
0 | 0 | 0
Maximum Cycles/Day |  | 0
1
Average Daily Cycles Calculations
Weekends? | DID NOT Run Weekends
Working Days for Average Calculation | #N/A
Total Days Since SOT | 0
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
Help
Search
x
^
Jump to Latest Entry Date
Fill in Today's Date
Note on A2: This document supports up to 15 transmissions at any given time. To hide extra columns, select the column of the given color that you would like to hide, right click, and select "Hide". Similarly, to bring back hidden columns, select the column immediately before and after the hidden column, right click, and select "unhide".
Note on B2: Type Engine RPO here.
Note on D2: Type Engine Number here.
Note on B3: Type Trans RPO here.
Note on D3: Type Transmission Number here.
Note on B4: Select a test cell.
Note on E4: Insert test schedule here.
Note on C5: Insert cycle goal here.
Note on E5: Insert pallet # here.
Note on C6: Type trans software here.
Note on E6: Type engine software here.
Note on D9: Type back up transmission number here.
Note on A10: Insert date here. Clicking on the cell and dragging it down to the cell below will automatically fill out the date for the next day. This does not skip weekends, however. Only add the latest date (Do not drag the date past your latest entry) or else the tracking sheet will not see your data. The tracking sheet looks at the latest date, regardless of whether or not there is information in it.

## 23 (hidden)
23
| LAF |  | LDK*111580392
Columns Active (Click to activate) | GENII 6T40 |  | 611FCRM1228A1474
| Test Cell |  | Test Schedule:
| Cycle Goal: |  | Pallet #:
| Trans Software: |  | Engine Software:
| PQMS# |  | PON#
Title:
| Back up Trans: |  |  |  | Part installed |  |  |  | Part removed
| Cycles | Cycles/day | Status | Comments | PN | Name | Prior cycles | Origin | PN | Name | Cycles on part Check for history! | Reason for change
0 | 0 | 0
Maximum Cycles/Day |  | 0
1
Average Daily Cycles Calculations
Weekends? | DID NOT Run Weekends
Working Days for Average Calculation | #N/A
Total Days Since SOT | 0
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
Help
Search
x
^
Jump to Latest Entry Date
Fill in Today's Date
Note on A2: This document supports up to 15 transmissions at any given time. To hide extra columns, select the column of the given color that you would like to hide, right click, and select "Hide". Similarly, to bring back hidden columns, select the column immediately before and after the hidden column, right click, and select "unhide".
Note on B2: Type Engine RPO here.
Note on D2: Type Engine Number here.
Note on B3: Type Trans RPO here.
Note on D3: Type Transmission Number here.
Note on B4: Select a test cell.
Note on E4: Insert test schedule here.
Note on C5: Insert cycle goal here.
Note on E5: Insert pallet # here.
Note on C6: Type trans software here.
Note on E6: Type engine software here.
Note on D9: Type back up transmission number here.
Note on A10: Insert date here. Clicking on the cell and dragging it down to the cell below will automatically fill out the date for the next day. This does not skip weekends, however. Only add the latest date (Do not drag the date past your latest entry) or else the tracking sheet will not see your data. The tracking sheet looks at the latest date, regardless of whether or not there is information in it.

## 24 (hidden)
24
| LAF |  | LDK*111580392
Columns Active (Click to activate) | GENII 6T40 |  | 611FCRM1228A1474
| Test Cell |  | Test Schedule:
| Cycle Goal: |  | Pallet #:
| Trans Software: |  | Engine Software:
| PQMS# |  | PON#
Title:
| Back up Trans: |  |  |  | Part installed |  |  |  | Part removed
| Cycles | Cycles/day | Status | Comments | PN | Name | Prior cycles | Origin | PN | Name | Cycles on part Check for history! | Reason for change
0 | 0 | 0
Maximum Cycles/Day |  | 0
1
Average Daily Cycles Calculations
Weekends? | DID NOT Run Weekends
Working Days for Average Calculation | #N/A
Total Days Since SOT | 0
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
Help
Search
x
^
Jump to Latest Entry Date
Fill in Today's Date
Note on A2: This document supports up to 15 transmissions at any given time. To hide extra columns, select the column of the given color that you would like to hide, right click, and select "Hide". Similarly, to bring back hidden columns, select the column immediately before and after the hidden column, right click, and select "unhide".
Note on B2: Type Engine RPO here.
Note on D2: Type Engine Number here.
Note on B3: Type Trans RPO here.
Note on D3: Type Transmission Number here.
Note on B4: Select a test cell.
Note on E4: Insert test schedule here.
Note on C5: Insert cycle goal here.
Note on E5: Insert pallet # here.
Note on C6: Type trans software here.
Note on E6: Type engine software here.
Note on D9: Type back up transmission number here.
Note on A10: Insert date here. Clicking on the cell and dragging it down to the cell below will automatically fill out the date for the next day. This does not skip weekends, however. Only add the latest date (Do not drag the date past your latest entry) or else the tracking sheet will not see your data. The tracking sheet looks at the latest date, regardless of whether or not there is information in it.

## 25 (hidden)
25
| LAF |  | LDK*111580392
Columns Active (Click to activate) | GENII 6T40 |  | 611FCRM1228A1474
| Test Cell |  | Test Schedule:
| Cycle Goal: |  | Pallet #:
| Trans Software: |  | Engine Software:
| PQMS# |  | PON#
Title:
| Back up Trans: |  |  |  | Part installed |  |  |  | Part removed
| Cycles | Cycles/day | Status | Comments | PN | Name | Prior cycles | Origin | PN | Name | Cycles on part Check for history! | Reason for change
0 | 0 | 0
Maximum Cycles/Day |  | 0
1
Average Daily Cycles Calculations
Weekends? | DID NOT Run Weekends
Working Days for Average Calculation | #N/A
Total Days Since SOT | 0
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
Help
Search
x
^
Jump to Latest Entry Date
Fill in Today's Date
Note on A2: This document supports up to 15 transmissions at any given time. To hide extra columns, select the column of the given color that you would like to hide, right click, and select "Hide". Similarly, to bring back hidden columns, select the column immediately before and after the hidden column, right click, and select "unhide".
Note on B2: Type Engine RPO here.
Note on D2: Type Engine Number here.
Note on B3: Type Trans RPO here.
Note on D3: Type Transmission Number here.
Note on B4: Select a test cell.
Note on E4: Insert test schedule here.
Note on C5: Insert cycle goal here.
Note on E5: Insert pallet # here.
Note on C6: Type trans software here.
Note on E6: Type engine software here.
Note on D9: Type back up transmission number here.
Note on A10: Insert date here. Clicking on the cell and dragging it down to the cell below will automatically fill out the date for the next day. This does not skip weekends, however. Only add the latest date (Do not drag the date past your latest entry) or else the tracking sheet will not see your data. The tracking sheet looks at the latest date, regardless of whether or not there is information in it.

## PTC (hidden)
1
| L2B |  | L2B*170763133
Columns Active (Click to activate) | MKF |  | C9KFG182CQ
| Test Cell |  | Test Schedule: | TEDD
| Cycle Goal: | 24000 | Pallet #: | PTC
| Trans Software: | S55TH_171712011_04Apr2017_TEDD_2 S55M1_171712011_04Apr2017_TEDD_2 S55M2_171712011_04Apr2017_TEDD_2 | Engine Software: | AA0202B516_toPATAC_FlashedMuleCar_Dynoized_3_9_2019
| PQMS# |  | PON#
|  | Title: | GFE Gamma TEDD Validation (K226 Local Content)
| Back up Trans: |  |  |  | Part installed |  |  |  | Part removed
| Cycles | Cycles/day | Status | Comments | PN | Name | Prior cycles | Origin | PN | Name | Cycles on part Check for history! | Reason for change
2017-07-18 | 0 | 0 | Pending | AVL commissioning
2017-07-19 | 0 | 0 | Pending | AVL commissioning
2017-07-20 | 0 | 0 | Pending | AVL commissioning
2017-07-21 | 0 | 0 | Pending | Running 2 cycles,waiting for GPS feedback
2017-07-22 | 0 | 0 | Pending | Running 2 cycles,waiting for GPS feedback
2017-07-23 | 0 | 0 | Pending | Running 2 cycles,waiting for GPS feedback
2017-07-24 | 0 | 0 | Pending | Waiting data trace confirm by GPS
2017-07-25 | 0 | 0 | Pending | Expect to sign off tomorrow,waiting to pallet installation for Gamma2 GFE
2017-07-26 | 0 | 0 | Pending | Waiting to pallet installation for Gamma2 GFE
2017-07-27 | 0 | 0 | Work In Progress | Dyno setup
2017-07-28 | 0 | 0 | Work In Progress | Dyno setup
2017-07-29 | 0 | 0 | Work In Progress | Dyno setup
2017-07-30 | 0 | 0 | Work In Progress | Dyno setup
2017-07-31 | 0 | 0 | Work In Progress | Dyno setup
2017-08-01 | 0 | 0 | Work In Progress | Install pressure sensor
2017-08-02 | 0 | 0 | Work In Progress | Annual maintance
2017-08-03 | 0 | 0 | Work In Progress | Annual maintance
2017-08-04 | 0 | 0 | Pending | Annual maintance
2017-08-05 | 0 | 0 | Pending | Annual maintance
2017-08-06 | 0 | 0 | Pending | Annual maintance
2017-08-07 | 0 | 0 | Work In Progress | Change dyno parameters for TEDD test,collect data to GPS
2017-08-08 | 0 | 0 | Work In Progress | Install ETK
2017-08-09 | 0 | 0 | Work In Progress | Ready to break-in
2017-08-10 | 0 | 0 | Work In Progress | Ready to break-in
2017-08-11 | 0 | 0 | Work In Progress | Finished break-in,modify vehicle speed to 170kph to start
2017-08-12
2017-08-13
2017-08-14 | 0 | 0 | Work In Progress | TPIM and ATF temperature exceed limit Freezing water cooling efficiency can not match test condition
2017-08-15 | 0 | 0 | Incident | TPIM and ATF temperature exceed limit Freezing water cooling efficiency can not match test condition Short term solution:Solve issue till 8/21—Xu Guoqiang/Gao Peiyuan Long term solution:Xu Guoqiang/Gao Peiyuan
2017-08-16 | 0 | 0 | Incident | TPIM and ATF temperature exceed limit Freezing water cooling efficiency can not match test condition Short term solution:Solve issue till 8/21—Xu Guoqiang/Gao Peiyuan Long term solution:Xu Guoqiang/Gao Peiyuan
2017-08-17
2017-08-18 | 0 | 0 | Incident | Cooling Flow Rate Measurement till 8/24—Gao Peiyuan Long term solution:Xu Guoqiang/Gao Peiyuan
2017-08-19
2017-08-20
2017-08-21 | 272 |  | Running | Cooling Flow Rate Measurement till 8/22—Gao Peiyuan Long term solution:Xu Guoqiang/Gao Peiyuan
2017-08-22 | 500 |  | Running | Cooling Flow Rate Measurement till 8/22—Gao Peiyuan Long term solution:Xu Guoqiang/Gao Peiyuan
2017-08-23 | 793 | 293 | Running | Stopped running due to AVL PUMA alarm last night Cooling Flow Rate Measurement till 8/22—Gao Peiyuan Long term solution:Xu Guoqiang/Gao Peiyuan
2017-08-24 | 1268 | 475 | Running | Cooling Flow Rate Measurement till 8/22—Gao Peiyuan Long term solution:Xu Guoqiang/Gao Peiyuan
2017-08-25 | 1750 | 482 | Running | Engine maintance and change DCDC filter,expect to run on 8/26
2017-08-26
2017-08-27
2017-08-28 | 3148 | 3148 | Running | Cooling Flow Rate Measurement Long term solution:Xu Guoqiang/Gao Peiyuan
2017-08-29 | 3684 | 536 | Running
2017-08-30 | 4210 | 526 | Running
2017-08-31 | 4554 | 344 | Running
2017-09-01 | 5054 | 500 | Work In Progress | Test suspended due to power off
2017-09-02
2017-09-03
2017-09-04 | 5160 | 5160 | Running
2017-09-05
2017-09-06 | 5988 | 5988
2017-09-07 | 6336 | 348 | Running
2017-09-08 | 6763 | 427 | Running
2017-09-09
2017-09-10
2017-09-11 | 7527 | 7527 | Running
2017-09-12 | 8052 | 525 | Running
2017-09-13 | 8533 | 481 | Running
2017-09-14 | 8866 | 333 | Work In Progress | Change new half shaft for dyno maintance
2017-09-15 | 9276 | 410 | Running
2017-09-16
2017-09-17
2017-09-18 | 10730 | 10730
2017-09-19 | 11279 | 549 | Running
2017-09-20 | 11661 | 382 | Work In Progress | Issue date:2017.9.20;Describe:CAN monitor cable issue;Next step:Investigation;Responser:Lin Xiaoquan
2017-09-21 | 11661 | 0 | Running Incident | Issue Describe:Cable connector burnt,TPIM isolation failed. Issue Date:2017.9.21 Resopnser:Yao Yuxing/Hong Nianzhong
2017-09-22 | 11661 | 0 | Running Incident | Issue Describe:Cable connector burnt,TPIM isolation failed. Issue Date:2017.9.21 Resopnser:Yao Yuxing/Hong Nianzhong Next step:Check transmission parts on 9/22—Li Xinlong
2017-09-23
2017-09-24
2017-09-25 | 11661 | 11661 | Running Incident | Issue Describe:High Voltage unstable Issue Date:2017.9.21. Next Step:Waiting GE response Resopnser:Yao Yuxing Next step:Check transmission carrier—Li Xinlong
2017-09-26 | 11661 | 0 | Running Incident | Issue Describe:High Voltage unstable Issue Date:2017.9.21. Next Step:Waiting GE response Resopnser:Yao Yuxing Next step:Check transmission carrier—Li Xinlong
2017-09-27 | 11661 | 0 | Running Incident | Issue Describe:High Voltage unstable Issue Date:2017.9.21. Next Step:Waiting GE response Resopnser:Yao Yuxing Next step:Check transmission carrier—Li Xinlong
2017-09-28 | 11661 | 0 | Running Incident | Issue Describe:High Voltage unstable Issue Date:2017.9.21. Next Step:Waiting GE response Resopnser:Yao Yuxing Next step:Check transmission carrier—Li Xinlong
2017-09-29 | 11661 | 0 | Running Incident | Issue Describe:High Voltage unstable Issue Date:2017.9.21. Next Step:Discuss action plan Resopnser:Yao Yuxing Next step:Retrofit transmission—Li Xinlong
2017-09-30 | 11661 | 0 | Running Incident | Issue Describe:High Voltage unstable Issue Date:2017.9.21. Next Step:Plan to debug on 10/9 Resopnser:Yao Yuxing Next step:Retrofit transmission—Li Xinlong
2017-10-01
2017-10-02
2017-10-03
2017-10-04
2017-10-05
2017-10-06
2017-10-07
2017-10-08
2017-10-09
2017-10-10
2017-10-11 | 11661 | 11661 | Running Incident | Issue Describe:Transmission damaged for high voltage unstable Next Step:Build new transmission today(2017.10.11),Spin function check on 2017.10.12 Owner:Hong Nianzhong
2017-10-12 | 11661 | 0 | Running Incident | Issue Describe:Transmission damaged for high voltage unstable Next Step:Waiting PTA result—Yao Yuxing Exchange PTA Trans(C9KFG182CQ) to PTC
2017-10-13 | 11661 | 0 | Running Incident | Issue Describe:Transmission damaged for high voltage unstable Next Step:Waiting PTA result—Yao Yuxing Exchange PTA Trans(C9KFG182CQ) to PTC
2017-10-14
2017-10-15
2017-10-16 | 11661 | 11661 | Running Incident | Issue Date:9/21 Issue Describe:Transmission damaged for high voltage unstable Next Step:Waiting PTA result—Yao Yuxing Exchange PTA Trans(C9KFG182CQ) to PTC
2017-10-17 | 11661 | 0 | Running Incident | Issue Date:9/21 Issue Describe:Transmission damaged for high voltage unstable Next Step:Waiting PTA result—Yao Yuxing Exchange PTA Trans(C9KFG182CQ) to PTC
2017-10-18 | 4691 | -6970 | Running Incident | Issue Date:9/21 Issue Describe:Transmission damaged for high voltage unstable Next Step:Discuss permanent solution tomorrow(2017.10.19)—Yao Yuxing Do function check tomorrow(2017.10.19)—Li Xinlong
2017-10-19 | 4691 | 0 | Running Incident | Issue Date:9/21 Issue Describe:High Voltage unstable Next Step:Waiting GE response Target Date:TBD Owner:Yao Yuxing Do function check tomorrow(2017.10.19)—Li Xinlong
2017-10-20 | 4691 | 0 | Running Incident | Issue Date:9/21 Issue Describe:High Voltage unstable Next Step:Try to find permanent solution Target Date:TBD Owner:Yao Yuxing Waiting do function check —Li Xinlong
2017-10-21 | 4691 | 0
2017-10-22 | 4691 | 0
2017-10-23 | 4691 | 0 | Work In Progress | Install transmission,expect to run test on 10/24
2017-10-24 | 4691 | 0 | Work In Progress | Install transmission,expect to run test on 10/25
2017-10-25 | 4691 | 0 | Work In Progress | Install transmission,expect to run test on 10/26
2017-10-26 | 4691 | 0 | Work In Progress | Issue Date:9/21 Issue Describe::High Voltage unstable Next Step:Change to permanent solution Target Date:TBD Owner:Yao Yuxing
2017-10-27 | 4691 | 0 | Running
2017-10-28 | 4691 | 0
2017-10-29 | 4691 | 0
2017-10-30 | 4691 | 0 | Work In Progress | Issue Date:10/29 Issue Describe:High voltage connector burning Next Step:Swap new high voltage cable,waiting PTA results Target Date:TBD Owner:Lin Xiaoquan/Yao Yuxing
2017-10-31 | 4691 | 0 | Work In Progress | Issue Date:10/29 Issue Describe:High voltage unstable Next Step:Waiting PTA results Target Date:TBD Owner:Yao Yuxing
2017-11-01 | 4691 | 0 | Work In Progress | Issue Date:10/29 Issue Describe:High voltage unstable Next Step:Change high voltage device Target Date:11/2 Owner:Yao Yuxing
2017-11-02 | 4707 | 16 | Running
2017-11-03 | 5126 | 419 | Running Incident | Issue Date:11/3 Issue Describe:EXH VVT DTC Code Next Step:Change CABLE Target Date:11/3 Owner:Hong Nianzhong
2017-11-04
2017-11-05
2017-11-06 | 5126 | 5126 | Running Incident | Issue Date:11/6 Issue Describe:Facility Error Target Date:TBD Owner:Yao Yuxing
2017-11-07 | 5126 | 0 | Running Incident | Issue Date:11/6 Issue Describe:Facility Error Target Date:TBD Owner:Yao Yuxing
2017-11-08
2017-11-09
2017-11-10
2017-11-11
2017-11-12
2017-11-13
2017-11-14
2017-11-15
2017-11-16
2017-11-17
2017-11-18
2017-11-19
2017-11-20
2017-11-21
2017-11-22
2017-11-23
2017-11-24
2017-11-25
2017-11-26
2017-11-27
2017-11-28
2017-11-29
2017-11-30
2017-12-01
2017-12-02
2017-12-03
2017-12-04
2017-12-05
2017-12-06
2017-12-07
2017-12-08
2017-12-09
2017-12-10
2017-12-11
2017-12-12
2017-12-13
2017-12-14
2017-12-15
2017-12-16
2017-12-17
2017-12-18
2017-12-19
2017-12-20
2017-12-21
2017-12-22
2017-12-23
2017-12-24
2017-12-25
2017-12-26
2017-12-27
2017-12-28
2017-12-29
2017-12-30
2017-12-31
2018-01-01
2018-01-02
2018-01-03
2018-01-04
2018-01-05
2018-01-06
2018-01-07
2018-01-08
2018-01-09
2018-01-10
2018-01-11
2018-01-12
2018-01-13
2018-01-14
2018-01-15
2018-01-16
2018-01-17
2018-01-18
2018-01-19
2018-01-20
2018-01-21
2018-01-22
2018-01-23
2018-01-24
2018-01-25
2018-01-26
2018-01-27
2018-01-28
2018-01-29
2018-01-30
2018-01-31
2018-02-01
2018-02-02
2018-02-03
2018-02-04
2018-02-05
2018-02-06
2018-02-07
2018-02-08
2018-02-09
2018-02-10
2018-02-11
2018-02-12
2018-02-13
2018-02-14
2018-02-15
2018-02-16
2018-02-17
2018-02-18
2018-02-19
2018-02-20
2018-02-21
2018-02-22
2018-02-23
2018-02-24
2018-02-25
2018-02-26
2018-02-27
2018-02-28
2018-03-01
2018-03-02
2018-03-03
2018-03-04
2018-03-05
2018-03-06
2018-03-07
2018-03-08
2018-03-09
2018-03-10
2018-03-11
2018-03-12
2018-03-13
2018-03-14
2018-03-15
2018-03-16
2018-03-17
2018-03-18
2018-03-19
2018-03-20
2018-03-21
2018-03-22
2018-03-23
2018-03-24
2018-03-25
2018-03-26
2018-03-27
2018-03-28
2018-03-29
2018-03-30
2018-03-31
2018-04-01
2018-04-02
2018-04-03
2018-04-04
2018-04-05
2018-04-06
2018-04-07
2018-04-08
2018-04-09
2018-04-10
2018-04-11
2018-04-12
2018-04-13
2018-04-14
2018-04-15
2018-04-16
2018-04-17
2018-04-18
2018-04-19
2018-04-20
2018-04-21
2018-04-22
2018-04-23
2018-04-24
2018-04-25
2018-04-26
2018-04-27
2018-04-28
2018-04-29
2018-04-30
2018-05-01
2018-05-02
2018-05-03
2018-05-04
2018-05-05
2018-05-06
2018-05-07
2018-05-08
2018-05-09
2018-05-10
2018-05-11
2018-05-12
2018-05-13
2018-05-14
2018-05-15
2018-05-16
2018-05-17
2018-05-18
2018-05-19
2018-05-20
2018-05-21
2018-05-22
2018-05-23
2018-05-24
2018-05-25
2018-05-26
2018-05-27
2018-05-28
2018-05-29
2018-05-30
2018-05-31
2018-06-01
2018-06-02
2018-06-03
2018-06-04
2018-06-05
2018-06-06
2018-06-07
2018-06-08
2018-06-09
2018-06-10
2018-06-11
2018-06-12
2018-06-13
2018-06-14
2018-06-15
2018-06-16
2018-06-17
2018-06-18
2018-06-19
2018-06-20
2018-06-21
2018-06-22
2018-06-23
2018-06-24
2018-06-25
2018-06-26
2018-06-27
2018-06-28
2018-06-29
2018-06-30
2018-07-01
2018-07-02
2018-07-03
2018-07-04
2018-07-05
2018-07-06
2018-07-07
2018-07-08
2018-07-09
2018-07-10
2018-07-11
2018-07-12
2018-07-13
2018-07-14
2018-07-15
2018-07-16
2018-07-17
2018-07-18
2018-07-19
2018-07-20
2018-07-21
2018-07-22
2018-07-23
2018-07-24
2018-07-25
2018-07-26
2018-07-27
2018-07-28
2018-07-29
2018-07-30
2018-07-31
2018-08-01
2018-08-02
2018-08-03 | [5 empty] | 完成
2018-08-04
2018-08-05
2018-08-06
2018-08-07
2018-08-08
2018-08-09
2018-08-10
2018-08-11
2018-08-12
2018-08-13
2018-08-14
2018-08-15
2018-08-16
2018-08-17
2018-08-18
2018-08-19
2018-08-20
2018-08-21
Maximum Cycles/Day |  | 11661
1
Average Daily Cycles Calculations
Weekends? | Ran Weekends
Working Days for Average Calculation | #N/A
Total Days Since SOT | 54
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
#N/A | #N/A | #N/A
Formulas:
Columns Active (Click to activate) = NETWORKDAYS(A1674,[Columns Active (Click to activate), row above],Holidays!$A2:A36)
Help
Search
Jump to Latest Entry Date
x
^
Fill in Today's Date
Note on A2: This document supports up to 15 transmissions at any given time. To hide extra columns, select the column of the given color that you would like to hide, right click, and select "Hide". Similarly, to bring back hidden columns, select the column immediately before and after the hidden column, right click, and select "unhide".
Note on B2: Type Engine RPO here.
Note on D2: Type Engine Number here.
Note on B3: Type Trans RPO here.
Note on D3: Type Transmission Number here.
Note on B4: Select a test cell.
Note on E4: Insert test schedule here.
Note on C5: Insert cycle goal here.
Note on E5: Insert pallet # here.
Note on C6: Type trans software here.
Note on E6: Type engine software here.
Note on C7: Enter PQMS # here.
Note on E7: Insert PON # here.
Note on D9: Type back up transmission number here.
Note on A10: Insert date here. Clicking on the cell and dragging it down to the cell below will automatically fill out the date for the next day. This does not skip weekends, however. Only add the latest date (Do not drag the date past your latest entry) or else the tracking sheet will not see your data. The tracking sheet looks at the latest date, regardless of whether or not there is information in it.
Note on B10: Insert current cycle count here.
Note on C10: Cycles per day is automatically calculated for you.
Note on D10: Select cell status from drop down box.
Note on E10: about cell condition or issues that occurred during the day here.
Note on B1671: Default is set to not include weekends in the average cycles count since 24/7 running is not usually practiced at this time. Change this if the cell commonly runs weekends or if weekend running becomes mandatory.

## B2B (hidden)
1
GFE 2nd Axis
Columns Active (Click to activate)
| Test Cell |  | Test Schedule: | B2B
| Cycle Goal: | 185 | Pallet #: | M 1
|  | Title: | 6th set
| Back up Trans: |  |  |  | Part installed |  |  |  | Part removed
| hours | hours/day | Status | Comments | PN | Name | Prior cycles | Origin | PN | Name | Cycles on part Check for history! | Reason for change
2017-06-08 |  |  |  | Waiting for GFE parts
2017-06-09 |  |  | Work In Progress | Warming up & Debugging
2017-06-10 |  |  | Work In Progress | Debugging
2017-06-11 |  |  | Work In Progress | Debugging
2017-06-12 |  |  | Work In Progress | Debugging
2017-06-13 |  |  | Work In Progress | Debugging
2017-06-14 |  |  | Work In Progress | Debugging
2017-06-15 |  |  | Work In Progress | Debugging
2017-06-16 |  |  | Work In Progress | Debugging
2017-06-17 |  |  | Work In Progress | Debugging
2017-06-18 |  |  | Work In Progress | Debugging
2017-06-19 |  |  | Work In Progress | Debugging
2017-06-20 |  |  | Work In Progress | Debugging
2017-06-21 |  |  | Work In Progress | Debugging
2017-06-22 |  |  | Work In Progress | Debugging
2017-06-23 |  |  | Work In Progress | Debugging
2017-06-24 |  |  | Work In Progress | Debugging
2017-06-25 |  |  | Work In Progress | Debugging
2017-06-26 |  |  | Work In Progress | Debugging
2017-06-27 |  |  | Waiting Ready to Run | Debugging
2017-06-28 | 2 | 2 | Running
2017-06-29 | 20.6 | 18.6 | Running
2017-06-30 | 41.2 | 20.6 | Test Terminated | P4 washer overheat broken 1st set EOT
2017-07-01
2017-07-02
2017-07-03 | 5.15 | 5.15 | Running | 1st set SOT
2017-07-04 | 5.15 | 0 | Work In Progress | 5% inspection
2017-07-05 | 5.15 | 0 | Work In Progress | 5% inspection
2017-07-06 | 5.15 | 0 | Work In Progress | 5% inspection
2017-07-07 | 5.15 | 0 | Work In Progress | 5% inspection
2017-07-08 | 5.15 | 0 | Work In Progress
2017-07-09 | 5.15 | 0 | Work In Progress
2017-07-10 | 5.15 | 0 | Running
2017-07-11 | 20.6 | 15.45 | Running
2017-07-12 | 22 | 1.4 | Running
2017-07-13 | 41.2 | 19.2 | Running
2017-07-14 | 61.8 | 20.6 | Running
2017-07-15 | 83 | 21.2 | Running
2017-07-16 | 104 | 21 | Running
2017-07-17 | 123.6 | 19.6 | Running
2017-07-18 | 144.2 | 20.6 | Running
2017-07-19 | 164.8 | 20.6 | Running
2017-07-20 | 183 | 18.2 | Running | Load side washer wear @164.8hr, replaced new.
2017-07-21 | 185.4 | 2.4 | Complete | GFE 2nd Axis 1st set completed.
2017-07-22 | 185.4 | 0 | Complete | GFE 2nd Axis 1st set completed.
2017-07-23 | 185.4 | 0 | Complete | GFE 2nd Axis 1st set completed.
2017-07-24 | 11.4 | -174 | Running | GFE 2nd Axis 1st set completed. 9T50 AWD 5P 3rd set setup and SOT.
2017-07-25 | 23 | 11.6 | Running
2017-07-26 | 46.5 | 23.5 | Running
2017-07-27 | 70.6 | 24.1 | Running
2017-07-28 | 93 | 22.4 | Running
2017-07-29 | 113 | 20 | Running
2017-07-30 | 133 | 20 | Running
2017-07-31 | 152.6 | 19.6 | Running
2017-08-01 | 174 | 21.4 | Running
2017-08-02 | 191.5 | 17.5 | Running
2017-08-03 | 207.5 | 16 | Running
2017-08-04 | 228 | 20.5 | Complete | 9T50 AWD 5P 3rd set completed.
2017-08-05
2017-08-06
2017-08-07 |  |  | Waiting Parts | Waiting T14
2017-08-08 |  |  | Waiting Parts | Waiting T14
2017-08-09 | 13 | 13 | Running | 2nd set SOT
2017-08-10 | 33 | 20 | Running
2017-08-11 | 53.2 | 20.2 | Running
2017-08-12 | 74 | 20.8 | Running
2017-08-13 | 95 | 21 | Running
2017-08-14 | 115 | 20 | Running
2017-08-15 | 136 | 21 | Running
2017-08-16 | 157 | 21 | Running
2017-08-17 | 180 | 23 | Running
2017-08-18 | 185 | 5 | Complete | Next set suspend due to ATF out of stock, plan to resume 8/22. Out of date ATF analysis in progress.
2017-08-19
2017-08-20
2017-08-21 |  |  | Work In Progress | 3rd set suspend due to ATF out of stock, plan to start today.
2017-08-22 | 11.3 | 11.3 | Running
2017-08-23 | 33.6 | 22.3 | Running
2017-08-24 | 57 | 23.4 | Running
2017-08-25 | 74.2 | 17.2 | Running
2017-08-26
2017-08-27
2017-08-28 | 134 | 134 | Running
2017-08-29 | 147 | 13
2017-08-30 | 164 | 17 | Running
2017-08-31 | 185 | 21 | Complete | Complete 3rd set.
2017-09-01 | 16 | -169 | Running
2017-09-02
2017-09-03 |  |  | Running
2017-09-04 | 60.3 | 60.3 | Running
2017-09-05
2017-09-06
2017-09-07 | 118.5 | 118.5 | Running
2017-09-08 | 138.2 | 19.7 | Running
2017-09-09 | 158 | 19.8
2017-09-10 | 180 | 22 | Complete | Complete 4th set.
2017-09-11 | 13.5 | -166.5 | Running
2017-09-12 | 37 | 23.5 | Running
2017-09-13 | 56.3 | 19.3 | Running
2017-09-14 | 76.2 | 19.9 | Running
2017-09-15 | 97.9 | 21.7 | Running
2017-09-16
2017-09-17
2017-09-18 | 160.1 | 160.1 | Running
2017-09-19 | 180.2 | 20.1 | Running
2017-09-20 | 185 | 4.8 | Complete
2017-09-21 | 9 | -176 | Running | Start 6th set
2017-09-22 | 28.9 | 19.9 | Running
2017-09-23
2017-09-24
2017-09-25 | 95.4 | 95.4 | Running
2017-09-26 | 98.8 | 3.4 | Running | Dyno maintance yesterday(2017/9/25)
2017-09-27 | 118.9 | 20.1 | Running
2017-09-28 | 140.1 | 21.2 | Running
2017-09-29 | 160.3 | 20.2 | Running
2017-09-30 | 178.2 | 17.9 | Running
2017-10-01
2017-10-02
2017-10-03
2017-10-04
2017-10-05
2017-10-06
2017-10-07
2017-10-08
2017-10-09
2017-10-10 | 185 | 185 | Complete | Complete all sets
2017-10-11
2017-10-12
2017-10-13
2017-10-14
2017-10-15
2017-10-16
2017-10-17
2017-10-18
2017-10-19
2017-10-20
2017-10-21
2017-10-22
2017-10-23
2017-10-24
2017-10-25
2017-10-26
2017-10-27
2017-10-28
2017-10-29
2017-10-30
2017-10-31
2017-11-01
2017-11-02
2017-11-03
2017-11-04
2017-11-05
2017-11-06
2017-11-07
2017-11-08
2017-11-09
2017-11-10
2017-11-11
2017-11-12
2017-11-13
2017-11-14
2017-11-15
2017-11-16
2017-11-17
2017-11-18
2017-11-19
2017-11-20
2017-11-21
2017-11-22
2017-11-23
2017-11-24
2017-11-25
2017-11-26
2017-11-27
2017-11-28
2017-11-29
2017-11-30
2017-12-01
2017-12-02
2017-12-03
2017-12-04
2017-12-05
2017-12-06
2017-12-07
2017-12-08
2017-12-09
2017-12-10
2017-12-11
2017-12-12
2017-12-13
2017-12-14
2017-12-15
2017-12-16
2017-12-17
2017-12-18
2017-12-19
2017-12-20
2017-12-21
2017-12-22
2017-12-23
2017-12-24
2017-12-25
2017-12-26
2017-12-27
2017-12-28
2017-12-29
2017-12-30
2017-12-31
2018-01-01
2018-01-02
2018-01-03
2018-01-04
2018-01-05
2018-01-06
2018-01-07
2018-01-08
2018-01-09
2018-01-10
2018-01-11
2018-01-12
2018-01-13
2018-01-14
2018-01-15
2018-01-16
2018-01-17
2018-01-18
2018-01-19
2018-01-20
2018-01-21
2018-01-22
2018-01-23
2018-01-24
2018-01-25
2018-01-26
2018-01-27
2018-01-28
2018-01-29
2018-01-30
2018-01-31
2018-02-01
2018-02-02
2018-02-03
2018-02-04
2018-02-05
2018-02-06
2018-02-07
2018-02-08
2018-02-09
2018-02-10
2018-02-11
2018-02-12
2018-02-13
2018-02-14
2018-02-15
2018-02-16
2018-02-17
2018-02-18
2018-02-19
2018-02-20
2018-02-21
2018-02-22
2018-02-23
2018-02-24
2018-02-25
2018-02-26
2018-02-27
2018-02-28
2018-03-01
2018-03-02
2018-03-03
2018-03-04
2018-03-05
2018-03-06
2018-03-07
2018-03-08
2018-03-09
2018-03-10
2018-03-11
2018-03-12
2018-03-13
2018-03-14
2018-03-15
2018-03-16
2018-03-17
2018-03-18
2018-03-19
2018-03-20
2018-03-21
2018-03-22
2018-03-23
2018-03-24
2018-03-25
2018-03-26
2018-03-27
2018-03-28
2018-03-29
2018-03-30
2018-03-31
2018-04-01
2018-04-02
2018-04-03
2018-04-04
2018-04-05
2018-04-06
2018-04-07
2018-04-08
2018-04-09
2018-04-10
2018-04-11
2018-04-12
2018-04-13
2018-04-14
2018-04-15
2018-04-16
2018-04-17
2018-04-18
2018-04-19
2018-04-20
2018-04-21
2018-04-22
2018-04-23
2018-04-24
2018-04-25
2018-04-26
2018-04-27
2018-04-28
2018-04-29
2018-04-30
2018-05-01
2018-05-02
2018-05-03
2018-05-04
2018-05-05
2018-05-06
2018-05-07
2018-05-08
2018-05-09
2018-05-10
2018-05-11
2018-05-12
2018-05-13
2018-05-14
2018-05-15
2018-05-16
2018-05-17
2018-05-18
2018-05-19
2018-05-20
2018-05-21
2018-05-22
2018-05-23
2018-05-24
2018-05-25
2018-05-26
2018-05-27
2018-05-28
2018-05-29
2018-05-30
2018-05-31
2018-06-01
2018-06-02
2018-06-03
2018-06-04
2018-06-05
2018-06-06
2018-06-07
2018-06-08
2018-06-09
2018-06-10
2018-06-11
2018-06-12
2018-06-13
2018-06-14
2018-06-15
2018-06-16
2018-06-17
2018-06-18
2018-06-19
2018-06-20
2018-06-21
2018-06-22
2018-06-23
2018-06-24
2018-06-25
2018-06-26
2018-06-27
2018-06-28
2018-06-29
2018-06-30
2018-07-01
2018-07-02
2018-07-03
2018-07-04
2018-07-05
2018-07-06
2018-07-07
2018-07-08
2018-07-09
2018-07-10
2018-07-11
2018-07-12
2018-07-13
2018-07-14
2018-07-15
2018-07-16
2018-07-17
2018-07-18
2018-07-19
2018-07-20
2018-07-21
2018-07-22
2018-07-23
2018-07-24
2018-07-25
2018-07-26
2018-07-27
2018-07-28
2018-07-29
2018-07-30
2018-07-31
2018-08-01
2018-08-02
2018-08-03
2018-08-04
2018-08-05
2018-08-06
2018-08-07
2018-08-08
2018-08-09
2018-08-10
2018-08-11
2018-08-12
2018-08-13
2018-08-14
2018-08-15
2018-08-16
2018-08-17
2018-08-18
2018-08-19
2018-08-20
2018-08-21
2018-08-22
2018-08-23
2018-08-24
2018-08-25
2018-08-26
2018-08-27
2018-08-28
2018-08-29
2018-08-30
2018-08-31
2018-09-01
2018-09-02
2018-09-03
2018-09-04
2018-09-05
2018-09-06
2018-09-07
2018-09-08
2018-09-09
2018-09-10
2018-09-11
2018-09-12
2018-09-13
2018-09-14
2018-09-15
2018-09-16
2018-09-17
2018-09-18
2018-09-19
2018-09-20
2018-09-21
2018-09-22
2018-09-23
2018-09-24
2018-09-25
2018-09-26
2018-09-27
2018-09-28
2018-09-29
2018-09-30
2018-10-01
2018-10-02
2018-10-03
2018-10-04
2018-10-05
2018-10-06
2018-10-07
2018-10-08
2018-10-09
2018-10-10
2018-10-11
2018-10-12
2018-10-13
2018-10-14
2018-10-15
2018-10-16
2018-10-17
2018-10-18
2018-10-19
2018-10-20
2018-10-21
2018-10-22
2018-10-23
2018-10-24
2018-10-25
2018-10-26
2018-10-27
2018-10-28
2018-10-29
2018-10-30
2018-10-31
2018-11-01
2018-11-02
2018-11-03
2018-11-04
2018-11-05
2018-11-06
2018-11-07
2018-11-08
2018-11-09
2018-11-10
2018-11-11
2018-11-12
2018-11-13
2018-11-14
2018-11-15
2018-11-16
2018-11-17
2018-11-18
2018-11-19
2018-11-20
2018-11-21
2018-11-22
2018-11-23
2018-11-24
2018-11-25
2018-11-26
2018-11-27
2018-11-28
2018-11-29
2018-11-30
2018-12-01
2018-12-02
2018-12-03
2018-12-04
2018-12-05
2018-12-06
2018-12-07
2018-12-08
2018-12-09
2018-12-10
2018-12-11
2018-12-12
2018-12-13
2018-12-14
2018-12-15
2018-12-16
2018-12-17
2018-12-18
2018-12-19
2018-12-20
2018-12-21
2018-12-22
2018-12-23
2018-12-24
2018-12-25
2018-12-26
2018-12-27
2018-12-28
2018-12-29
2018-12-30
2018-12-31
2019-01-01
2019-01-02
2019-01-03
2019-01-04
2019-01-05
2019-01-06
2019-01-07
2019-01-08
2019-01-09
2019-01-10
2019-01-11
2019-01-12
2019-01-13
2019-01-14
2019-01-15
2019-01-16
2019-01-17
2019-01-18
2019-01-19
2019-01-20
2019-01-21
2019-01-22
2019-01-23
2019-01-24
2019-01-25
2019-01-26
2019-01-27
2019-01-28
2019-01-29
2019-01-30
2019-01-31
2019-02-01
2019-02-02
2019-02-03
2019-02-04
2019-02-05
2019-02-06
2019-02-07
2019-02-08
2019-02-09
2019-02-10
2019-02-11
2019-02-12
2019-02-13
2019-02-14
2019-02-15
2019-02-16
2019-02-17
2019-02-18
2019-02-19
2019-02-20
2019-02-21
2019-02-22
2019-02-23
2019-02-24
2019-02-25
2019-02-26
2019-02-27
2019-02-28
2019-03-01
2019-03-02
2019-03-03
2019-03-04
2019-03-05
2019-03-06
2019-03-07
2019-03-08
2019-03-09
2019-03-10
2019-03-11
2019-03-12
2019-03-13
2019-03-14
2019-03-15
2019-03-16
Maximum Cycles/Day
Average Daily Cycles Calculations
Weekends? | Ran Weekends
Working Days for Average Calculation | #REF!
Total Days Since SOT | 77
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
Note on A2: This document supports up to 15 transmissions at any given time. To hide extra columns, select the column of the given color that you would like to hide, right click, and select "Hide". Similarly, to bring back hidden columns, select the column immediately before and after the hidden column, right click, and select "unhide".
Note on B2: Type Engine RPO here.
Note on D2: Type Engine Number here.
Note on B3: Type Trans RPO here.
Note on D3: Type Transmission Number here.
Note on B4: Select a test cell.
Note on E4: Insert test schedule here.
Note on C5: Insert cycle goal here.
Note on E5: Insert pallet # here.
Note on D7: Type back up transmission number here.
Note on A8: Insert date here. Clicking on the cell and dragging it down to the cell below will automatically fill out the date for the next day. This does not skip weekends, however. Only add the latest date (Do not drag the date past your latest entry) or else the tracking sheet will not see your data. The tracking sheet looks at the latest date, regardless of whether or not there is information in it.
Note on B8: Insert current cycle count here.
Note on C8: Cycles per day is automatically calculated for you.
Note on D8: Select cell status from drop down box.
Note on E8: about cell condition or issues that occurred during the day here.
Note on B848: Default is set to not include weekends in the average cycles count since 24/7 running is not usually practiced at this time. Change this if the cell commonly runs weekends or if weekend running becomes mandatory.

## GRC (hidden)
1
| L2B |  | L2B*161333733*
Columns Active (Click to activate) | MKF |  | T9EPG612CQ
| Test Cell |  | Test Schedule: | TEDD
| Cycle Goal: | 24000 | Pallet #: | GRC
| Trans Software: | S55TH_171712011_04Apr2017_TEDD_2 S55M1_171712011_04Apr2017_TEDD_2 S55M2_171712011_04Apr2017_TEDD_2 | Engine Software: | AA0202B516_toPATAC_FlashedMuleCar_Dynoized_3_9_2019
| PQMS# |  | PON#
|  | Title: | GFE Gamma TEDD Validation (K226 Local Content)
| Back up Trans: |  |  |  | Part installed |  |  |  | Part removed
| Cycles | Cycles/day | Status | Comments | PN | Name | Prior cycles | Origin | PN | Name | Cycles on part Check for history! | Reason for change
2017-07-18
2017-07-19
2017-07-20
2017-07-21
2017-07-22
2017-07-23
2017-07-24
2017-07-25
2017-07-26
2017-07-27
2017-07-28
2017-07-29
2017-07-30
2017-07-31
2017-08-01
2017-08-02 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-08-03 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-08-04 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-08-05 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-08-06 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-08-07 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-08-08 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-08-09 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-08-10 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-08-11 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-08-12
2017-08-13
2017-08-14 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-08-15 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-08-16 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-08-17 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-08-18 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-08-19
2017-08-20
2017-08-21 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-08-22 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-08-23 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-08-24 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-08-25 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-08-26
2017-08-27
2017-08-28 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-08-29 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-08-30 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-08-31 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-09-01 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-09-02
2017-09-03
2017-09-04 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-09-05 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-09-06 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-09-07 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-09-08 | 0 | 0 | Running | Change to new gamma1 transmission due to Motor B touble,try to run today
2017-09-09
2017-09-10
2017-09-11 | 0 | 0 | Running | Dyno setup with gamma1 transmission for debugging,checking data Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-09-12 | 0 | 0 | Running | Dyno setup with gamma1 transmission for debugging,checking data Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-09-13 | 0 | 0 | Running | Dyno setup with gamma1 transmission for debugging,checking data Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-09-14 | 0 | 0 | Running | Dyno setup with gamma1 transmission for debugging,TVE support onsite. Gamma2 transmission: Waiting EWO parts until 9/28.
2017-09-15 | 1400 | 0 | Running | Dyno setup with gamma1 transmission ,brief TEDD,TVE support onsite. Gamma2 transmission: Waiting EWO parts until 9/28.
2017-09-16
2017-09-17
2017-09-18 | 2100 | 0 | Running | Dyno setup with gamma1 transmission ,brief TEDD Gamma2 transmission: Waiting EWO parts until 9/28.
2017-09-19 | 2126 |  | Running | Dyno setup with gamma1 transmission ,brief TEDD Gamma2 transmission: Waiting EWO parts until 9/28. | 昨晚7点，CAN线反馈的油门信息未跟随油门输入量，报警停机
2017-09-20 |  |  | Waiting Parts | Gamma2 transmission: Waiting EWO parts until10/15.
2017-09-21 |  |  | Waiting Parts | Gamma2 transmission: Waiting EWO parts until10/15.
2017-09-22 |  |  | Waiting Parts | Gamma2 transmission: Waiting EWO parts until10/15.
2017-09-23
2017-09-24
2017-09-25 |  |  | Waiting Parts | Gamma2 transmission: Waiting EWO parts until10/15.
2017-09-26 |  |  | Waiting Parts | Gamma2 transmission: Waiting EWO parts until10/15.
2017-09-27 |  |  | Waiting Parts | Gamma2 transmission: Waiting EWO parts until10/15.
2017-09-28 |  |  | Waiting Parts | Gamma2 transmission: Waiting EWO parts until10/15.
2017-09-29 |  |  | Waiting Parts | Gamma2 transmission: Waiting EWO parts until10/15.
2017-09-30 |  |  | Waiting Parts | Gamma2 transmission: Waiting EWO parts until10/15.
2017-10-01 |  |  | Waiting Parts | Gamma2 transmission: Waiting EWO parts until10/15.
2017-10-02 |  |  | Waiting Parts | Gamma2 transmission: Waiting EWO parts until10/15.
2017-10-03 |  |  | Waiting Parts | Gamma2 transmission: Waiting EWO parts until10/15.
2017-10-04 |  |  | Waiting Parts | Gamma2 transmission: Waiting EWO parts until10/15.
2017-10-05 |  |  | Waiting Parts | Gamma2 transmission: Waiting EWO parts until10/15.
2017-10-06 |  |  | Waiting Parts | Gamma2 transmission: Waiting EWO parts until10/15.
2017-10-07 |  |  | Waiting Parts | Gamma2 transmission: Waiting EWO parts until10/15.
2017-10-08
2017-10-09
2017-10-10
2017-10-11 |  |  | Waiting Parts | Gamma2 transmission: Waiting EWO parts until10/15.
2017-10-12 |  |  | Waiting Parts | Gamma2 transmission: Waiting EWO parts until10/15.
2017-10-13 |  |  | Waiting Parts | Gamma2 transmission: Waiting EWO parts until10/15.
2017-10-14 |  |  | Waiting Parts | Gamma2 transmission: Waiting EWO parts until10/15.
2017-10-15 |  |  | Waiting Parts | Gamma2 transmission: Waiting EWO parts until10/15.
2017-10-16 |  |  | Waiting Parts | Action:Do function check,plan to install transmission on 10/20. Owner:Hong Nianzhong
2017-10-17 |  |  | Waiting Parts | Action:Do function check,plan to install transmission on 10/20. Owner:Hong Nianzhong
2017-10-18 |  |  | Waiting Parts | Action:Do function check,plan to install transmission on 10/20. Owner:Hong Nianzhong
2017-10-19 |  |  | Waiting Parts | Action:Do function check,plan to install transmission on 10/20. Owner:Hong Nianzhong
2017-10-20 |  |  | Work In Progress | Deliver materials,plan to install palley on 10/23.
2017-10-21
2017-10-22
2017-10-23 |  |  | Work In Progress | Install palley on 10/23,expect to run test on 10/30
2017-10-24 |  |  | Work In Progress | Install palley on 10/23,expect to run test on 10/30
2017-10-25 |  |  | Work In Progress | Install palley on 10/23,expect to run test on 10/30
2017-10-26 |  |  | Work In Progress | Install palley on 10/23,expect to run test on 10/30
2017-10-27 |  |  | Work In Progress | Install palley on 10/23,expect to run test on 10/30
2017-10-28 |  |  | Work In Progress | Install palley on 10/23,expect to run test on 10/30
2017-10-29 |  |  | Work In Progress | Install palley on 10/23,expect to run test on 10/30
2017-10-30 |  |  | Work In Progress | Install palley on 10/23,expect to run test on 11/10
2017-10-31 |  |  | Work In Progress | Install palley on 10/23,expect to run test on 11/10 | 台架被人占了……
2017-11-01 |  |  | Work In Progress | Install palley on 10/23,expect to run test on 11/15
2017-11-02 |  |  | Work In Progress | Install palley on 10/23,expect to run test on 11/15
2017-11-03 |  |  | Work In Progress | Install palley on 10/23,expect to run test on 11/15
2017-11-04 |  |  | Work In Progress | Install palley on 10/23,expect to run test on 11/15
2017-11-05 |  |  | Work In Progress | Install palley on 10/23,expect to run test on 11/15
2017-11-06 |  |  | Work In Progress | Debugging ,expect to run test on 11/15
2017-11-07 |  |  | Work In Progress | Debugging ,expect to run test on 11/15
2017-11-08 |  |  | Work In Progress | Debugging ,expect to run test on 11/15
2017-11-09 |  |  | Work In Progress | Debugging ,expect to run test on 11/15
2017-11-10 |  |  | Work In Progress | Debugging ,expect to run test on 11/15
2017-11-11 |  |  | Work In Progress | Debugging ,expect to run test on 11/15
2017-11-12 |  |  | Work In Progress | Debugging ,expect to run test on 11/15
2017-11-13 |  |  | Work In Progress | Debugging ,expect to run test on 11/15
2017-11-14 |  |  | Work In Progress | Debugging ,expect to run test on 11/15
2017-11-15 |  |  | Work In Progress | Debugging ,expect to run test on 11/15
2017-11-16
2017-11-17
2017-11-18
2017-11-19
2017-11-20
2017-11-21
2017-11-22
2017-11-23
2017-11-24
2017-11-25
2017-11-26
2017-11-27
2017-11-28
2017-11-29
2017-11-30
2017-12-01
2017-12-02
2017-12-03
2017-12-04
2017-12-05
2017-12-06
2017-12-07
2017-12-08
2017-12-09
2017-12-10
2017-12-11
2017-12-12
2017-12-13
2017-12-14
2017-12-15
2017-12-16
2017-12-17
2017-12-18
2017-12-19
2017-12-20
2017-12-21
2017-12-22
2017-12-23
2017-12-24
2017-12-25
2017-12-26
2017-12-27
2017-12-28
2017-12-29
2017-12-30
2017-12-31
2018-01-01
2018-01-02
2018-01-03
2018-01-04
2018-01-05
2018-01-06
2018-01-07
2018-01-08
2018-01-09
2018-01-10
2018-01-11
2018-01-12
2018-01-13
2018-01-14
2018-01-15
2018-01-16
2018-01-17
2018-01-18
2018-01-19
2018-01-20
2018-01-21
2018-01-22
2018-01-23
2018-01-24
2018-01-25
2018-01-26
2018-01-27
2018-01-28
2018-01-29
2018-01-30
2018-01-31
2018-02-01
2018-02-02
2018-02-03
2018-02-04
2018-02-05
2018-02-06
2018-02-07
2018-02-08
2018-02-09
2018-02-10
2018-02-11
2018-02-12
2018-02-13
2018-02-14
2018-02-15
2018-02-16
2018-02-17
2018-02-18
2018-02-19
2018-02-20
2018-02-21
2018-02-22
2018-02-23
2018-02-24
2018-02-25
2018-02-26
2018-02-27
2018-02-28
2018-03-01
2018-03-02
2018-03-03
2018-03-04
2018-03-05
2018-03-06
2018-03-07
2018-03-08
2018-03-09
2018-03-10
2018-03-11
2018-03-12
2018-03-13
2018-03-14
2018-03-15
2018-03-16
2018-03-17
2018-03-18
2018-03-19
2018-03-20
2018-03-21
2018-03-22
2018-03-23
2018-03-24
2018-03-25
2018-03-26
2018-03-27
2018-03-28
2018-03-29
2018-03-30
2018-03-31
2018-04-01
2018-04-02
2018-04-03
2018-04-04
2018-04-05
2018-04-06
2018-04-07
2018-04-08
2018-04-09
2018-04-10
2018-04-11
2018-04-12
2018-04-13
2018-04-14
2018-04-15
2018-04-16
2018-04-17
2018-04-18
2018-04-19
2018-04-20
2018-04-21
2018-04-22
2018-04-23
2018-04-24
2018-04-25
2018-04-26
2018-04-27
2018-04-28
2018-04-29
2018-04-30
2018-05-01
2018-05-02
2018-05-03
2018-05-04
2018-05-05
2018-05-06
2018-05-07
2018-05-08
2018-05-09
2018-05-10
2018-05-11
2018-05-12
2018-05-13
2018-05-14
2018-05-15
2018-05-16
2018-05-17
2018-05-18
2018-05-19
2018-05-20
2018-05-21
2018-05-22
2018-05-23
2018-05-24
2018-05-25
2018-05-26
2018-05-27
2018-05-28
2018-05-29
2018-05-30
2018-05-31
2018-06-01
2018-06-02
2018-06-03
2018-06-04
2018-06-05
2018-06-06
2018-06-07
2018-06-08
2018-06-09
2018-06-10
2018-06-11
2018-06-12
2018-06-13
2018-06-14
2018-06-15
2018-06-16
2018-06-17
2018-06-18
2018-06-19
2018-06-20
2018-06-21
2018-06-22
2018-06-23
2018-06-24
2018-06-25
2018-06-26
2018-06-27
2018-06-28
2018-06-29
2018-06-30
2018-07-01
2018-07-02
2018-07-03
2018-07-04
2018-07-05
2018-07-06
2018-07-07
2018-07-08
2018-07-09
2018-07-10
2018-07-11
2018-07-12
2018-07-13
2018-07-14
2018-07-15
2015-11-03
2015-11-04
2018-04-17
Maximum Cycles/Day |  | 0
1
Average Daily Cycles Calculations
Weekends? | Ran Weekends
Working Days for Average Calculation | #REF!
Total Days Since SOT | 3
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
Formulas:
Columns Active (Click to activate) = NETWORKDAYS(A980,[Columns Active (Click to activate), row above],Holidays!$A2:A36)
Note on A2: This document supports up to 15 transmissions at any given time. To hide extra columns, select the column of the given color that you would like to hide, right click, and select "Hide". Similarly, to bring back hidden columns, select the column immediately before and after the hidden column, right click, and select "unhide".
Note on B2: Type Engine RPO here.
Note on D2: Type Engine Number here.
Note on B3: Type Trans RPO here.
Note on D3: Type Transmission Number here.
Note on B4: Select a test cell.
Note on E4: Insert test schedule here.
Note on C5: Insert cycle goal here.
Note on E5: Insert pallet # here.
Note on C6: Type trans software here.
Note on E6: Type engine software here.
Note on C7: Enter PQMS # here.
Note on E7: Insert PON # here.
Note on D9: Type back up transmission number here.
Note on A10: Insert date here. Clicking on the cell and dragging it down to the cell below will automatically fill out the date for the next day. This does not skip weekends, however. Only add the latest date (Do not drag the date past your latest entry) or else the tracking sheet will not see your data. The tracking sheet looks at the latest date, regardless of whether or not there is information in it.
Note on B10: Insert current cycle count here.
Note on C10: Cycles per day is automatically calculated for you.
Note on D10: Select cell status from drop down box.
Note on E10: about cell condition or issues that occurred during the day here.
Note on B977: Default is set to not include weekends in the average cycles count since 24/7 running is not usually practiced at this time. Change this if the cell commonly runs weekends or if weekend running becomes mandatory.

## Horiba (hidden)
1
| L2B |  | L2B*161333732*
Columns Active (Click to activate) | MKF |  | C9KFG005CQ
| Test Cell |  | Test Schedule: | TEDD
| Cycle Goal: | 24000 | Pallet #: | Horiba
| Trans Software: | S55TH_171712011_04Apr2017_TEDD_2 S55M1_171712011_04Apr2017_TEDD_2 S55M2_171712011_04Apr2017_TEDD_2 | Engine Software: | AA0202B516_toPATAC_FlashedMuleCar_Dynoized_3_9_2019
| PQMS# |  | PON#
|  | Title: | GFE Gamma TEDD Validation (K226 Local Content)
| Back up Trans: |  |  |  | Part installed |  |  |  | Part removed
| Cycles | Cycles/day | Status | Comments | PN | Name | Prior cycles | Origin | PN | Name | Cycles on part Check for history! | Reason for change
2017-07-18
2017-07-19
2017-07-20
2017-07-21
2017-07-22
2017-07-23
2017-07-24
2017-07-25
2017-07-26
2017-07-27
2017-07-28
2017-07-29
2017-07-30
2017-07-31
2017-08-01 | 0 | 0 | Pending | Horiba facility issue,waiting for new parts,plan to debug at 8/11
2017-08-02 | 0 | 0 | Pending | Horiba facility issue,waiting for new parts,plan to debug at 8/11
2017-08-03 | 0 | 0 | Pending | Horiba facility issue,waiting for new parts,plan to debug at 8/11
2017-08-04 | 0 | 0 | Pending | Horiba facility issue,waiting for new parts,plan to debug at 8/11
2017-08-05 | 0 | 0 | Pending | Horiba facility issue,waiting for new parts,plan to debug at 8/11
2017-08-06 | 0 | 0 | Pending | Horiba facility issue,waiting for new parts,plan to debug at 8/11
2017-08-07 | 0 | 0 | Pending | Horiba facility issue,waiting for new parts,plan to debug at 8/11
2017-08-08 | 0 | 0 | Pending | Horiba facility issue,waiting for new parts,plan to debug at 8/11
2017-08-09 | 0 | 0 | Pending | Horiba facility issue,waiting for new parts,plan to debug at 8/15
2017-08-10 | 0 | 0 | Pending | Horiba facility issue,waiting for new parts,plan to debug at 8/15
2017-08-11 | 0 | 0 | Pending | Horiba facility issue,waiting for new parts,plan to debug at 8/15
2017-08-12
2017-08-13
2017-08-14 | 0 | 0 | Pending | Horiba facility issue,waiting for new parts,plan to debug at 8/18
2017-08-15 | 0 | 0 | Pending | Horiba facility issue,new parts in customs clearance,plan to debug at 8/18
2017-08-16 | 0 | 0 | Pending | Horiba facility issue,waiting for new parts,plan to debug at 8/18
2017-08-17 | 0 | 0 | Pending | Horiba facility issue,waiting for new parts,plan to debug at 8/18
2017-08-18 | 0 | 0 | Pending | Horiba facility issue,waiting for new parts,plan to debug at 8/21
2017-08-19
2017-08-20
2017-08-21 | 0 | 0 | Pending | Horiba check facility issue
2017-08-22 | 0 | 0 | Pending | Horiba check facility issue
2017-08-23 | 0 | 0 | Pending | Horiba check facility and software issue,plan to debugging on site till 8/31
2017-08-24 | 0 | 0 | Pending | Horiba check facility and software issue,plan to debugging on site till 8/31
2017-08-25 | 0 | 0 | Pending | Horiba check facility and software issue,plan to debugging on site till 8/31
2017-08-26
2017-08-27
2017-08-28 | 0 | 0 | Pending | Horiba check facility and software issue,plan to debugging on site till 8/31
2017-08-29 | 0 | 0 | Pending | Horiba check facility and software issue,plan to debugging on site till 8/31
2017-08-30 | 0 | 0 | Pending | Horiba check facility and software issue,plan to debugging on site till 8/31
2017-08-31 | 0 | 0 | Pending | Horiba check facility and software issue,plan to debugging on site till 8/31
2017-09-01 | 0 | 0 | Pending | Plan to debugging on site on 9/2.
2017-09-02
2017-09-03
2017-09-04 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-09-05 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-09-06 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-09-07 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-09-08 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-09-09
2017-09-10
2017-09-11 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-09-12 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-09-13 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until mid of Sep.
2017-09-14 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until 9/28.
2017-09-15 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until 9/28.
2017-09-16 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until 9/28.
2017-09-17
2017-09-18 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until 9/28.
2017-09-19 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until 9/28.
2017-09-20 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until 10/15.
2017-09-21 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until 10/15.
2017-09-22 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until 10/15.
2017-09-23
2017-09-24
2017-09-25 | 0 | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until 10/15.
2017-09-26 |  | 0 | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until 10/15.
2017-09-27 |  |  | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until 10/15.
2017-09-28 |  |  | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until 10/15.
2017-09-29 |  |  | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until 10/15.
2017-09-30 |  |  | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until 10/15.
2017-10-01 |  |  | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until 10/15.
2017-10-02 |  |  | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until 10/15.
2017-10-03 |  |  | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until 10/15.
2017-10-04 |  |  | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until 10/15.
2017-10-05 |  |  | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until 10/15.
2017-10-06 |  |  | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until 10/15.
2017-10-07
2017-10-08
2017-10-09
2017-10-10 |  |  | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until 10/15.
2017-10-11 |  |  | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until 10/15.
2017-10-12 |  |  | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until 10/15.
2017-10-13 |  |  | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until 10/15.
2017-10-14 |  |  | Pending | Dyno setup with gamma1 transmission for debugging Gamma2 transmission: Waiting EWO parts until 10/15.
2017-10-15
2017-10-16 |  |  | Pending | Dyno setup with gamma1 transmission for debugging Issue Date:9/21. Issue Describe:High Voltage unstable Next Step:Waiting PTA result and supplier check on site 10.17. Owner:Wu Chengwen
2017-10-17 |  |  | Pending | Dyno setup with gamma1 transmission for debugging Issue Date:9/21. Issue Describe:High Voltage unstable Next Step:Waiting supplier check on 10/18. Owner:Xu Guoqiang/Wu Chengwen
2017-10-18 |  |  | Pending | Dyno setup with gamma1 transmission for debugging Issue Date:9/21. Issue Describe:High Voltage unstable Next Step:Waiting supplier check on 10/19. Owner:Xu Guoqiang/Wu Chengwen
2017-10-19 |  |  | Pending | Dyno setup with gamma1 transmission for debugging Issue Date:9/21. Issue Describe:High Voltage unstable Next Step::Waiting GE response Target Date:TBD Owner:Xu Guoqiang/Wu Chengwen
2017-10-20 |  |  | Pending | Dyno setup with gamma1 transmission for debugging Issue Date:9/21. Issue Describe:High Voltage unstable Next Step:Solving issue,try to find permanent solution Target Date:TBD Owner:Xu Guoqiang
2017-10-21 |  |  |  | Dyno setup with gamma1 transmission for debugging Issue Date:9/21. Issue Describe:High Voltage unstable Next Step:Solving issue,try to find permanent solution Target Date:TBD Owner:Xu Guoqiang
2017-10-22 |  |  |  | Dyno setup with gamma1 transmission for debugging Issue Date:9/21. Issue Describe:High Voltage unstable Next Step:Solving issue,try to find permanent solution Target Date:TBD Owner:Xu Guoqiang
2017-10-23 |  |  |  | Dyno setup with gamma1 transmission for debugging Issue Date:9/21. Issue Describe:High Voltage unstable Next Step:Solving issue,try to find permanent solution Target Date:TBD Owner:Xu Guoqiang
2017-10-24 |  |  |  | Dyno setup with gamma1 transmission for debugging Issue Date:9/21. Issue Describe:High Voltage unstable Next Step:Solving issue,try to find permanent solution Target Date:TBD Owner:Xu Guoqiang
2017-10-25 |  |  |  | Debugging Target Date:TBD Owner:Wu Chenwen
2017-10-26 |  |  |  | Debugging Target Date:11/2 Owner:Wu Chenwen
2017-10-27 |  |  |  | Debugging Target Date:11/2 Owner:Wu Chenwen
2017-10-28
2017-10-29
2017-10-30 |  |  |  | Debugging Target Date:11/2 Owner:Wu Chenwen
2017-10-31 |  |  |  | Debugging Target Date:11/2 Owner:Wu Chenwen
2017-11-01 |  |  |  | Debugging Target Date:11/2 Owner:Wu Chenwen
2017-11-02 |  |  |  | Debugging Target Date:11/10 Owner:Wu Chenwen
2017-11-03 |  |  |  | Debugging Target Date:11/10 Owner:Wu Chenwen
2017-11-04 |  |  |  | Debugging Target Date:11/10 Owner:Wu Chenwen
2017-11-05 |  |  |  | Debugging Target Date:11/10 Owner:Wu Chenwen
2017-11-06 |  |  |  | Debugging Target Date:11/10 Owner:Wu Chenwen
2017-11-07 |  |  |  | Debugging Target Date:11/10 Owner:Wu Chenwen
2017-11-08 |  |  |  | Debugging Target Date:11/10 Owner:Wu Chenwen
2017-11-09 |  |  |  | Debugging Target Date:11/10 Owner:Wu Chenwen
2017-11-10 |  |  |  | Debugging Target Date:11/10 Owner:Wu Chenwen
2017-11-11
2017-11-12
2017-11-13
2017-11-14
2017-11-15
2017-11-16
2017-11-17
2017-11-18
2017-11-19
2017-11-20
2017-11-21
2017-11-22
2017-11-23
2017-11-24
2017-11-25
2017-11-26
2017-11-27
2017-11-28
2017-11-29
2017-11-30
2017-12-01
2017-12-02
2017-12-03
2017-12-04
2017-12-05
2017-12-06
2017-12-07
2017-12-08
2017-12-09
2017-12-10
2017-12-11
2017-12-12
2017-12-13
2017-12-14
2017-12-15
2017-12-16
2017-12-17
2017-12-18
2017-12-19
2017-12-20
2017-12-21
2017-12-22
2017-12-23
2017-12-24
2017-12-25
2017-12-26
2017-12-27
2017-12-28
2017-12-29
2017-12-30
2017-12-31
2018-01-01
2018-01-02
2018-01-03
2018-01-04
2018-01-05
2018-01-06
2018-01-07
2018-01-08
2018-01-09
2018-01-10
2018-01-11
2018-01-12
2018-01-13
2018-01-14
2018-01-15
2018-01-16
2018-01-17
2018-01-18
2018-01-19
2018-01-20
2018-01-21
2018-01-22
2018-01-23
2018-01-24
2018-01-25
2018-01-26
2018-01-27
2018-01-28
2018-01-29
2018-01-30
2018-01-31
2018-02-01
2018-02-02
2018-02-03
2018-02-04
2018-02-05
2018-02-06
2018-02-07
2018-02-08
2018-02-09
2018-02-10
2018-02-11
2018-02-12
2018-02-13
2018-02-14
2018-02-15
2018-02-16
2018-02-17
2018-02-18
2018-02-19
2018-02-20
2018-02-21
2018-02-22
2018-02-23
2018-02-24
2018-02-25
2018-02-26
2018-02-27
2018-02-28
2018-03-01
2018-03-02
2018-03-03
2018-03-04
2018-03-05
2018-03-06
2018-03-07
2018-03-08
2018-03-09
2018-03-10
2018-03-11
2018-03-12
2018-03-13
2018-03-14
2018-03-15
2018-03-16
2018-03-17
2018-03-18
2018-03-19
2018-03-20
2018-03-21
2018-03-22
2018-03-23
2018-03-24
2018-03-25
2018-03-26
2018-03-27
2018-03-28
2018-03-29
2018-03-30
2018-03-31
2018-04-01
2018-04-02
2018-04-03
2018-04-04
2018-04-05
2018-04-06
2018-04-07
2018-04-08
2018-04-09
2018-04-10
2018-04-11
2018-04-12
2018-04-13
2018-04-14
2018-04-15
2018-04-16
2018-04-17
2018-04-18
2018-04-19
2018-04-20
2018-04-21
2018-04-22
2018-04-23
2018-04-24
2018-04-25
2018-04-26
2018-04-27
2018-04-28
2018-04-29
2018-04-30
2018-05-01
2018-05-02
2018-05-03
2018-05-04
2018-05-05
2018-05-06
2018-05-07
2018-05-08
2018-05-09
2018-05-10
2018-05-11
2018-05-12
2018-05-13
2018-05-14
2018-05-15
2018-05-16
2018-05-17
2018-05-18
2018-05-19
2018-05-20
2018-05-21
2018-05-22
2018-05-23
2018-05-24
2018-05-25
2018-05-26
2018-05-27
2018-05-28
2018-05-29
2018-05-30
2018-05-31
2018-06-01
2018-06-02
2018-06-03
2018-06-04
2018-06-05
2018-06-06
2018-06-07
2018-06-08
2018-06-09
2018-06-10
2018-06-11
2018-06-12
2018-06-13
2018-06-14
2018-06-15
2018-06-16
2018-06-17
2018-06-18
2018-06-19
2018-06-20
2018-06-21
2018-06-22
2018-06-23
2018-06-24
2018-06-25
2018-06-26
2018-06-27
2018-06-28
2018-06-29
2018-06-30
2018-07-01
2018-07-02
2018-07-03
2018-07-04
2018-07-05
2018-07-06
2018-07-07
2018-07-08
2018-07-09
2018-07-10
2018-07-11
2018-07-12
2018-07-13
2018-07-14
2018-07-15
2018-07-16
2018-07-17
2018-07-18
2018-07-19
2018-07-20
2018-07-21
2018-07-22
2018-07-23
2018-07-24
2018-07-25
2018-07-26
2018-07-27
2018-07-28
2018-07-29
2018-07-30
2018-07-31
2018-08-01
2018-08-02
2018-08-03
2018-08-04
2018-08-05
2018-08-06
2018-08-07
2018-08-08
2018-08-09
2018-08-10
2018-08-11
2018-08-12
2018-08-13
2018-08-14
2018-08-15
2018-08-16
2018-08-17
2018-08-18
2018-08-19
2018-08-20
2018-08-21
2018-08-22
2018-08-23
2018-08-24
2018-08-25
2018-08-26
2018-08-27
2018-08-28
2018-08-29
2018-08-30
2018-08-31
2018-09-01
2018-09-02
2018-09-03
2018-09-04
2018-09-05
2018-09-06
2018-09-07
2018-09-08
2018-09-09
2018-09-10
2018-09-11
2018-09-12
2018-09-13
2018-09-14
2018-09-15
2018-09-16
2018-09-17
2018-09-18
2018-09-19
2018-09-20
2018-09-21
2018-09-22
2018-09-23
2018-09-24
2018-09-25
2018-09-26
2018-09-27
2018-09-28
2018-09-29
2018-09-30
2018-10-01
2018-10-02
2018-10-03
2018-10-04
2018-10-05
2018-10-06
2018-10-07
2018-10-08
2018-10-09
2018-10-10
2018-10-11
2018-10-12
2018-10-13
2018-10-14
2018-10-15
2018-10-16
2018-10-17
2018-10-18
2018-10-19
2018-10-20
2018-10-21
2018-10-22
2018-10-23
2018-10-24
2018-10-25
2018-10-26
2018-10-27
2018-10-28
2018-10-29
2018-10-30
2018-10-31
2018-11-01
2018-11-02
2018-11-03
2018-11-04
2018-11-05
2018-11-06
2018-11-07
2018-11-08
2018-11-09
2018-11-10
2018-11-11
2018-11-12
2018-11-13
2018-11-14
2018-11-15
2018-11-16
2018-11-17
2018-11-18
2018-11-19
2018-11-20
2018-11-21
2018-11-22
2018-11-23
2018-11-24
2018-11-25
2018-11-26
2018-11-27
2018-11-28
2018-11-29
2018-11-30
2018-12-01
2018-12-02
2018-12-03
2018-12-04
2018-12-05
2018-12-06
2018-12-07
2018-12-08
2018-12-09
2018-12-10
2018-12-11
2018-12-12
2018-12-13
2018-12-14
2018-12-15
2018-12-16
2018-12-17
2018-12-18
2018-12-19
2018-12-20
2018-12-21
2018-12-22
2018-12-23
2018-12-24
2018-12-25
2018-12-26
2018-12-27
2018-12-28
2018-12-29
2018-12-30
2018-12-31
2019-01-01
2019-01-02
2019-01-03
2019-01-04
2019-01-05
2019-01-06
2019-01-07
2019-01-08
2019-01-09
2019-01-10
2019-01-11
2019-01-12
2019-01-13
2019-01-14
2019-01-15
2019-01-16
2019-01-17
2019-01-18
2019-01-19
2019-01-20
2019-01-21
2019-01-22
2019-01-23
2019-01-24
2019-01-25
2019-01-26
2019-01-27
2019-01-28
2019-01-29
2019-01-30
2019-01-31
2019-02-01
2019-02-02
2019-02-03
2019-02-04
2019-02-05
Maximum Cycles/Day |  | 0
1
Average Daily Cycles Calculations
Weekends? | Ran Weekends
Working Days for Average Calculation | #REF!
Total Days Since SOT | 0
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
Formulas:
Columns Active (Click to activate) = NETWORKDAYS(A1376,[Columns Active (Click to activate), row above],Holidays!$A2:A36)
Note on A2: This document supports up to 15 transmissions at any given time. To hide extra columns, select the column of the given color that you would like to hide, right click, and select "Hide". Similarly, to bring back hidden columns, select the column immediately before and after the hidden column, right click, and select "unhide".
Note on B2: Type Engine RPO here.
Note on D2: Type Engine Number here.
Note on B3: Type Trans RPO here.
Note on D3: Type Transmission Number here.
Note on B4: Select a test cell.
Note on E4: Insert test schedule here.
Note on C5: Insert cycle goal here.
Note on E5: Insert pallet # here.
Note on C6: Type trans software here.
Note on E6: Type engine software here.
Note on C7: Enter PQMS # here.
Note on E7: Insert PON # here.
Note on D9: Type back up transmission number here.
Note on A10: Insert date here. Clicking on the cell and dragging it down to the cell below will automatically fill out the date for the next day. This does not skip weekends, however. Only add the latest date (Do not drag the date past your latest entry) or else the tracking sheet will not see your data. The tracking sheet looks at the latest date, regardless of whether or not there is information in it.
Note on B10: Insert current cycle count here.
Note on C10: Cycles per day is automatically calculated for you.
Note on D10: Select cell status from drop down box.
Note on E10: about cell condition or issues that occurred during the day here.
Note on B1373: Default is set to not include weekends in the average cycles count since 24/7 running is not usually practiced at this time. Change this if the cell commonly runs weekends or if weekend running becomes mandatory.

## Retrofit Log (hidden)
168# | [5 empty] | 113# |  |  |  |  | 182#
Date | Cycle | PN | PFEP Description | Chinese name | Comments | Date | Cycle | PN | Chinese name | Comments | Date | Cycle | PN | Name | Chinese name | Comments
2017-09-21 | 11661 | 24286565 | STATOR ASM-DRV MOT (2ND POSN) | 驱动电机定子（第二位置） | 零件损坏，需要更换 | [5 empty] | 2017-08-29 | 1476 | 24277227 | OUTPUT CARRIRER | 输出支架总成 | 更换大连压装的零件，与168#进行对比
2017-09-21 | 11661 | 24274987 | ROTOR ASM-DRV MOT GEN (2ND POSN) - E2xx | 驱动电机转子（第二位置）- E2XX | 零件损坏，需要更换
2017-09-21 | 11661 | 24275239 | SUPPORT ASM-DRV MOT A | 驱动电机支架总成 | 零件损坏，需要更换
2017-09-21 | 11661 | 24285150 | PLATE-VAR LOW CLU BKG | 低档离合器支撑片 | 零件未损坏，零件用于问题排查，故更换新零件
2017-09-21 | 11661 | 24256285 | RING-VAR LOW CLU BKG PLT RET (SELECTIVE) | 低档离合器支撑片可选卡簧 | 零件未损坏，零件用于问题排查，故更换新零件
2017-09-21 | 11661 | 24277227 | CARRIER ASM-OUTPUT | 输出支架总成 | 更换成进口材料零件