## GFE Validation New Daily Log
2017-11-08
▶GFE DYNO Validation Plan&Status
SN | Trans NO. | Trans Status | Eng NO. | Eng Status | Test Item | Cell | 2017 | [7 empty] | 2018 | Target | Trans Cycles | Current % | Test Status | Remark | PCRS | SOT Status | Remark
[7 empty] | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | 1
1 | C9KFG168CQ | Gamma | L2B*170763134 | Gamma | TEDD | PTA | [7 empty] | VSO:22Jan |  | 24000 | 15227 | 63.45% | Ongoing | 0 |  | Yellow | Cooling flow rate not meet test request. Long term solution:Xu Guoqiang/Gao Peiyuan
2 | C9KFG113CQ | Gamma | L2B*170763135 | Gamma | Start&Stop | PTB | [9 empty] | 43708 | 3230 | 7.39% | Running Incident | Issue Date:10/30 Issue Describe:Facility fault Next Step:Fix facility Target Date:TBD Owner:Yao Yuxing |  | Yellow | Cooling flow rate not meet test request. Long term solution:Xu Guoqiang/Gao Peiyuan
3 | C9KFG182CQ | Gamma | L2B*170763133 | Gamma | TEDD | PTC | [9 empty] | 24000 | 5579 | 23.25% | Running Incident | Issue Date:11/6 Issue Describe:Facility Error Next Step:Change 10KΩ resistor Target Date:TBD Owner:Yao Yuxing |  | Yellow | Cooling flow rate not meet test request. Long term solution:Xu Guoqiang/Gao Peiyuan
4 | B2B | Gamma | NA | Gamma | B2B | M 1 | [9 empty] | 185.4 | 0 | 100% | Finished | 0 |  | Green
5 | T9EPG612CQ | Gamma | L2B*161333733* | Gamma | TEDD | GRC | [9 empty] | 24000 | 0 | 0% | Working in Progress | Debugging ,expect to run test on 11/15 |  | Green
6 | C9KFG005CQ | Gamma | L2B*161333732* | Gamma | TEDD | Horiba | [9 empty] | 24000 | 0 | 0% | Working in Progress | Finished debugging,running brief TEDD with Gamma1 transmission,waiting GPS confirm dyno trace. Target Date:11/10 Owner:Wu Chenwen |  | Green
Original Plan
Actual plan
Forecasting finish plan