## GFE Validation New Daily Log
2017-11-10
▶GFE DYNO Validation Plan&Status
SN | Trans NO. | Trans Status | Eng NO. | Eng Status | Test Item | Cell | 2017 | [6 empty] | 2018 | Target | Trans Cycles | Current % | Test Status | Remark | PCRS | SOT Status | Remark
[7 empty] | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1
1 | C9KFG168CQ | Gamma | L2B*170763134 | Gamma | TEDD | PTA | [6 empty] | VSO:22Jan |  | 24000 | 16202 | 67.51% | Ongoing | 0 |  | Yellow | Cooling flow rate not meet test request. Long term solution:Xu Guoqiang/Gao Peiyuan
2 | C9KFG113CQ | Gamma | L2B*170763135 | Gamma | Start&Stop | PTB | [8 empty] | 43708 | 3283 | 7.511% | Ongoing | 0 |  | Yellow | Cooling flow rate not meet test request. Long term solution:Xu Guoqiang/Gao Peiyuan
3 | C9KFG182CQ | Gamma | L2B*170763133 | Gamma | TEDD | PTC | [8 empty] | 24000 | 6195 | 25.81% | Ongoing | 0 |  | Yellow | Cooling flow rate not meet test request. Long term solution:Xu Guoqiang/Gao Peiyuan
4 | B2B | Gamma | NA | Gamma | B2B | M 1 | [8 empty] | 185.4 | 0 | 100% | Finished | 0 |  | Green
5 | T9EPG612CQ | Gamma | L2B*161333733* | Gamma | TEDD | GRC | [8 empty] | 24000 | 0 | 0% | Working in Progress | Debugging ,expect to run test on 11/15 |  | Green
6 | C9KFG005CQ | Gamma | L2B*161333732* | Gamma | TEDD | Horiba | [8 empty] | 24000 | 0 | 0% | Working in Progress | Finished debugging,running brief TEDD with Gamma1 transmission,waiting GPS confirm dyno trace. Target Date:11/10 Owner:Wu Chenwen |  | Green
Original Plan
Actual plan
Forecasting finish plan