## GFE Validation New Daily Log
2017-11-14
▶GFE DYNO Validation Plan&Status
SN | Trans NO. | Trans Status | Eng NO. | Eng Status | Test Item | Cell | 2017 | [6 empty] | 2018 | Target | Trans Cycles | Current % | Test Status | Remark
[7 empty] | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1
1 | C9KFG168CQ | Gamma | L2B*170763134 | Gamma | TEDD | PTA | [6 empty] | VSO:22Jan |  | 24000 | 17170 | 71.54% | Running Incident | Issue Date:11/14. Issue Describe:High Voltage Cable burnt Next Step:Swap High Voltage Cable on 11/20
2 | C9KFG113CQ | Gamma | L2B*170763135 | Gamma | Start&Stop | PTB | [8 empty] | 43708 | 3395 | 7.767% | Ongoing | 0
3 | C9KFG182CQ | Gamma | L2B*170763133 | Gamma | TEDD | PTC | [8 empty] | 24000 | 6327 | 26.36% | Ongoing | 0
4 | T9EPG612CQ | Gamma | L2B*161333733* | Gamma | TEDD | GRC | [8 empty] | 24000 | 0 | 0% | Working in Progress | Debugging ,expect to run test on 11/17.
5 | C9KFG005CQ | Gamma | L2B*161333732* | Gamma | TEDD | Horiba | [8 empty] | 24000 | 0 | 0% | Working in Progress | Running brief TEDD with Gamma1 transmission,waiting NCT phase Trans on 11/15. Owner:Li Xinlong
6 | B2B | Gamma | NA | Gamma | B2B | M 1 | [8 empty] | 185.4 | 0 | 100% | Finished | 0
Original Plan
Actual plan
Forecasting finish plan