## 48V Validation New Daily Log
2017-11-10
▶EPXX eM18 DYNO Validation Plan&Status
[8 empty] | PRC:10April2018 |  |  |  | VSO:30July2019
SN | Trans NO. | Trans Status | Test Item | Cell | 2018 | [6 empty] | 2019 |  | Target | Current % | Test Status | Remark | PRTS | SOT Status | Remark
[5 empty] | 1 | 2 | 3 |  | 4 | 5 | 6 | … | 7
1 | TBD | Beta1 | 油位润滑 效率 高速 | SAGW/华依/GRC | [9 empty] | TBD | 0% | 0 | 0 |  | Yellow | 1、Spin试验和Beta1的试验需要大通软件和标定支持。——Datong 2、需要马上启动后续试验费用PR以支持锁定台架资源，目前无费用和WBS支持。——Shi Xunliang
2 | TBD | Beta1 | 齿轴耐久 | SAGW/华依/GRC | [9 empty] | TBD | 0% | 0 | 0 |  | Yellow
3 | TBD | Beta1 | 差速器耐久 同步器耐久 | SAGW/华依/GRC | [9 empty] | TBD | 0% | 0 | 0 |  | Yellow
4 | TBD | Beta1 | TEDD Start Stop(开发调试) | GRC | [9 empty] | TBD | 0% | Working in Progress | 0 |  | Yellow
Original Plan
Actual plan
Forecasting finish plan

## 48V ss (hidden)
1
| LIW |  | LIW*163528017* |  | MGU
Columns Active (Click to activate) | DCT150 |  |  |  | 116358A00000029
| Test Cell |  | Test Schedule: | Start Stop
| Cycle Goal: | 500000 | Pallet #: | DYPT
| Trans Software: |  | Engine Software:
| PQMS# |  | PON#
|  | Title: | K218 C10T Beta 48V BAS Start Stop Validation
Back up Trans:
| hours | hours/day | Status | Comments
2017-05-01
2017-05-02
2017-05-03 | 0
2017-05-04 | 2035 | 2035 | Running
2017-05-05 | 5135 | 3100 | Running
2017-05-06 | 8235 | 3100 | Running
2017-05-07 | 11335 | 3100 | Running
2017-05-08 | 14435 | 3100 | Running
2017-05-09 | 17535 | 3100 | Running
2017-05-10 | 20552 | 3017 | Running
2017-05-11 | 23569 | 3017 | Running
2017-05-12 | 26586 | 3017 | Running
2017-05-13 | 29603 | 3017 | Running
2017-05-14 | 32620 | 3017 | Running
2017-05-15 | 35637 | 3017 | Running
2017-05-16 | 38654 | 3017 | Running
2017-05-17 | 41671 | 3017 | Running
2017-05-18 | 44688 | 3017 | Running
2017-05-19 | 47705 | 3017 | Running
2017-05-20 | 50722 | 3017 | Running
2017-05-21 | 53739 | 3017 | Running
2017-05-22 | 56756 | 3017 | Running
2017-05-23 | 59770 | 3014 | Running
2017-05-24 | 62128 | 2358 | Running
2017-05-25 | 64486 | 2358 | Running
2017-05-26 | 66844 | 2358 | Running
2017-05-27 | 69202 | 2358 | Running
2017-05-28 | 71560 | 2358 | Running
2017-05-29 | 73918 | 2358 | Running
2017-05-30 | 76276 | 2358 | Running
2017-05-31 | 78634 | 2358 | Running
2017-06-01 | 80992 | 2358 | Running
2017-06-02 | 83350 | 2358 | Running
2017-06-03 | 85708 | 2358 | Running
2017-06-04 | 88066 | 2358 | Running
2017-06-05 | 90424 | 2358 | Running
2017-06-06 | 92782 | 2358 | Running
2017-06-07 | 95140 | 2358 | Running
2017-06-08 | 97498 | 2358 | Running
2017-06-09 | 99850 | 2352 | Running
2017-06-10 | 102581 | 2731 | Running
2017-06-11 | 105312 | 2731 | Running
2017-06-12 | 108043 | 2731 | Running
2017-06-13 | 110774 | 2731 | Running
2017-06-14 | 113505 | 2731 | Running
2017-06-15 | 116236 | 2731 | Running
2017-06-16 | 118967 | 2731 | Running
2017-06-17 | 121698 | 2731 | Running
2017-06-18 | 124429 | 2731 | Running
2017-06-19 | 127160 | 2731 | Running
2017-06-20 | 129891 | 2731 | Running
2017-06-21 | 132622 | 2731 | Running
2017-06-22 | 135353 | 2731 | Running
2017-06-23 | 138084 | 2731 | Running
2017-06-24 | 140815 | 2731 | Running
2017-06-25 | 143546 | 2731 | Running
2017-06-26 | 146277 | 2731 | Running
2017-06-27 | 149000 | 2723 | Running
2017-06-28 | 151380 | 2380 | Running
2017-06-29 | 154520 | 3140 | Running
2017-06-30 | 157610 | 3090 | Running
2017-07-01 | 160800 | 3190 | Running
2017-07-02 | 163900 | 3100 | Running
2017-07-03 | 167000 | 3100 | Running
2017-07-04 | 170000 | 3000 | Running
2017-07-05 | 173260 | 3260 | Running
2017-07-06 | 176400 | 3140 | Running
2017-07-07 | 179410 | 3010 | Running
2017-07-08 | 182600 | 3190 | Running
2017-07-09 | 185600 | 3000 | Running
2017-07-10 | 188780 | 3180 | Running
2017-07-11 | 191810 | 3030 | Running
2017-07-12 | 194920 | 3110 | Running
2017-07-13 | 197850 | 2930 | Running
2017-07-14 | 200520 | 2670 | Running
2017-07-15 | 203300 | 2780 | Running
2017-07-16 | 205590 | 2290 | Running
2017-07-17 | 208220 | 2630 | Running
2017-07-18 | 211280 | 3060 | Running
2017-07-19 | 214435 | 3155 | Running
2017-07-20 | 217600 | 3165 | Running
2017-07-21 | 220720 | 3120 | Running
2017-07-22 | 220720 | 0 | Waiting Manpower
2017-07-23 | 220720 | 0 | Running Incident | Battery simulator restart trouble, supplier fixed
2017-07-24 | 223805 | 3085 | Running
2017-07-25 | 226500 | 2695 | Running
2017-07-26 | 229510 | 3010 | Running
2017-07-27 | 232660 | 3150 | Running
2017-07-28 | 235675 | 3015 | Running
2017-07-29 | 238700 | 3025 | Running
2017-07-30 | 241700 | 3000 | Running
2017-07-31 | 244700 | 3000 | Running
2017-08-01 | 247820 | 3120 | Running
2017-08-02 | 250770 | 2950 | Running
2017-08-03 | 253890 | 3120 | Running
2017-08-04 | 257000 | 3110 | Running
2017-08-05 | 259900 | 2900 | Running
2017-08-06 | 262900 | 3000 | Running
2017-08-07 | 265895 | 2995 | Running
2017-08-08 | 268815 | 2920 | Running
2017-08-09 | 270660 | 1845 | Running
2017-08-10 | 274630 | 3970 | Running
2017-08-11 | 277745 | 3115 | Running
2017-08-12 | 279100 | 1355 | Running
2017-08-13 | 280400 | 1300 | Running
2017-08-14 | 281750 | 1350 | Running
2017-08-15 | 284720 | 2970 | Running
2017-08-16 | 287830 | 3110 | Running
2017-08-17 | 291020 | 3190 | Running
2017-08-18 | 294215 | 3195 | Running
2017-08-19 | 297150 | 2935 | Running
2017-08-20 | 300150 | 3000 | Running
2017-08-21 | 303120 | 2970 | Ongoing
2017-08-22 | 306095 | 2975 | Ongoing
2017-08-23 | 309165 | 3070 | Ongoing
2017-08-24 | 312245 | 3080 | Ongoing
2017-08-25 | 315340 | 3095 | Ongoing
2017-08-26
2017-08-27
2017-08-28 | 324370 | 324370 | Ongoing
2017-08-29 | 326930 | 2560 | Ongoing
2017-08-30 | 329720 | 2790 | Ongoing
2017-08-31 | 331960 | 2240 | Ongoing
2017-09-01 | 334850 | 2890 | Ongoing
2017-09-02
2017-09-03
2017-09-04 | 344000 | 344000 | Ongoing
2017-09-05
2017-09-06 | 350140 | 350140
2017-09-07 | 353325 | 3185 | Ongoing
2017-09-08 | 356540 | 3215 | Ongoing
2017-09-09
2017-09-10
2017-09-11 | 359645 | 359645 | Ongoing
2017-09-12 | 362715 | 3070 | Ongoing
2017-09-13 | 365870 | 3155 | Ongoing
2017-09-14 | 368740 | 2870 | Ongoing
2017-09-15 | 371935 | 3195 | Ongoing
2017-09-16
2017-09-17
2017-09-18 | 375000 | 375000 | Ongoing
2017-09-19 | 377940 | 2940 | Ongoing
2017-09-20 | 380980 | 3040 | Ongoing
2017-09-21 | 384140 | 3160 | Ongoing
2017-09-22 | 387295 | 3155 | Ongoing
2017-09-23 | 393400 | 6105 | Ongoing
2017-09-24
2017-09-25 | 393400 | 393400 | Ongoing
2017-09-26 | 396430 | 3030 | Ongoing
2017-09-27 | 399310 | 2880 | Ongoing
2017-09-28 | 401410 | 2100 | Ongoing
2017-09-29 | 404530 | 3120 | Ongoing
2017-09-30 | 406560 | 2030 | Ongoing
2017-10-01
2017-10-02
2017-10-03
2017-10-04
2017-10-05
2017-10-06
2017-10-07
2017-10-08 | 423000 | 423000 | Ongoing
2017-10-09 | 425000 | 2000 | Ongoing
2017-10-10 | 426285 | 1285 | Working in Progress | 本周试验室有CNAS换证评审，需要进行返拖等一系列试验项目，计划暂停AC1的SS试验5天，相应结束时间推迟至11.5号
2017-10-11 | 426285 | 0 | Working in Progress | Test suspends 5 days for CNAS certification renew
2017-10-12 | 426285 | 0 | Working in Progress | Test suspends 5 days for CNAS certification renew,plan to start test on 10/16.
2017-10-13 | 426285 | 0 | Working in Progress | Test suspends 5 days for CNAS certification renew,plan to start test on 10/16.
2017-10-14 | 426285 | 0 | Working in Progress | Test suspends 5 days for CNAS certification renew,plan to start test on 10/16.
2017-10-15 | 426285 | 0 | Working in Progress | Test suspends 5 days for CNAS certification renew,plan to start test on 10/16.
2017-10-16 | 426285 | 0 | Working in Progress | Test suspends 5 days for CNAS certification renew,plan to start test on 10/17
2017-10-17 | 426285 | 0 | Working in Progress | Test suspends 5 days for CNAS certification renew,plan to start test on 10/17
2017-10-18 | 428980 | 2695 | Ongoing
2017-10-19 | 432125 | 3145 | Ongoing
2017-10-20 | 434970 | 2845 | Ongoing
2017-10-21 | 438110 | 3140 | Ongoing
2017-10-22 | 441285 | 3175 | Ongoing
2017-10-23 | 444430 | 3145 | Ongoing
2017-10-24 | 447580 | 3150 | Ongoing
2017-10-25 | 450487 | 2907 | Ongoing
2017-10-26 | 453695 | 3208 | Ongoing
2017-10-27
2017-10-28
2017-10-29
2017-10-30
2017-10-31
2017-11-01
2017-11-02
2017-11-03
2017-11-04
2017-11-05
2017-11-06
2017-11-07
2017-11-08
2017-11-09
2017-11-10
2017-11-11
2017-11-12
2017-11-13
2017-11-14
2017-11-15
2017-11-16
2017-11-17
2017-11-18
2017-11-19
2017-11-20
2017-11-21
2017-11-22
2017-11-23
2017-11-24
2017-11-25
2017-11-26
2017-11-27
2017-11-28
2017-11-29
2017-11-30
2017-12-01
2017-12-02
2017-12-03
2017-12-04
2017-12-05
2017-12-06
2017-12-07
2017-12-08
2017-12-09
2017-12-10
2017-12-11
2017-12-12
2017-12-13
2017-12-14
2017-12-15
2017-12-16
2017-12-17
2017-12-18
2017-12-19
2017-12-20
2017-12-21
2017-12-22
2017-12-23
2017-12-24
2017-12-25
2017-12-26
2017-12-27
2017-12-28
2017-12-29
2017-12-30
2017-12-31
2018-01-01
2018-01-02
2018-01-03
2018-01-04
2018-01-05
2018-01-06
2018-01-07
2018-01-08
2018-01-09
2018-01-10
2018-01-11
2018-01-12
2018-01-13
2018-01-14
2018-01-15
2018-01-16
2018-01-17
2018-01-18
2018-01-19
2018-01-20
2018-01-21
2018-01-22
2018-01-23
2018-01-24
2018-01-25
2018-01-26
2018-01-27
2018-01-28
2018-01-29
2018-01-30
2018-01-31
2018-02-01
2018-02-02
2018-02-03
2018-02-04
2018-02-05
2018-02-06
2018-02-07
2018-02-08
2018-02-09
2018-02-10
2018-02-11
2018-02-12
2018-02-13
2018-02-14
2018-02-15
2018-02-16
2018-02-17
2018-02-18
2018-02-19
2018-02-20
2018-02-21
2018-02-22
2018-02-23
2018-02-24
2018-02-25
2018-02-26
2018-02-27
2018-02-28
2018-03-01
2018-03-02
2018-03-03
2018-03-04
2018-03-05
2018-03-06
2018-03-07
2018-03-08
2018-03-09
2018-03-10
2018-03-11
2018-03-12
2018-03-13
2018-03-14
2018-03-15
2018-03-16
2018-03-17
2018-03-18
2018-03-19
2018-03-20
2018-03-21
2018-03-22
2018-03-23
2018-03-24
2018-03-25
2018-03-26
2018-03-27
2018-03-28
2018-03-29
2018-03-30
2018-03-31
2018-04-01
2018-04-02
2018-04-03
2018-04-04
2018-04-05
2018-04-06
2018-04-07
2018-04-08
2018-04-09
2018-04-10
2018-04-11
2018-04-12
2018-04-13
2018-04-14
2018-04-15
2018-04-16
2018-04-17
2018-04-18
2018-04-19
2018-04-20
2018-04-21
2018-04-22
2018-04-23
2018-04-24
2018-04-25
2018-04-26
2018-04-27
2018-04-28
2018-04-29
2018-04-30
2018-05-01
2018-05-02
2018-05-03
2018-05-04
2018-05-05
2018-05-06
2018-05-07
2018-05-08
2018-05-09
2018-05-10
2018-05-11
2018-05-12
2018-05-13
2018-05-14
2018-05-15
2018-05-16
2018-05-17
2018-05-18
2018-05-19
2018-05-20
2018-05-21
2018-05-22
2018-05-23
2018-05-24
2018-05-25
2018-05-26
2018-05-27
2018-05-28
2018-05-29
2018-05-30
2018-05-31
2018-06-01
2018-06-02
2018-06-03
2018-06-04
2018-06-05
2018-06-06
2018-06-07
2018-06-08
2018-06-09
2018-06-10
2018-06-11
2018-06-12
2018-06-13
2018-06-14
2018-06-15
2018-06-16
2018-06-17
2018-06-18
2018-06-19
2018-06-20
2018-06-21
2018-06-22
2018-06-23
2018-06-24
2018-06-25
2018-06-26
2018-06-27
2018-06-28
2018-06-29
2018-06-30
2018-07-01
2018-07-02
2018-07-03
2018-07-04
2018-07-05
2018-07-06
2018-07-07
2018-07-08
2018-07-09
2018-07-10
2018-07-11
2018-07-12
2018-07-13
2018-07-14
2018-07-15
2018-07-16
2018-07-17
2018-07-18
2018-07-19
2018-07-20
2018-07-21
2018-07-22
2018-07-23
2018-07-24
2018-07-25
2018-07-26
2018-07-27
2018-07-28
2018-07-29
2018-07-30
2018-07-31
2018-08-01
2018-08-02
2018-08-03
2018-08-04
2018-08-05
2018-08-06
2018-08-07
2018-08-08
2018-08-09
2018-08-10
2018-08-11
2018-08-12
2018-08-13
2018-08-14
2018-08-15
2018-08-16
2018-08-17
2018-08-18
2018-08-19
2018-08-20
2018-08-21
2018-08-22
2018-08-23
2018-08-24
2018-08-25
2018-08-26
2018-08-27
2018-08-28
2018-08-29
2018-08-30
2018-08-31
2018-09-01
2018-09-02
2018-09-03
2018-09-04
2018-09-05
2018-09-06
2018-09-07
2018-09-08
2018-09-09
2018-09-10
2018-09-11
2018-09-12
2018-09-13
2018-09-14
2018-09-15
2018-09-16
2018-09-17
2018-09-18
2018-09-19
2018-09-20
2018-09-21
2018-09-22
2018-09-23
2018-09-24
2018-09-25
2018-09-26
2018-09-27
2018-09-28
2018-09-29
2018-09-30
2018-10-01
2018-10-02
2018-10-03
2018-10-04
2018-10-05
2018-10-06
2018-10-07
2018-10-08
2018-10-09
2018-10-10
2018-10-11
2018-10-12
2018-10-13
2018-10-14
2018-10-15
2018-10-16
2018-10-17
2018-10-18
2018-10-19
2018-10-20
2018-10-21
2018-10-22
2018-10-23
2018-10-24
2018-10-25
2018-10-26
2018-10-27
2018-10-28
2018-10-29
2018-10-30
2018-10-31
2018-11-01
2018-11-02
2018-11-03
2018-11-04
2018-11-05
2018-11-06
2018-11-07
2018-11-08
2018-11-09
2018-11-10
2018-11-11
2018-11-12
2018-11-13
2018-11-14
2018-11-15
2018-11-16
2018-11-17
2018-11-18
2018-11-19
2018-11-20
2018-11-21
2018-11-22
2018-11-23
2018-11-24
2018-11-25
2018-11-26
2018-11-27
2018-11-28
2018-11-29
2018-11-30
2018-12-01
2018-12-02
2018-12-03
2018-12-04
2018-12-05
2018-12-06
2018-12-07
2018-12-08
2018-12-09
2018-12-10
2018-12-11
2018-12-12
2018-12-13
2018-12-14
2018-12-15
2018-12-16
2018-12-17
2018-12-18
2018-12-19
2018-12-20
2018-12-21
2018-12-22
2018-12-23
2018-12-24
2018-12-25
2018-12-26
2018-12-27
2018-12-28
2018-12-29
2018-12-30
2018-12-31
2019-01-01
2019-01-02
2019-01-03
2019-01-04
2019-01-05
2019-01-06
2019-01-07
2019-01-08
2019-01-09
2019-01-10
2019-01-11
2019-01-12
2019-01-13
2019-01-14
2019-01-15
2019-01-16
2019-01-17
2019-01-18
2019-01-19
2019-01-20
2019-01-21
2019-01-22
2019-01-23
2019-01-24
2019-01-25
2019-01-26
2019-01-27
2019-01-28
2019-01-29
2019-01-30
2019-01-31
2019-02-01
2019-02-02
2019-02-03
2019-02-04
2019-02-05
2019-02-06
2019-02-07
2019-02-08
2019-02-09
2019-02-10
2019-02-11
2019-02-12
2019-02-13
2019-02-14
2019-02-15
2019-02-16
2019-02-17
2019-02-18
2019-02-19
2019-02-20
2019-02-21
2019-02-22
2019-02-23
2019-02-24
2019-02-25
2019-02-26
2019-02-27
2019-02-28
2019-03-01
2019-03-02
2019-03-03
2019-03-04
2019-03-05
2019-03-06
2019-03-07
2019-03-08
2019-03-09
2019-03-10
2019-03-11
2019-03-12
2019-03-13
2019-03-14
2019-03-15
2019-03-16
2019-03-17
2019-03-18
2019-03-19
2019-03-20
2019-03-21
2019-03-22
2019-03-23
2019-03-24
2019-03-25
2019-03-26
2019-03-27
2019-03-28
2019-03-29
2019-03-30
2019-03-31
2019-04-01
2019-04-02
2019-04-03
2019-04-04
2019-04-05
2019-04-06
2019-04-07
2019-04-08
2019-04-09
2019-04-10
2019-04-11
2019-04-12
2019-04-13
2019-04-14
2019-04-15
2019-04-16
2019-04-17
2019-04-18
2019-04-19
2019-04-20
2019-04-21
2019-04-22
2019-04-23
2019-04-24
2019-04-25
2019-04-26
2019-04-27
2019-04-28
2019-04-29
2019-04-30
2019-05-01
2019-05-02
2019-05-03
2019-05-04
2019-05-05
2019-05-06
2019-05-07
2019-05-08
2019-05-09
2019-05-10
2019-05-11
2019-05-12
2019-05-13
2019-05-14
2019-05-15
2019-05-16
2019-05-17
2019-05-18
2019-05-19
2019-05-20
2019-05-21
2019-05-22
2019-05-23
2019-05-24
2019-05-25
2019-05-26
2019-05-27
2019-05-28
2019-05-29
2019-05-30
2019-05-31
2019-06-01
2019-06-02
2019-06-03
2019-06-04
2019-06-05
2019-06-06
2019-06-07
2019-06-08
2019-06-09
2019-06-10
2019-06-11
2019-06-12
2019-06-13
2019-06-14
2019-06-15
2019-06-16
2019-06-17
2019-06-18
2019-06-19
2019-06-20
2019-06-21
2019-06-22
2019-06-23
2019-06-24
2019-06-25
2019-06-26
2019-06-27
2019-06-28
2019-06-29
2019-06-30
2019-07-01
2019-07-02
2019-07-03
2019-07-04
2019-07-05
2019-07-06
2019-07-07
2019-07-08
2019-07-09
2019-07-10
2019-07-11
2019-07-12
2019-07-13
2019-07-14
2019-07-15
2019-07-16
2019-07-17
2019-07-18
2019-07-19
2019-07-20
2019-07-21
2019-07-22
2019-07-23
2019-07-24
2019-07-25
2019-07-26
2019-07-27
2019-07-28
2019-07-29
2019-07-30
2019-07-31
2019-08-01
2019-08-02
2019-08-03
2019-08-04
2019-08-05
2019-08-06
2019-08-07
2019-08-08
2019-08-09
2019-08-10
2019-08-11
2019-08-12
2019-08-13
2019-08-14
2019-08-15
2019-08-16
2019-08-17
2019-08-18
2019-08-19
2019-08-20
2019-08-21
2019-08-22
2019-08-23
2019-08-24
2019-08-25
2019-08-26
2019-08-27
2019-08-28
2019-08-29
2019-08-30
2019-08-31
2019-09-01
2019-09-02
2019-09-03
2019-09-04
2019-09-05
2019-09-06
2019-09-07
2019-09-08
2019-09-09
2019-09-10
2019-09-11
2019-09-12
2019-09-13
2019-09-14
2019-09-15
2019-09-16
2019-09-17
2019-09-18
2019-09-19
2019-09-20
2019-09-21
2019-09-22
2019-09-23
2019-09-24
2019-09-25
2019-09-26
2019-09-27
2019-09-28
2019-09-29
2019-09-30
2019-10-01
2019-10-02
2019-10-03
2019-10-04
2019-10-05
2019-10-06
2019-10-07
2019-10-08
2019-10-09
2019-10-10
2019-10-11
2019-10-12
2019-10-13
2019-10-14
2019-10-15
2019-10-16
2019-10-17
2019-10-18
2019-10-19
2019-10-20
2019-10-21
2019-10-22
2019-10-23
2019-10-24
2019-10-25
2019-10-26
2019-10-27
2019-10-28
2019-10-29
2019-10-30
2019-10-31
2019-11-01
2019-11-02
2019-11-03
2019-11-04
2019-11-05
2019-11-06
2019-11-07
2019-11-08
2019-11-09
2019-11-10
2019-11-11
2019-11-12
2019-11-13
2019-11-14
2019-11-15
2019-11-16
2019-11-17
2019-11-18
2019-11-19
2019-11-20
2019-11-21
2019-11-22
2019-11-23
2019-11-24
2019-11-25
2019-11-26
2019-11-27
2019-11-28
2019-11-29
2019-11-30
2019-12-01
2019-12-02
2019-12-03
2019-12-04
2019-12-05
2019-12-06
2019-12-07
2019-12-08
2019-12-09
2019-12-10
2019-12-11
2019-12-12
2019-12-13
2019-12-14
2019-12-15
2019-12-16
2019-12-17
2019-12-18
2019-12-19
2019-12-20
2019-12-21
2019-12-22
2019-12-23
2019-12-24
2019-12-25
2019-12-26
2019-12-27
2019-12-28
2019-12-29
2019-12-30
2019-12-31
2020-01-01
2020-01-02
2020-01-03
2020-01-04
2020-01-05
2020-01-06
2020-01-07
2020-01-08
2020-01-09
2020-01-10
2020-01-11
2020-01-12
2020-01-13
2020-01-14
2020-01-15
2020-01-16
2020-01-17
2020-01-18
2020-01-19
2020-01-20
2020-01-21
2020-01-22
2020-01-23
2020-01-24
2020-01-25
2020-01-26
2020-01-27
2020-01-28
2020-01-29
2020-01-30
2020-01-31
2020-02-01
2020-02-02
2020-02-03
2020-02-04
2020-02-05
2020-02-06
2020-02-07
2020-02-08
2020-02-09
2020-02-10
2020-02-11
2020-02-12
2020-02-13
2020-02-14
2020-02-15
2020-02-16
2020-02-17
2020-02-18
2020-02-19
2020-02-20
2020-02-21
2020-02-22
2020-02-23
2020-02-24
2020-02-25
2020-02-26
2020-02-27
2020-02-28
2020-02-29
2020-03-01
2020-03-02
2020-03-03
2020-03-04
2020-03-05
2020-03-06
2020-03-07
2020-03-08
2020-03-09
2020-03-10
2020-03-11
2020-03-12
2020-03-13
2020-03-14
2020-03-15
2020-03-16
2020-03-17
2020-03-18
2020-03-19
2020-03-20
2020-03-21
2020-03-22
2020-03-23
2020-03-24
2020-03-25
2020-03-26
2020-03-27
2020-03-28
2020-03-29
2020-03-30
2020-03-31
2020-04-01
2018-11-02
2018-11-03
2018-11-04
2018-11-05
2018-11-06
2018-11-07
2018-11-08
2018-11-09
2018-11-10
2018-11-11
2018-11-12
2018-11-13
2018-11-14
2018-11-15
2018-11-16
2018-11-17
2018-11-18
2018-11-19
2018-11-20
2018-11-21
2018-11-22
2018-11-23
2018-11-24
2018-11-25
2018-11-26
2018-11-27
2018-11-28
2018-11-29
2018-11-30
2018-12-01
2018-12-02
2018-12-03
2018-12-04
2018-12-05
2018-12-06
2018-12-07
2018-12-08
2018-12-09
2018-12-10
2018-12-11
2018-12-12
2018-12-13
2018-12-14
2018-12-15
2018-12-16
2018-12-17
2018-12-18
2018-12-19
2018-12-20
2018-12-21
2018-12-22
2018-12-23
2018-12-24
2018-12-25
2018-12-26
2018-12-27
2018-12-28
2018-12-29
2018-12-30
2018-12-31
2019-01-01
2019-01-02
2019-01-03
2019-01-04
2019-01-05
2019-01-06
2019-01-07
2019-01-08
2019-01-09
2019-01-10
2019-01-11
2019-01-12
2019-01-13
2019-01-14
2019-01-15
2019-01-16
2019-01-17
2019-01-18
2019-01-19
2019-01-20
2019-01-21
2019-01-22
2019-01-23
2019-01-24
2019-01-25
2019-01-26
2019-01-27
2019-01-28
2019-01-29
2019-01-30
2019-01-31
2019-02-01
2019-02-02
2019-02-03
2019-02-04
2019-02-05
2019-02-06
2019-02-07
2019-02-08
2019-02-09
2019-02-10
2019-02-11
2019-02-12
2019-02-13
2019-02-14
2019-02-15
2019-02-16
2019-02-17
2019-02-18
2019-02-19
2019-02-20
2019-02-21
2019-02-22
2019-02-23
2019-02-24
2019-02-25
2019-02-26
2019-02-27
2019-02-28
2019-03-01
2019-03-02
2019-03-03
2019-03-04
2019-03-05
2019-03-06
2019-03-07
2019-03-08
2019-03-09
2019-03-10
2019-03-11
2019-03-12
2019-03-13
2019-03-14
2019-03-15
2019-03-16
Maximum Cycles/Day
Average Daily Cycles Calculations
Weekends? | Ran Weekends
Working Days for Average Calculation | #REF!
Total Days Since SOT | 159
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
Note on A2: This document supports up to 15 transmissions at any given time. To hide extra columns, select the column of the given color that you would like to hide, right click, and select "Hide". Similarly, to bring back hidden columns, select the column immediately before and after the hidden column, right click, and select "unhide".
Note on B2: Type Engine RPO here.
Note on D2: Type Engine Number here.
Note on B3: Type Trans RPO here.
Note on D3: Type Transmission Number here.
Note on B4: Select a test cell.
Note on E4: Insert test schedule here.
Note on C5: Insert cycle goal here.
Note on E5: Insert pallet # here.
Note on C6: Type trans software here.
Note on E6: Type engine software here.
Note on C7: Enter PQMS # here.
Note on E7: Insert PON # here.
Note on D9: Type back up transmission number here.
Note on A10: Insert date here. Clicking on the cell and dragging it down to the cell below will automatically fill out the date for the next day. This does not skip weekends, however. Only add the latest date (Do not drag the date past your latest entry) or else the tracking sheet will not see your data. The tracking sheet looks at the latest date, regardless of whether or not there is information in it.
Note on B10: Insert current cycle count here.
Note on C10: Cycles per day is automatically calculated for you.
Note on D10: Select cell status from drop down box.
Note on E10: about cell condition or issues that occurred during the day here.
Note on B1405: Default is set to not include weekends in the average cycles count since 24/7 running is not usually practiced at this time. Change this if the cell commonly runs weekends or if weekend running becomes mandatory.

## 48V start cart DCT (hidden)
| LIW |  | LIW*170468040* |  | MGU
Columns Active (Click to activate) | DCT150 |  | LS163577M2WX0002 |  | 116358A00000031
| Test Cell |  | Test Schedule: | Start Cart
| Cycle Goal: | 500000 | Pallet #: | GRC
| Trans Software: |  | Engine Software:
| PQMS# |  | PON#
|  | Title: | K218 C10T Beta 48V BAS Start Cart Validation
Back up Trans:
| Cycles | Cycles/day | Status | Comments
2017-06-21
2017-06-22
2017-06-23 | 0
2017-06-24 | 1000 | 1000
2017-06-25 | 2000 | 1000
2017-06-26 | 3000 | 1000
2017-06-27 | 4000 | 1000 | Running
2017-06-28 | 4000 | 0 | Running Incident | MGU over current frequently.
2017-06-29 | 4000 | 0 | Running Incident | MGU over current frequently.
2017-06-30 | 5494 | 1494 | Running Incident | MGU over current problem solved. Running incident analysis in progress.
2017-07-01 | 5567 | 73 | Running Incident | MGU over current problem solved. Running incident analysis in progress.
2017-07-02 | 5567 | 0
2017-07-03 | 5567 | 0 | Running Incident | MGU over current problem solved. MGU over power occasionally, analysis in progress.
2017-07-04 | 6620 | 1053 | Running | MGU over power occasionally
2017-07-05 | 7850 | 1230 | Running | MGU over power occasionally
2017-07-06 | 9535 | 1685 | Running | MGU over power occasionally
2017-07-07 | 11306 | 1771 | Running | MGU over power occasionally
2017-07-08 | 13000 | 1694 | Running | MGU over power occasionally
2017-07-09 | 14000 | 1000 | Running | MGU over power occasionally, TVE onsite support.
2017-07-10 | 15074 | 1074 | Running | MGU over power occasionally, TVE onsite support.
2017-07-11 | 15074 | 0 | Work In Progress | Replacing MGU (new status circuit board).
2017-07-12 | 15074 | 0 | Work In Progress | Replacing MGU (new status circuit board).
2017-07-13 | 16960 | 1886 | Running
2017-07-14 | 19460 | 2500 | Running
2017-07-15 | 21700 | 2240 | Running
2017-07-16 | 23159 | 1459 | Running Incident | MGU over current
2017-07-17 | 23159 | 0 | Running
2017-07-18 | 25420 | 2261 | Running
2017-07-19 | 28160 | 2740 | Running
2017-07-20 | 28892 | 732 | Work In Progress | MGU software update, debugging.
2017-07-21 | 30100 | 1208 | Running
2017-07-22 | 33300 | 3200 | Running
2017-07-23 | 36550 | 3250 | Running
2017-07-24 | 39866 | 3316 | Running
2017-07-25 | 42700 | 2834 | Running
2017-07-26 | 43885 | 1185 | Running
2017-07-27 | 46500 | 2615 | Running
2017-07-28 | 49580 | 3080 | Running
2017-07-29 | 52100 | 2520 | Running
2017-07-30 | 54700 | 2600 | Running
2017-07-31 | 57215 | 2515 | Running
2017-08-01 | 58174 | 959 | Running
2017-08-02 | 59815 | 1641 | Running Incident | MGU rev speed warning.
2017-08-03 | 59815 | 0 | Work In Progress | MGU rev speed warning. TVE onsite support, analysis in progress.
2017-08-04 | 60647 | 832 | Running
2017-08-05 | 61471 | 824 | Running Incident | Engine startup failure
2017-08-06 | 61471 | 0 | Running Incident | Engine startup failure
2017-08-07 | 61474 | 3 | Running
2017-08-08 | 64280 | 2806 | Running
2017-08-09 | 66006 | 1726 | Running
2017-08-10 | 68900 | 2894 | Running
2017-08-11 | 71838 | 2938 | Running
2017-08-12 | 74500 | 2662 | Running
2017-08-13 | 76500 | 2000 | Running
2017-08-14 | 77755 | 1255 | Running Incident | No trans output speed in D gear, engine output normal. Abnormal sound from tensioner spring at idle speed, supplier onsite support.
2017-08-15 | 77755 | 0 | Running Incident | No trans output speed in D gear, engine output normal. Tensioner OK.
2017-08-16 | 77755 | 0 | Running Incident | No trans output speed in D gear, engine output normal. New trans ship to GRC today.
2017-08-17 | 79540 | 1785 | Running | No trans output speed in D gear, engine output normal. Replaced trans and test resume. LS163577M2WX0003→LS163577M2WX0002
2017-08-18 | 80833 | 1293 | Running | Replaced trans @ 77755 Cycle
2017-08-19 | 83150 | 2317 | Running
2017-08-20 | 85500 | 2350 | Running
2017-08-21 | 87952 | 2452 | Ongoing
2017-08-22 | 90730 | 2778 | Ongoing
2017-08-23 | 93480 | 2750 | Ongoing
2017-08-24 | 96390 | 2910 | Ongoing
2017-08-25 | 99280 | 2890 | Ongoing
2017-08-26
2017-08-27 |  |  |  | 台架汽油泵故障造成停机约8小时
2017-08-28 | 106930 | 106930 | Ongoing
2017-08-29 | 109700 | 2770 | Ongoing
2017-08-30 | 112580 | 2880 | Ongoing
2017-08-31 | 115490 | 2910 | Ongoing
2017-09-01 | 118370 | 2880 | Ongoing
2017-09-02 |  |  |  | MGU过流报错，停机7小时候后重启实验
2017-09-03
2017-09-04 | 126240 | 126240 | Ongoing
2017-09-05
2017-09-06 | 131400 | 5160
2017-09-07 | 134280 | 2880 | Ongoing
2017-09-08 | 135867 | 1587 | Ongoing | Engine shut off due to engine and MGU speed shuddering last night,restart again,test running normal
2017-09-09
2017-09-10
2017-09-11 | 145830 | 145830 | Ongoing
2017-09-12 | 148710 | 2880 | Ongoing
2017-09-13 | 151588 | 2878 | Ongoing
2017-09-14 | 154265 | 2677 | Ongoing
2017-09-15 | 157170 | 2905 | Ongoing
2017-09-16
2017-09-17
2017-09-18 | 157891 | 157891 | Running Incident | Transmission no output speed in Drive gear | 在发动机启动成功D档零油门时变速箱输出扭矩降到-400左右，发动机加速失败。 之后发现发动机怠速，挂D档变速箱无输出转速。与第一台变速箱情况类似，手动也无法将变速箱两输出轴朝同一方向旋转。
2017-09-19 | 157891 | 0 | Running Incident | Issue date：2017.9.18；Describe:Transmission no output speed in Drive gear;Next action:Analyse data ;Responser:Zhou Xiao
2017-09-20 | 157891 | 0 | Running Incident | Issue date：2017.9.18；Describe:Transmission no output speed in Drive gear;Next action:Analyse data ;Responser:Zhou Xiao
2017-09-21 | 157891 | 0 | Running Incident | Issue date：2017.9.18； Describe:Transmission no output speed in Drive gear; Next action:Plan to replace new transmission 9/22. Responser:GRC
2017-09-22 | 157891 | 0 | Running Incident | Issue date：2017.9.18； Describe:Transmission no output speed in Drive gear; Next action:Plan to replace new transmission 9/22. Responser:GRC
2017-09-23
2017-09-24
2017-09-25 | 157891 | 157891 | Ongoing | Replace new transmission Start to run test
2017-09-26 | 159200 | 1309 | Ongoing |  | 由于蓄电池没电导致PLC报警，控制发动机启动电机（大部分），监测台架机油压力（小部分）
2017-09-27 | 161966 | 2766 | Ongoing
2017-09-28 | 164800 | 2834 | Ongoing
2017-09-29 | 167557 | 2757 | Ongoing
2017-09-30 | 170136 | 2579 | Ongoing
2017-10-01
2017-10-02
2017-10-03
2017-10-04
2017-10-05
2017-10-06
2017-10-07
2017-10-08
2017-10-09 | 182125 | 182125 |  | 因为MGU过压报错，变速箱档位异常，试验暂停。
2017-10-10 | 182125 | 0 | Running Incident | MGU error,transmission gear abnormal, test suspended.
2017-10-11 | 183605 | 1480 | Ongoing |  | 昨晚10点后因为HCU报错,试验暂停。
2017-10-12 | 186119 | 2514 | Ongoing
2017-10-13 | 188745 | 2626 | Ongoing
2017-10-14
2017-10-15
2017-10-16 | 195566 | 195566 | Working in Progress | Change engine cable on 10/16. Owner:Zhou Xiao
2017-10-17 | 196816 | 1250 | Ongoing |  | 今早8:18左右，MGU过压报错，停机1小时，现在正常运行。
2017-10-18 | 199121 | 2305 | Ongoing
2017-10-19 | 201784 | 2663 | Ongoing
2017-10-20 | 204375 | 2591 | Ongoing
2017-10-21
2017-10-22
2017-10-23 | 212324 | 212324 | Ongoing
2017-10-24 | 212324 | 0 | Working in Progress | Change UP6 to UD8,debugging,expected to run 10/25.
2017-10-25 | 212324 | 0 | Working in Progress | Issue Date:10/24 Issue Describe:Can't start engine during Drive Gear Next Step:Flash updated CAL 10/26 Owner:Zhou Xiao
2017-10-26 | 212324 | 0 | Working in Progress | Issue Date:10/24 Issue Describe:Can't start engine during Drive Gear Next Step:Flash updated CAL 10/26 Owner:Zhou Xiao
2017-10-27
2017-10-28
2017-10-29
2017-10-30
2017-10-31
2017-11-01
2017-11-02
2017-11-03
2017-11-04
2017-11-05
2017-11-06
2017-11-07
2017-11-08
2017-11-09
2017-11-10
2017-11-11
2017-11-12
2017-11-13
2017-11-14
2017-11-15
2017-11-16
2017-11-17
2017-11-18
2017-11-19
2017-11-20
2017-11-21
2017-11-22
2017-11-23
2017-11-24
2017-11-25
2017-11-26
2017-11-27
2017-11-28
2017-11-29
2017-11-30
2017-12-01
2017-12-02
2017-12-03
2017-12-04
2017-12-05
2017-12-06
2017-12-07
2017-12-08
2017-12-09
2017-12-10
2017-12-11
2017-12-12
2017-12-13
2017-12-14
2017-12-15
2017-12-16
2017-12-17
2017-12-18
2017-12-19
2017-12-20
2017-12-21
2017-12-22
2017-12-23
2017-12-24
2017-12-25
2017-12-26
2017-12-27
2017-12-28
2017-12-29
2017-12-30
2017-12-31
2018-01-01
2018-01-02
2018-01-03
2018-01-04
2018-01-05
2018-01-06
2018-01-07
2018-01-08
2018-01-09
2018-01-10
2018-01-11
2018-01-12
2018-01-13
2018-01-14
2018-01-15
2018-01-16
2018-01-17
2018-01-18
2018-01-19
2018-01-20
2018-01-21
2018-01-22
2018-01-23
2018-01-24
2018-01-25
2018-01-26
2018-01-27
2018-01-28
2018-01-29
2018-01-30
2018-01-31
2018-02-01
2018-02-02
2018-02-03
2018-02-04
2018-02-05
2018-02-06
2018-02-07
2018-02-08
2018-02-09
2018-02-10
2018-02-11
2018-02-12
2018-02-13
2018-02-14
2018-02-15
2018-02-16
2018-02-17
2018-02-18
2018-02-19
2018-02-20
2018-02-21
2018-02-22
2018-02-23
2018-02-24
2018-02-24 | 212324 | 0
Maximum Cycles/Day |  | 212324
Average Daily Cycles Calculations
Weekends? | Ran Weekends
Working Days for Average Calculation | 28
Total Days Since SOT | 102
2018-01-28 | 0
2018-01-29 | 0
2018-01-30 | 0
2018-01-31 | 0
2018-02-01 | 0
2018-02-02 | 0
2018-02-03 | 0
2018-02-04 | 0
2018-02-05 | 0
2018-02-06 | 0
2018-02-07 | 0
2018-02-08 | 0
2018-02-09 | 0
2018-02-10 | 0
2018-02-11 | 0
2018-02-12 | 0
2018-02-13 | 0
2018-02-14 | 0
2018-02-15 | 0
2018-02-16 | 0
2018-02-17 | 0
2018-02-18 | 0
2018-02-19 | 0
2018-02-20 | 0
2018-02-21 | 0
2018-02-22 | 0
2018-02-23 | 0
2018-02-24 | 0
20 | 0 | 0
Formulas:
Columns Active (Click to activate) = [Columns Active (Click to activate), row below]-1
Columns Active (Click to activate) = NETWORKDAYS(A1363,[Columns Active (Click to activate), row above],[1]Holidays!$A2:A36)
Note on A2: This document supports up to 15 transmissions at any given time. To hide extra columns, select the column of the given color that you would like to hide, right click, and select "Hide". Similarly, to bring back hidden columns, select the column immediately before and after the hidden column, right click, and select "unhide".
Note on B2: Type Engine RPO here.
Note on D2: Type Engine Number here.
Note on B3: Type Trans RPO here.
Note on D3: Type Transmission Number here.
Note on B4: Select a test cell.
Note on E4: Insert test schedule here.
Note on C5: Insert cycle goal here.
Note on E5: Insert pallet # here.
Note on C6: Type trans software here.
Note on E6: Type engine software here.
Note on C7: Enter PQMS # here.
Note on E7: Insert PON # here.
Note on D9: Type back up transmission number here.
Note on A10: Insert date here. Clicking on the cell and dragging it down to the cell below will automatically fill out the date for the next day. This does not skip weekends, however. Only add the latest date (Do not drag the date past your latest entry) or else the tracking sheet will not see your data. The tracking sheet looks at the latest date, regardless of whether or not there is information in it.

## 48V start cart DCT (2) (hidden)
| LIW |  | NA |  | MGU
Columns Active (Click to activate) | DCT150 |  | NA |  | 116358A00000031
| Test Cell |  | Test Schedule: | Start Cart
| Cycle Goal: | 500000 | Pallet #: | GRC
| Trans Software: |  | Engine Software:
| PQMS# |  | PON#
|  | Title: | K218 C10T Beta 48V BAS Start Cart Validation
Back up Trans:
| Cycles | Cycles/day | Status | Comments
2017-06-21
2017-06-22
2017-06-23
2017-06-24
2017-06-25
2017-06-26
2017-06-27
2017-06-28
2017-06-29
2017-06-30
2017-07-01
2017-07-02
2017-07-03
2017-07-04
2017-07-05
2017-07-06
2017-07-07
2017-07-08
2017-07-09
2017-07-10
2017-07-11
2017-07-12
2017-07-13
2017-07-14
2017-07-15
2017-07-16
2017-07-17
2017-07-18
2017-07-19
2017-07-20
2017-07-21
2017-07-22
2017-07-23
2017-07-24
2017-07-25
2017-07-26
2017-07-27
2017-07-28
2017-07-29
2017-07-30
2017-07-31
2017-08-01
2017-08-02
2017-08-03
2017-08-04
2017-08-05
2017-08-06
2017-08-07
2017-08-08
2017-08-09
2017-08-10
2017-08-11
2017-08-12
2017-08-13
2017-08-14
2017-08-15
2017-08-16
2017-08-17
2017-08-18
2017-08-19
2017-08-20
2017-08-21
2017-08-22
2017-08-23
2017-08-24
2017-08-25
2017-08-26
2017-08-27
2017-08-28
2017-08-29
2017-08-30
2017-08-31
2017-09-01
2017-09-02
2017-09-03
2017-09-04
2017-09-05
2017-09-06
2017-09-07
2017-09-08
2017-09-09
2017-09-10
2017-09-11
2017-09-12
2017-09-13
2017-09-14
2017-09-15
2017-09-16
2017-09-17
2017-09-18
2017-09-19
2017-09-20
2017-09-21
2017-09-22
2017-09-23
2017-09-24
2017-09-25
2017-09-26
2017-09-27
2017-09-28
2017-09-29
2017-09-30
2017-10-01
2017-10-02
2017-10-03
2017-10-04
2017-10-05
2017-10-06
2017-10-07
2017-10-08
2017-10-09
2017-10-10
2017-10-11
2017-10-12
2017-10-13
2017-10-14
2017-10-15
2017-10-16
2017-10-17
2017-10-18
2017-10-19
2017-10-20
2017-10-21
2017-10-22
2017-10-23
2017-10-24
2017-10-25
2017-10-26
2017-10-27
2017-10-28
2017-10-29
2017-10-30
2017-10-31
2017-11-01
2017-11-02
2017-11-03
2017-11-04
2017-11-05
2017-11-06
2017-11-07
2017-11-08
2017-11-09
2017-11-10
2017-11-11
2017-11-12
2017-11-13
2017-11-14
2017-11-15
2017-11-16
2017-11-17
2017-11-18
2017-11-19
2017-11-20
2017-11-21
2017-11-22
2017-11-23
2017-11-24
2017-11-25
2017-11-26
2017-11-27
2017-11-28
2017-11-29
2017-11-30
2017-12-01
2017-12-02
2017-12-03
2017-12-04
2017-12-05
2017-12-06
2017-12-07
2017-12-08
2017-12-09
2017-12-10
2017-12-11
2017-12-12
2017-12-13
2017-12-14
2017-12-15
2017-12-16
2017-12-17
2017-12-18
2017-12-19
2017-12-20
2017-12-21
2017-12-22
2017-12-23
2017-12-24
2017-12-25
2017-12-26
2017-12-27
2017-12-28
2017-12-29
2017-12-30
2017-12-31
2018-01-01
2018-01-02
2018-01-03
2018-01-04
2018-01-05
2018-01-06
2018-01-07
2018-01-08
2018-01-09
2018-01-10
2018-01-11
2018-01-12
2018-01-13
2018-01-14
2018-01-15
2018-01-16
2018-01-17
2018-01-18
2018-01-19
2018-01-20
2018-01-21
2018-01-22
2018-01-23
2018-01-24
2018-01-25
2018-01-26
2018-01-27
2018-01-28
2018-01-29
2018-01-30
2018-01-31
2018-02-01
2018-02-02
2018-02-03
2018-02-04
2018-02-05
2018-02-06
2018-02-07
2018-02-08
2018-02-09
2018-02-10
2018-02-11
2018-02-12
2018-02-13
2018-02-14
2018-02-15
2018-02-16
2018-02-17
2018-02-18
2018-02-19
2018-02-20
2018-02-21
2018-02-22
2018-02-23
2018-02-24
2018-02-24
Maximum Cycles/Day |  | 0
Average Daily Cycles Calculations
Weekends? | Ran Weekends
Working Days for Average Calculation | 0
Total Days Since SOT | 0
2018-01-28 | 0 | 0
2018-01-29 | 0 | 0
2018-01-30 | 0 | 0
2018-01-31 | 0 | 0
2018-02-01 | 0 | 0
2018-02-02 | 0 | 0
2018-02-03 | 0 | 0
2018-02-04 | 0 | 0
2018-02-05 | 0 | 0
2018-02-06 | 0 | 0
2018-02-07 | 0 | 0
2018-02-08 | 0 | 0
2018-02-09 | 0 | 0
2018-02-10 | 0 | 0
2018-02-11 | 0 | 0
2018-02-12 | 0 | 0
2018-02-13 | 0 | 0
2018-02-14 | 0 | 0
2018-02-15 | 0 | 0
2018-02-16 | 0 | 0
2018-02-17 | 0 | 0
2018-02-18 | 0 | 0
2018-02-19 | 0 | 0
2018-02-20 | 0 | 0
2018-02-21 | 0 | 0
2018-02-22 | 0 | 0
2018-02-23 | 0 | 0
2018-02-24 | 0 | 0
20 | 0 | #DIV/0!
Formulas:
Columns Active (Click to activate) = [Columns Active (Click to activate), row below]-1
Columns Active (Click to activate) = NETWORKDAYS(A1363,[Columns Active (Click to activate), row above],[1]Holidays!$A2:A36)
Note on A2: This document supports up to 15 transmissions at any given time. To hide extra columns, select the column of the given color that you would like to hide, right click, and select "Hide". Similarly, to bring back hidden columns, select the column immediately before and after the hidden column, right click, and select "unhide".
Note on B2: Type Engine RPO here.
Note on D2: Type Engine Number here.
Note on B3: Type Trans RPO here.
Note on D3: Type Transmission Number here.
Note on B4: Select a test cell.
Note on E4: Insert test schedule here.
Note on C5: Insert cycle goal here.
Note on E5: Insert pallet # here.
Note on C6: Type trans software here.
Note on E6: Type engine software here.
Note on C7: Enter PQMS # here.
Note on E7: Insert PON # here.
Note on D9: Type back up transmission number here.
Note on A10: Insert date here. Clicking on the cell and dragging it down to the cell below will automatically fill out the date for the next day. This does not skip weekends, however. Only add the latest date (Do not drag the date past your latest entry) or else the tracking sheet will not see your data. The tracking sheet looks at the latest date, regardless of whether or not there is information in it.

## 48V start cart 6T35 (hidden)
| C13T |  | LIY*171469025* |  | MGU
Columns Active (Click to activate) | MNU |  | CONUB004AS |  | 1117156A10000006
| Test Cell |  | Test Schedule: | Start Cart
| Cycle Goal: | 500000 | Pallet #: | GRC
| Trans Software: |  | Engine Software:
| PQMS# |  | PON#
|  | Title: | K218 C13T Beta 48V BAS Start Cart Validation
Back up Trans:
| Cycles | Cycles/day | Status | Comments
2017-08-01 |  |  | Work In Progress | Debugging
2017-08-02 |  |  | Work In Progress | Debugging
2017-08-03 |  |  | Work In Progress | Debugging
2017-08-04 |  |  | Work In Progress | Debugging, expect to run on 8/15.
2017-08-05 |  |  | Work In Progress | Debugging, expect to run on 8/15.
2017-08-06 |  |  | Work In Progress | Debugging, expect to run on 8/15.
2017-08-07 |  |  | Work In Progress | Debugging, expect to run on 8/15.
2017-08-08 |  |  | Work In Progress | Debugging, expect to run on 8/15.
2017-08-09 |  |  | Work In Progress | Debugging, expect to run on 8/15.
2017-08-10 |  |  | Work In Progress | Debugging, expect to run on 8/15.
2017-08-11 |  |  | Work In Progress | Debugging, expect to run on 8/15.
2017-08-12 |  |  | Work In Progress | Debugging, expect to run on 8/15.
2017-08-13 |  |  | Work In Progress | Debugging, expect to run on 8/15.
2017-08-14 |  |  | Work In Progress | Debugging, working on MGU software.
2017-08-15 |  |  | Work In Progress | Debugging, working on MGU software.
2017-08-16 |  |  | Work In Progress | Debugging, working on MGU software.
2017-08-17 |  |  | Work In Progress | Debugging, working on MGU software.
2017-08-18 |  |  | Work In Progress | Debugging, working on MGU software.
2017-08-19 |  |  | Work In Progress | Debugging, working on MGU software.
2017-08-20 |  |  | Work In Progress | Debugging, working on MGU software.
2017-08-21 |  |  | Working in Progress | Debugging, working on MGU software. Plan to be ready on 8/25 ---- Jiang Yintian
2017-08-22 |  |  | Working in Progress | Debugging, working on MGU software. Plan to be ready on 8/25 ---- Jiang Yintian
2017-08-23 |  |  | Running Incident | Debugging, working on MGU software. Plan to be ready on 8/25 ---- Jiang Yintian
2017-08-24 |  |  | Running Incident | Debugging, working on MGU software. Plan to be ready on 8/25 ---- Jiang Yintian
2017-08-25 |  |  | Running Incident | Auto-Start doesn't work,plan to solve on 8/30
2017-08-26
2017-08-27
2017-08-28 |  |  | Running Incident | Auto-Start doesn't work,plan to solve on 8/30
2017-08-29 |  |  | Running Incident | Auto-Start doesn't work,plan to solve on 8/30
2017-08-30 |  |  | Running Incident | Auto-Start work not well,checking debugging data,plan to solve on 9/1
2017-08-31 |  |  | Running Incident | Auto-Start work not well,checking debugging data,plan to solve on 9/1
2017-09-01 |  |  | Running Incident | Auto-Start work not well,checking debugging data,plan to solve on 9/1
2017-09-02
2017-09-03
2017-09-04 |  |  | Running Incident | Auto-Start work not well,checking debugging data,plan to solve on 9/6
2017-09-05 |  |  |  | TVE onsite debugging test procedure
2017-09-06 |  |  |  | TVE onsite debugging test procedure
2017-09-07 |  |  |  | TVE onsite debugging test procedure
2017-09-08 |  |  |  | Start to run test
2017-09-09
2017-09-10
2017-09-11 | 1244 | 1244 | Running Incident | Motor overpower and overcurrent,checking power status
2017-09-12 | 1244 | 0 | Running Incident | Motor overpower and overcurrent,under investigation
2017-09-13 | 1244 | 0 | Running Incident | Change new motor and check dyno power,motor supplier flash cal on 9/13. TVE onsite support for motor overpower and overcurrent DTC.
2017-09-14 | 1437 | 193 | Ongoing | Change new capacity due to motor overpower and overcurrent DTC, flash new motor CAL,start to run today | 1、发动机起动失败，由于发动机转速信号丢失，在三秒内未切换running状态，所以报警2、在电机侧并联一个4000μF的电容，此电容损坏，导致后续报电机过流过压故障3、更换了一个电机，今天电机供应商刷新软件4、发动机转速信号丢失发生无规律
2017-09-15 | 2247 | 810 | Ongoing |  | 变速箱油压报警，昨晚7点后停机，现在正常运行。
2017-09-16
2017-09-17
2017-09-18 | 5498 | 5498 | Running Incident | Engine auto-start failed | 发动机自动启动失败次数较多，周六六点后SBN报警后停机。
2017-09-19 | 6861 | 1363 | Ongoing
2017-09-20 | 8612 | 1751 | Ongoing |  | 发动机自动启动失败，今早2点后停机，现在正常运行
2017-09-21 | 11391 | 2779 | Ongoing
2017-09-22 | 13528 | 2137 | Ongoing
2017-09-23
2017-09-24
2017-09-25 | 19369 | 19369 | Ongoing
2017-09-26 | 21719 | 2350 | Ongoing |  | INCA电脑死机
2017-09-27 | 22870 | 1151 | Ongoing |  | 零晨因为发动机自动启动失败，试验暂停，现在正常运行。
2017-09-28 | 25222 | 2352 | Ongoing |  | 今早7点因为发动机自动启动失败停机2小时，现在正常运行。
2017-09-29 | 28138 | 2916 | Ongoing |  | 今早8：17因为发动机自动启动失败停机1小时，现在正常运行
2017-09-30 | 31301 | 3163 | Ongoing
2017-10-01
2017-10-02
2017-10-03
2017-10-04
2017-10-05
2017-10-06
2017-10-07
2017-10-08
2017-10-09 | 57172 | 57172 | Ongoing |  | 早上8:50左右发动机自动启动失败，后由于台架电源问题试验暂停，现在正常运行。在国庆期间发动机自动启动失败次数较频繁，重启后可继续试验。
2017-10-10 | 59517 | 2345 | Ongoing
2017-10-11 | 62263 | 2746 | Ongoing
2017-10-12 | 65304 | 3041 | Ongoing
2017-10-13 | 68259 | 2955 | Ongoing
2017-10-14
2017-10-15
2017-10-16 | 72875 | 72875 | Working in Progress | Issue date:10/21 Issue Description:Engine start failed due to accumulator no power. Next Step:Waiting to start again till accumulator fully charged. Owner:GRC | 周六晚上11:30左右，由于蓄电池没电，发动机启动失败，然后停机。
2017-10-17 | 75539 | 2664 | Ongoing
2017-10-18 | 78381 | 2842 | Ongoing
2017-10-19 | 81066 | 2685 | Ongoing |  | 由于1小时内发动机自动启动失败3次，今早7:30左右，停机，现在正常运行。
2017-10-20 | 83846 | 2780 | Ongoing |  | 今早8:00左右，发动机自动启动失败，停机1小时，现在正常运行。
2017-10-21
2017-10-22
2017-10-23 | 90347 | 90347 | Ongoing |  | 昨天下午2:00左右，连接变速箱的悬置上的螺栓断了，导致试验暂停。现在正在重新安装螺栓，试验暂停。
2017-10-24 | 92656 | 2309 | Ongoing
2017-10-25 | 95511 | 2855 | Ongoing
2017-10-26 | 97876 | 2365 | Ongoing
2017-10-27
2017-10-28
2017-10-29
2017-10-30
2017-10-31
2017-11-01
2017-11-02
2017-11-03
2017-11-04
2017-11-05
2017-11-06
2017-11-07
2017-11-08
2017-11-09
2017-11-10
2017-11-11
2017-11-12
2017-11-13
2017-11-14
2017-11-15
2017-11-16
2017-11-17
2017-11-18
2017-11-19
2017-11-20
2017-11-21
2017-11-22
2017-11-23
2017-11-24
2017-11-25
2017-11-26
2017-11-27
2017-11-28
2017-11-29
2017-11-30
2017-12-01
2017-12-02
2017-12-03
2017-12-04
2017-12-05
2017-12-06
2017-12-07
2017-12-08
2017-12-09
2017-12-10
2017-12-11
2017-12-12
2017-12-13
2017-12-14
2017-12-15
2017-12-16
2017-12-17
2017-12-18
2017-12-19
2017-12-20
2017-12-21
2017-12-22
2017-12-23
2017-12-24
2017-12-25
2017-12-26
2017-12-27
2017-12-28
2017-12-29
2017-12-30
2017-12-31
2018-01-01
2018-01-02
2018-01-03
2018-01-04
2018-01-05
2018-01-06
2018-01-07
2018-01-08
2018-01-09
2018-01-10
2018-01-11
2018-01-12
2018-01-13
2018-01-14
2018-01-15
2018-01-16
2018-01-17
2018-01-18
2018-01-19
2018-01-20
2018-01-21
2018-01-22
2018-01-23
2018-01-24
2018-01-25
2018-01-26
2018-01-27
2018-01-28
2018-01-29
2018-01-30
2018-01-31
2018-02-01
2018-02-02
2018-02-03
2018-02-04
2018-02-05
2018-02-06
2018-02-07
2018-02-08
2018-02-09
2018-02-10
2018-02-11
2018-02-12
2018-02-13
2018-02-14
2018-02-15
2018-02-16
2018-02-17
2018-02-18
2018-02-19
2018-02-20
2018-02-21
2018-02-22
2018-02-23
2018-02-24
2018-02-25
2018-02-26
2018-02-27
2018-02-28
2018-03-01
2018-03-02
2018-03-03
2018-03-04
2018-03-05
2018-03-06
2018-03-07
2018-03-08
2018-03-09
2018-03-10
2018-03-11
2018-03-12
2018-03-13
2018-03-14
2018-03-15
2018-01-14
2018-01-15
2018-01-16
2018-01-17
2018-01-18
2018-01-19
2018-01-20
2018-01-21
2018-01-22
2018-01-23
2018-01-24
2018-01-25
2018-01-26
2018-01-27
2018-01-28
2018-01-29
2018-01-30
2018-01-31
2018-02-01
2018-02-02
2018-02-03
2018-02-04
2018-02-05
2018-02-06
2018-02-07
2018-02-08
2018-02-09
2018-02-10
2018-02-11
2018-02-12
2018-02-13
2018-02-14
2018-02-15
2018-02-16
2018-02-17
2018-02-18
2018-02-19
2018-02-20
2018-02-21
2018-02-22
2018-02-23
2018-02-24
2018-03-15 | 97876 | 0
Maximum Cycles/Day |  | 90347
Average Daily Cycles Calculations
Weekends? | Ran Weekends
Working Days for Average Calculation | 28
Total Days Since SOT | 30
2018-01-28 | 0
2018-01-29 | 0
2018-01-30 | 0
2018-01-31 | 0
2018-02-01 | 0
2018-02-02 | 0
2018-02-03 | 0
2018-02-04 | 0
2018-02-05 | 0
2018-02-06 | 0
2018-02-07 | 0
2018-02-08 | 0
2018-02-09 | 0
2018-02-10 | 0
2018-02-11 | 0
2018-02-12 | 0
2018-02-13 | 0
2018-02-14 | 0
2018-02-15 | 0
2018-02-16 | 0
2018-02-17 | 0
2018-02-18 | 0
2018-02-19 | 0
2018-02-20 | 0
2018-02-21 | 0
2018-02-22 | 0
2018-02-23 | 0
2018-02-24 | 0
20 | 0 | 0
Formulas:
Columns Active (Click to activate) = [Columns Active (Click to activate), row below]-1
Columns Active (Click to activate) = NETWORKDAYS(A1383,[Columns Active (Click to activate), row above],[1]Holidays!$A2:A36)
Note on A2: This document supports up to 15 transmissions at any given time. To hide extra columns, select the column of the given color that you would like to hide, right click, and select "Hide". Similarly, to bring back hidden columns, select the column immediately before and after the hidden column, right click, and select "unhide".
Note on B2: Type Engine RPO here.
Note on D2: Type Engine Number here.
Note on B3: Type Trans RPO here.
Note on D3: Type Transmission Number here.
Note on B4: Select a test cell.
Note on E4: Insert test schedule here.
Note on C5: Insert cycle goal here.
Note on E5: Insert pallet # here.
Note on C6: Type trans software here.
Note on E6: Type engine software here.
Note on C7: Enter PQMS # here.
Note on E7: Insert PON # here.
Note on D9: Type back up transmission number here.
Note on A10: Insert date here. Clicking on the cell and dragging it down to the cell below will automatically fill out the date for the next day. This does not skip weekends, however. Only add the latest date (Do not drag the date past your latest entry) or else the tracking sheet will not see your data. The tracking sheet looks at the latest date, regardless of whether or not there is information in it.