## Sheet1 (2) (hidden)
pickup | RPO | Test | Plant | dyno | Purpose | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug |  | Sep | Oct |  | Nov |  | Dec
| L3A |  |  |  | OTS车，25台
| L3A |  |  |  | PPV车，22台
| L3A |  |  |  | PPAP,300台 | [8 empty] | 1 |  |  | 2
| LYX |  |  |  | PPV车，20台.8月22日
| LYX |  |  |  | PPAP,300台 | [13 empty] | 1 |  | 2
5月30日，共6台（2备+1 cordwood) | LFV | GED | WH | Yantai | 陆磊——住友曲轴（4月15日毛坯到PATAC)，活塞销（已有）验证 朱敏婧-进气凸轮轴、排气凸轮轴、国产化弹簧座
| LFV | GED | WH | Yantai | 陆磊——住友曲轴（4月15日毛坯到PATAC)，活塞销（已有）验证 朱敏婧-进气凸轮轴、排气凸轮轴、国产化弹簧座
| LFV | GETC | WH | FM | 张灏俊——增压器隔热罩，4个月——TBD 钱顾军——油底壳(5月零件可ok） 胡斌-EK气缸垫？
8月15日，共9台 | LFV | GED | WH | MAHLE | 陆磊——活塞加强验证，住友曲轴（4月15日毛坯到PATAC)，活塞销（已有）验证
| LFV | GED | WH | MAHLE | 陆磊——活塞加强验证，住友曲轴（4月15日毛坯到PATAC)，活塞销（已有）验证
| LFV | GEHS | WH | Yantai | 陆磊——活塞加强验证，住友曲轴（4月15日毛坯到PATAC)，活塞销（已有）验证
| LFV | GCSD | WH | Yantai | 陆磊——活塞加强验证，住友曲轴（4月15日毛坯到PATAC)，活塞销（已有）验证
5月4日，共17台 | LYX | GED | WH | PATAC | 朱敏婧——VVT（4月1日到）、凸轮轴（4月1日到）OTS验证 钱鹏——加长螺栓（4月1日到） 唐宁-水泵 D2UC NCT 13台
| LYX | GED | WH | PATAC | 朱敏婧——VVT、凸轮轴OTS验证 钱鹏——加长螺栓 唐宁-水泵
7月20，共4台 | L3A | GED | WH | PATAC | 徐超——油轨，油泵壳体国产化（6月1日到），EGE cooler？
| L3A | GED | WH | Yantai | 徐超——油轨，油泵壳体国产化（6月1日到）
6月30日，共4台 | LFV | GED | Nor | Yantai | 陆磊——CIE南京2线（4月30日毛坯到） 国产化连杆
| LE2 | GED | Nor | Yantai | 陆磊——CIE南京2线（4月30日毛坯到） 国产化连杆 （胡斌——EK气缸垫）
| LE2 | GED | Nor | Yantai | M2验证
| L3G | GED | Nor | Yantai | 陆磊-国产化连杆
造机大致时间
造机时间
特殊零件MRD至泛亚
试验时间
*特殊零件清单必须在MRD前两周锁定
Note on AJ4: MVBP2.0: 8月8日

## GEM CVG
▶ GEM CVG 10T Gamma1 Subsystem Test Plan
SN | ENG NO. | Engine Status | Test Item | Cell | 2017 | [5 empty] | 2018 |  |  |  | Target | Current | Remark | Test Status | SOT Status | Engineer | Test Fuel
[5 empty] | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | .. | 7
1 | Beta:LIV161397003 Gamma:LIV171949011 | Gamma1 | Component friction | AVL PTC1 | [10 empty] | 100% | 60% |  | Ongoing | Already done | Wang libin | 92RON
2 |  | Gamma1 | Component friction | Rig-Friction | [13 empty] | Not start | Already done | Cheng Yi | 92RON
3 | LIV*172129027* | Gamma1 | Exhaust valve thermal survey(Special Valves) | AVL ETC6 | [10 empty] | 100% | 10% |  | Ongoing | Already done | Wang libin | 92RON
4 | LIV*172129027* | Gamma1 | Piston peak temperature(Templug) | AVL ETC6 | [13 empty] | Not start | Already done | Wang libin | 92RON
5 |  | Gamma1 | Thermal Survey (Contain TC shutdown/Warm up) | AVL ETC6 | [13 empty] | Not start | Already done | Wang libin | 92RON
6 | LIV*172119022* | Gamma1 | Damper pulley Tuning | PATAC EP4 | [10 empty] | 100% | 10% |  | Work in progress | Already done | Wang libin | 92RON
7 |  | Gamma1 | Timing Chain Perfomance | PATAC EP2 | [13 empty] | Not start | Already done | Wang libin | 92RON
8 | LIV*172119022* | Gamma1 | TC Oil Sealing Test | PATAC EP4 | [13 empty] | Not start | Already done | Wang libin | 92RON
9 | 10 Cylinder heads | Gamma1 | Port Flow test | Rig-Flow | [10 empty] | 100% | 60% |  | Ongoing | Already done | Cheng Yi
10 |  | Gamma1 | Cooling Rig | Rig-Cooling | [13 empty] | Not start | Already done | Cheng Yi
11 |  | Gamma1 | EGR Cooler fouling | AVL ETC3 | [13 empty] | Not start | Already done | Wang libin | 95RON high gum-GLSD
12 |  | Gamma1 | Injector Coking | AVL ETC3 | [13 empty] | Not start | Already done | Wang libin | 95RON Marketing
13 |  | Gamma1 | Lubrication Test | AVL ETC3 | [13 empty] | Not start | Already done | Wang libin | 95RON Marketing
14 |  | Gamma1 | Lube System Cold evaluation ( really cold -30C， warmup included) | AVL cold | [13 empty] | Not start | Already done | Wang libin | 95RON Marketing
15 | LIV*172809095* | Gamma1 | Tilting Test | AVL SCHRICK | [13 empty] | Not start | Already done | Wang libin | 95RON Marketing
16 |  | Gamma1 | Ventilation System Test | PATAC EP2 | [13 empty] | Not start | Already done | Wang libin | 95RON Marketing
17 |  | Gamma1 | Cooling 3155 | Rig-3155 | [13 empty] | Not start | Already done | Zhang Wei | 95RON Marketing
18 |  | Gamma1 | High oil pressure 3155 | Supplier | [13 empty] | Not start | Already done | Zhang Wei | 95RON Marketing
19 |  | Gamma1 | oil spray 3155 | Supplier | [13 empty] | Not start | Already done | Zhang Wei | 95RON Marketing
19 |  | Gamma1 | Air Leak | Rig-3155 | [13 empty] | Not start | Already done | Zhang Wei | 95RON Marketing
Original Plan
Actual plan
Forecasting finish plan
VSO

## Sheet1 (3)
Test List | Test Site | Test Engineer
Component friction | Rig-Friction | Wang libin
Port Flow test | Rig-Flow | Cheng Yi
Templug | Rig-3155 | Zhang Wei
Thermal Survey (Contain TC shutdown/Warm up) | Rig-Valvetrain
Valvetrain Dynamic Rig test | Rig-Cooling
Timing Chain Perfomance | PATAC EP1
Exhaust valve thermal survey(Special Valves) | PATAC EP2
Damper pulley Tuning | PATAC EP4
Piston peak temperature(Templug) | AVL ETC3
TC Oil Sealing Test | AVL ETC9
TC Shutdown | AVL PTC1
Intake system flow test | AVL ETC6
Exhaust system flow test | AVL cold
spark plug thermal tests(heat range) | AVL SCHRICK
EGR Cooler fouling | Supplier
Injector Coking
Injector temperature survey test
Cooling Rig
Warm up
Oil dipstick calibration
Lubrication Test
Lube System Cold evaluation ( really cold -30C， warmup included)
Tilting Test
Ventilation System Test
Cooling 3155
High oil pressure 3155
oil spray 3155
Air Leak

## Sheet1 (hidden)
RPO | Test | Location | Purpose | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
L3A |  |  | OTS车，25台
L3A |  |  | PPV车，24台
L3A |  |  | PPAP,300台
LYX |  |  | PPV车，20台.暂定6月
LYX |  |  | PPAP,300台
LFV | GED | Yantai | 陆磊——住友曲轴（3月30日到PATAC)，活塞销验证，活塞加强验证
LFV | GED | Yantai | 陆磊——住友曲轴（3月30日到PATAC)，活塞销验证，活塞加强验证
LFV | GETC | MAHLE | 张灏俊——增压器隔热罩
LYX | GED | PATAC | 朱敏婧——VVT凸轮轴OTS验证 陆磊——活塞加强验证 D2UC NCT 估计6台
LYX | GED | PATAC | 朱敏婧——VVT凸轮轴OTS验证 陆磊——活塞加强验证
LFV | GED | Yantai | 陆磊——CIE南京2线
LE2 | GED | Yantai | 陆磊——CIE南京2线 胡斌——EK气缸垫
LE2 | GED | Yantai | M2验证
L3A | GED | PATAC | 徐超——油轨，油泵壳体国产化，EGE cooler？
L3A | GED | Yantai | 徐超——油轨，油泵壳体国产化
造机大致时间
造机时间
特殊零件MRD至泛亚
试验时间
*特殊零件清单必须在MRD前两周锁定