## K218 C13T FE Beta
▶ NGC K218 C13T FE Beta Subsystem Test Plan
SN | ENG NO. | Engine Status | Test Item | Cell | 2017 | [7 empty] | Target | Current | Remark | Test Status | SOT Status | Engineer | Test Fuel
[5 empty] | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | LIY*171299017* | FE | Ventilation System Test | PATAC EP1 | [8 empty] | 100% | 100% |  | Finished | Already done | Wang libin | 95RON Marketing
2-1 | LIY*171579042* | FE | Lubrication Test | AVL ETC6 | [8 empty] | 100% | 100% |  | Finished | Already done | Wang libin | 95RON Marketing
3 | 3 Cylinder heads | FE | Port Flow test | Rig-Flow | [8 empty] | 100% | 100% |  | Finished | Already done | Wang libin | 95RON Marketing
4 | Engine Buck | FE | Valvetrain Dynamic Rig test | Rig-Valvetrain | [8 empty] | 100% | 100% |  | Finished | Already done | Cheng Yi | 95RON Marketing
5 | LIY-171669040 | FE | Component friction | Rig-Friction | [8 empty] | 100% | 10% |  | Ongoing | Already done | Wang libin | 95RON Low FD
6 | Engine Buck | FE | Cooling Rig | Rig-Cooling | [8 empty] | 100% | 100% |  | Finished | Already done | Cheng Yi | 95RON Marketing
7 | LIY*172049055* | FE | TC Oil Sealing Test | PATAC EP2 | [8 empty] | 100% | 10% |  | Ongoing | Already done | Cheng Yi | 95RON Marketing
8 | LIY-171989047 | FE | Thermal Survey (Contain TC shutdown/Warm up) | AVL ETC6 | [8 empty] | 100% | 100% |  | Finished | Already done |  | 95RON Marketing
Wang libin
9 | LIY*171569034* | FE | Exhaust valve thermal survey(Special Valves) | AVL ETC6 | [8 empty] | 100% | 100% |  | Finished | Already done |  | 95RON Marketing
Wang libin
10 | LIY*171299017* | FE | Piston peak temperature(Templug) | AVL ETC6 | [8 empty] | 100% | 100% |  | Finished | Already done |  | 92RON marketing
Wang libin
11 | LIY*171709041* | FE | Timing Chain Perfomance | PATAC EP1 | [8 empty] | 100% | 95% |  | Ongoing |  | Cheng Yi | 95RON Marketing
12 | LIY-171669040 | FE | Damper pulley Tuning | AVL ETC6 | [8 empty] | 100% | 100% |  | Finished |  | Wang libin | 92RON marketing
2-2 | LIY*171579042* | FE | Lube System Cold evaluation ( really cold -30C， warmup included) | AVL ETC6 | [8 empty] | 100% | 0% |  | Not start | Already done | Wang libin | 95RON Marketing
Original Plan
Actual plan
Forecasting finish plan
Gamma DC

## Sheet1
Test List | Test Site | Test Engineer
Component friction | Rig-Friction | Wang libin
Port Flow test | Rig-Flow | Cheng Yi
Templug | Rig-3155
Thermal Survey (Contain TC shutdown/Warm up) | Rig-Valvetrain
Valvetrain Dynamic Rig test | Rig-Cooling
Timing Chain Perfomance | PATAC EP1
Exhaust valve thermal survey(Special Valves) | PATAC EP2
Damper pulley Tuning | PATAC EP4
Piston peak temperature(Templug) | AVL ETC3
TC Oil Sealing Test | AVL ETC9
TC Shutdown | AVL PTC1
Intake system flow test | AVL ETC6
Exhaust system flow test
spark plug thermal tests(heat range)
EGR Cooler fouling
Injector Coking
Injector temperature survey test
Cooling Rig
Warm up
Oil dipstick calibration
Lubrication Test
Lube System Cold evaluation ( really cold -30C， warmup included)
Tilting Test
Ventilation System Test
Cooling 3155
High oil pressure 3155
oil spray 3155
Air Leak