## 48V Validation New Daily Log
2017-11-13
▶48V NGC13T+6T35 DYNO Validation Plan&Status
VSO:10Dec2018
SN | Trans NO. | Trans Status | Test Item | Cell | [6 empty] | 2018 | [6 empty] | Target | Current % | Test Status | Remark
[5 empty] | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 |  | … | 12
1 | CONUB004AS | 6T35 BETA | Start Cart | GRC | [13 empty] | 500000 cycles | 27.14% | Working in Progress | Issue Describe:Dyno can't receive PE CAN signal after flash ECU Next Step:Swap new software Target Date:TBD Owner:UAES
Original Plan
Actual plan
Forecasting finish plan