## SGE LFV
▶ MY21_D2UC_SGE LFV Gamma_DYNO Subsystem Test Daily Report
SN | ENG NO. | Engine Status | Test Item | Cell | 2017 |  |  |  |  | 2018 |  |  | Target | Current | Remark | Test Status | SOT Status | Engineer | Test Fuel
[5 empty] | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3
1 | LYX*153233005* | Gamma | Exhaust valve thermal survey(Real time) | AVL ETC3 | [8 empty] | 100% | 0% |  | Ongoing | NA | Wang libin | 92RON marketing
2 |  | Gamma | Thermal Survey (Contain TC shutdown/Warm up) | AVL PTC1 | [11 empty] | Not start | NA | Wang libin | 95RON Marketing
3 | [16 empty] | NA
NA
Original Plan
Actual plan
Forecasting finish plan
Gamma DC

## Sheet1
Test List | Test Site | Test Engineer
Component friction | Rig-Friction | Wang libin
Port Flow test | Rig-Flow | Cheng Yi
Templug | Rig-3155
Thermal Survey (Contain TC shutdown) | Rig-Valvetrain
Valvetrain Dynamic Rig test | Rig-Cooling
Timing Chain Perfomance | PATAC EP1
Exhaust valve thermal survey(Special Valves) | PATAC EP2
Exhaust valve thermal survey(Real time)
Damper pulley Tuning | PATAC EP4
Piston peak temperature(Templug) | AVL ETC3
TC Oil Sealing Test | AVL ETC9
TC Shutdown | AVL PTC1
Intake system flow test | AVL ETC6
Exhaust system flow test
spark plug thermal tests(heat range)
EGR Cooler fouling
Injector Coking
Injector temperature survey test
Cooling Rig
Warm up
Oil dipstick calibration
Lubrication Test
Lube System Cold evaluation ( really cold -30C， warmup included)
Tilting Test
Ventilation System Test
Cooling 3155
High oil pressure 3155
oil spray 3155
Air Leak